## Completed
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
5 |  |  |  |  | Project Name: Reduce and Control Utilization of Certified Home Health Agency Services Division Lead: DHCF Team Lead: Charles Tobey Add'l Staff: Tim Casey Description: To control utilization and reduce costs, the proposal will transition long-term CHHA patients to Managed Long Term Care. | -100 | Completed
PER PATIENT SPENDING LIMITS
| 2011-03-15 | P | P | P | Request updated CHHA paid claims data for base year (CY 2009)
| 2011-03-22 | P | P | P | Determine if preliminary caps will be implemented by adjusting provider rates or provider payments.
| 2011-03-30 | P | P | P | Calculate Provider Caps and interim rate/payment adjustments.
| 2011-04-01 | P | P | P | Work with BHOFA staff to prepare necessary State Plan Amendment materials.
| 2011-04-01 | P | P | P | Determine if regulations are needed for Provider Caps - if so, work with legal staff to prepare regs. and determine public notice requirements.
| 2011-04-11 | P | P | P | 10 days after legislation approved: Send Dear Administrator Letter to providers regarding caps (if/when budget approved).
| 2011-04-15 | P | P | P | Work with DOH Division of Systems and eMedNY staff to determine systems requirements.
| 2011-04-19 | P | P | P | Submit State Plan Amendment 11-50 to BHOFA for processing to CMS.
| 2011-04-29 | P | P | P | Contact DOH Managed Care staff to discuss potential issues involving accelerated movement of LT patients from CHHAs to MLTC.
| 2011-05-15 | P | P | P | Distribute additional data used in calculation of caps to providers via HCS website.
| 2011-05-25 | P | P | P | Meet with Division of Systems and Medicaid Financial Management to discusss recoupment issues/strategy.
| 2011-06-23 | P | P | P | Home Care Webinar (Briefing on 2011-12 Enacted Budget Actions)
| 2011-08-26 | P | P | P | Review claims data for April 2011 through July 2011 to determine if per-patient spending has decreased for specific providers. Inform providers of resulting adjustments to claims payment reduction percentages.
| 2011-08-30 | P | P | P | CMS approval of SPA
| 2011-09-07 | P | P | P | On or before 9/7/11 providers have the opportunity to discuss with the Department the information provided on 8/26/11 to evaluate the progress they have made in per-patient spending.
| 7/15/11 8/1/11 9/22/11 | P | P | P | Send Dear Administrator Letter to all providers, notifying them of CMS approval and schedule for implementing payment reductions on eMedNY.
| 10/1/11 10/20/11 10/28/11 | P | P | P | Provide all CHHAs with preliminary updates on provider progress toward reducing utilization; re-evaluate payment reduction percentages for affected CHHAs based on latest available data.
| 2011-11-20 | P | P | P | Re-evaluate payment reduction percentages for affected CHHAs based on latest available data.
| 9/15/11 10/31/11 12/1/11 | P | P | P | Analyze possible adjustments to MLTC rates due to increase in long-term patients transitioning from CHHAs.
| 2011-12-20 | P | P | P | Re-evaluate payment reduction percentages for affected CHHAs based on latest available data.
| 2012-02-08 | P | P | P | Re-evaluate payment reduction percentages for affected CHHAs based on latest available data.
| 1/1/12 1/20/12 2/8/12 2/24/12 | P | P | P | Provide all CHHAs with updates on provider progress toward reducing utilization; re-evaluate payment reduction percentages for affected CHHAs based on latest available data.
| 2012-03-01 | P | P | P | Re-evaluate payment reduction percentages for affected CHHAs based on latest available data.
| 2012-04-01 | P | P | P | Re-evaluate payment reduction percentages for affected CHHAs based on latest available data.
| 4/1/2012 4/20/12 5/10/12 | 8 | 8 | 8 | Provide all CHHAs with updates on provider progress toward reducing utilization.
| 7/1/2012 7/20/12 | 8 | 8 | 8 | Provide all CHHAs with preliminary data on utilization during FY 2011-12.
| 2012-10-01 | 8 | 8 | 8 | Final reconciliation for 4/1/11-3/31/12 - calculate actual savings vs. target.
EPISODIC PAYMENT SYSTEM
| 2011-05-15 | P | P | P | Work with BHOFA staff to prepare necessary State Plan Amendment materials.
| 2011-06-01 | P | P | P | Determine if regulations are needed for Provider Caps - if so, work with legal staff to prepare regs. and determine public notice requirements.
| 2011-07-01 | P | P | P | Determine systems requirements.
| 7/1/11 7/26/11 | P | P | P | Meet with industry representatives to plan for testing and provider software requirements.
| 8/9/11 8-16-11 | P | P | P | Followup meeting with industry representatives
| 2011-08-25 | P | P | P | Followup meeting with industry representatives
| 2011-09-19 | P | P | P | Followup meeting with industry representatives
| 6/1/11 6/10/11 8-1-11 10-1-11 | P | P | P | Formally Submit State Plan Amendment in Draft Form.
| 10/1/11 10/15/11 | P | P | P | Finalize base price, CMI etc. from base year data (2009).
| 10/17/11 11/10/11 | P | P | P | On 11/10/11 conduct a webinar for CHHA providers and vendors to provide implementation briefing.
| 12/1/11 12/8/11 1/7/12 | P | P | P | Submit final SPA and reg
| 2011-12-31 | P | P | P | Provide detailed billing instructions to agencies
| 2011-12-31 | P | P | P | Complete system design and begin testing
| 2012-02-08 | P | P | P | Provide new Wage Index Factors and Weighted Average Rates to all CHHAs and software vendors.
| 2012-02-28 | P | P | P | Provide Guidelines to providers for application of Medicaid Spend Down/Surplus amounts to episodic claims.
| 2012-02-29 | P | P | P | Provide new Wage Index Factors and Weighted Average Rates to DOH Division of Systems.
| 2012-03-05 | P | P | P | Submit episodic payment rates to Division of Budget for approval.
| 3/1/2012 3/15/12 4/10/12 | P | P | P | Transmit episodic rates to eMedNY.
| 2012-04-30 | P | P | P | Receive approval from CMS.
| 4/1/12 5/1/12 | P | P | P | Implement episodic system.
| 1/1/13 2/1/13 | P | P | P | Evaluate data from first six months of episodic system - estimate savings.
| 7/1/13 8/1/13 | P | P | P | Evaluate date from full year of new system - compare savings to target.
6 |  |  |  |  | Project Name: Reduce Medicaid Managed Care and Family Health Plus Profit (from 3% to 1%) Division Lead: DMC Team Lead: Paul Souliske Add'l Staff: James DeMatteo Description: Reduce the profit component included in the plan rates from 3% to 1% for the Medicaid and Family Health Plus Managed Care Programs. | -103.13 | Completed
REVISE PART 98-1.11(b) & (e)
| 2011-03-11 | P | P | P | Submitted regulatory Concept Paper to Regulatory Affairs Unit (RAU)
| 2011-03-16 | P | P | P | Present Concept Paper to Regulatory Affairs Committee
| 2011-04-22 | P | P | P | Prepare Regulatory package and submits to RAU
| 2011-04-29 | P | P | P | RAU Submits Reg Package to DLA for approval
| 5/20/11 6/8/11 6/22/11 | P | P | P | RAU seeks Commissioner's approval and files rule with Dept of State
| 5/31/11 6/22/11 7/6/11 | P | P | P | Emergency Rule filed with the Department of State
CALCULATE REVISED PREMIUM RATES
| 8/1/11 8/15/11 8/25/11 9/1/11 9/14/11 | P | P | P | Implement all changes to rates effective 4/1/11 (marketing, trend reduction, surplus reduction, inpatient changes, etc) & add pharmacy to 10/1/11 rates
| 8/15/11 8/25/11 9/1/11 9/14/11 9/15/11 | P | P | P | Submit Rates to DOB for approval
| 9/12/11 9/15/11 9/21/11 | P | P | P | DOB Approval
| 2011-09-19 | P | P | P | Mercer rate certification letter
| 9/26/11 9/14/11 9/15/11 | P | P | P | Submit to CMS for approval
| 10/24/11 9/20/11 9/23/11 | P | P | P | Mail/Post rates after CMS approval and all needed changes have been made to model contract and 1115 waiver (see MRT 1458)
10 |  |  |  |  | Project Name: Eliminate Marketing Costs From Medicaid Managed Care and Family Health Plus Premiums Division Lead: DMC Team Lead: Adella Lamb Additional Staff: James DeMatteo Description: Eliminate the marketing component from the Medicaid and Family Health Plus Rates | -22.46 | Completed
CALUCATE REVISED PREMIUM RATES (note completion of premium rate changes will reflect impact of multiple MRTs)
| 2011-03-16 | P | P | P | meet with trade associations todiscuss marketing carve-out
| 2011-04-01 | P | P | P | calculate marketing carve-out component from rate
| See MRT # 6 |  |  |  | Rate Implementation
REVISE MODEL CONTRACT
| 4/1/11 6-1-11 6/24/11 | P | P | P | Send marketing notice to plans and counties
| 4/1/11 6/1/11 6/22/11 | P | P | P | Contract changes drafted
| 6/1/11 7/1/11 8/1/11 9/10/11 11/1/11 1/31/12 | P | P | P | Section 11 and Appendix D revisions of model contract approved by by OSC
11 |  |  |  |  | Project Name: Bundle Pharmacy into Medicaid Managed Care Division Lead: DFPP Team Lead: Kim Leonard Additional Staff: Adella Lamb, Jennifer Dean Description: Move the NYS Medicaid Pharmacy program under the management of Medicaid managed Care to leverage additional clinical and fiscal benefits | -94.41 | Completed
ADMINISTRATIVE
| 2011-04-01 | P | P | P | Obtain enabling legislation
| 2011-03-10 | P | P | P | Determine Federal Public Notice needs
| 2011-03-10 | P | P | P | Amend 1115 Waiver for MMC
| 2011-03-10 | P | P | P | Amend 1115 Waiver for Family Health Plus
EVOLUTION
| 2011-03-28 | P | P | P | Submit evolution project
| 2011-06-15 | P | P | P | Coordinate pharmacy claim data exchange with MMC/FHP plans
| 2011-08-19 | P | P | P | Establish process for pharmacy encounter data submission to fiscal agent
| 2011-10-01 | P | P | P | Implement EP1605 Bundle Pharmacy into Medicaid Managed Care
ELIGIBILITY SYSTEM CHANGES
| 2011-05-15 | P | P | P | Submit system change request to eliminate CBIC cards for FHP beneficiaries
| 2011-06-15 | P | P | P | Resolve all outstanding system issues
| 2011-06-20 | P | P | P | Submit SA to inhibit card code generator for FHP enrollees
| 2011-06-27 | P | P | P | Submit SA to convert existing FHP enrollees
| 2011-08-01 | P | P | P | Coding and development complete
| 2011-08-22 | P | P | P | Eligibility system testing completed
| 10/1/11 10/18/11 | P | P | P | CBIC cards no longer produced for existing FHP enrollees
| 2011-10-01 | P | P | P | Complete FHP card code conversion for upstate
| 10/22/11 11/21/11 | P | P | P | Begin conversion of card code downstate
| 12/3/11 12/7/11 12/23/11 | P | P | P | Complete FHP card code conversion for downstate
PROGRAM DEVELOPMENT
| 2011-04-20 | P | P | P | Begin ongoing MMC Operational Issues Conference Calls
| 2011-05-02 | P | P | P | Determine scope of benefits for MMC
| 2011-05-02 | P | P | P | Determine scope of benefits for FHP
| 2011-05-13 | P | P | P | Identify transition issues
| 2011-05-20 | P | P | P | Establish transition policy and guidance
| 2011-05-27 | P | P | P | MMC/FHP transition procedures/policies and timeline issued to plans
| 2011-06-01 | P | P | P | Notification to Medicaid Prescriber Education Program
| 2011-07-01 | P | P | P | MMC/FHP ID card issuance
| 2011-07-06 | P | P | P | MMC/FHP evaluation of pharmacy data file by MMC/FHP plans to ensure transition
| 7/6/11 7/10/11 7/25/11 9/6/11 | P | P | P | Assess necessary cost report changes
| 7/6/2011 7/10/11 7/25/11 | P | P | P | Require transition policy/identification of issues from MMC/FHP plans
| 7/6/11 7/10/11 7/25/11 | P | P | P | State to evaluate transition plan for coverage and access
| 2011-08-12 | P | P | P | Evaluate plan contractual requirements
| 7/27/11 8/17/11 | P | P | P | State review/approval of transition plan completed
| 2011-08-23 | P | P | P | CSC Call Center staff training
| 2011-09-02 | P | P | P | Develop process for handling issues post 10/1 implementation
| 2011-09-02 | P | P | P | Develop Emergency process for at counter issues
| 9/2/11 9/15/11 | P | P | P | Provide pharmacy providers with MC/FHP billing information
CONTRACT
| 6/10/11 6/17/11 | P | P | P | Notification of contract changes to MMC plans
| 6/10/11 6/17/11 | P | P | P | Notification of contract changes to FHP plans
| 2011-08-05 | P | P | P | Amend MMC contracts to include pharmacy benefit
| 2011-08-05 | P | P | P | Amend FHP contracts to include pharmacy benefit
| See MRT # 6 |  |  |  | Rate Implementation
| 10/1/11 11/1/11 11/15/11 | P | P | P | Implement cost report changes
ELIGIBLITY
| 2011-08-05 | P | P | P | Establish an eligiblity feed to MMC plans
| 2011-08-05 | P | P | P | Establish an eligiblity feed to FHP plans
| 2011-09-02 | P | P | P | Determine eligible MMC population (including guarantee MMC)
| 2011-09-02 | P | P | P | Determine eligible FHP population (including guarantee FHP)
NOTIFICATIONS
| 2011-04-08 | P | P | P | Determine if "reduction of benefits" letter is required to beneficiaries
| 2011-05-15 | P | P | P | Develop modifications for beneficiary coverage letter
| 2011-06-06 | P | P | P | Participate in FE Conference Call
| 2011-07-01 | P | P | P | Develop beneficiary notification
| 2011-07-08 | P | P | P | Submit Medicaid Update article to alert prescribers/pharmacies
| 2011-07-08 | P | P | P | Develop poster/notification for MNY update
| 2011-07-22 | P | P | P | Approved beneficiary notification translated
| 8/2/2011 8/25/11 | P | P | P | Mail beneficary notification
| 2011-08-12 | P | P | P | Provide Medicaid Helpline staff training information
| 7/1/11 8/2/11 8/24/11 | P | P | P | Participate in MTAG conference call with LDSS
| 2011-08-05 | P | P | P | Develop GIS for LDSS
| 2011-08-05 | P | P | P | Notification to Facilitated enrollers
| 2011-08-05 | P | P | P | Notify SUNY FE trainers of program changes
| 2011-08-05 | P | P | P | Notification to other state programs
| 2011-08-12 | P | P | P | Determine changes needed for MMC/FHP website
| 2011-08-12 | P | P | P | Determine changes needed for eMedny website and provider manuals
| 2011-08-12 | P | P | P | Determine changes needed for DOH/pharmacy website
| 2011-08-12 | P | P | P | Determine changes for MMC brochures, materials, etc…
| 2011-08-12 | P | P | P | Determine changes for FHP brochures, materials, etc…
REBATE COLLECTION
| 2011-04-15 | P | P | P | Establish rebate workgroup to include DFPP, CSC, MC staff
| 2011-08-05 | P | P | P | Guidance to plans regarding forumulary development and management
| 2011-08-05 | P | P | P | Establish process for OBRA rebate program administration
| 2011-08-05 | P | P | P | Determine process for rebate collection
| 2011-08-05 | P | P | P | Identify MMC/FHP data encounter contacts needed for data issues
| 2011-08-26 | P | P | P | Process for MMC/FHP plans to provide drug data
| 2011-08-26 | P | P | P | Data extract process
| 2011-09-09 | P | P | P | Process to create and mail invoices
| 2011-09-09 | P | P | P | Process for dispute resolution
| 2011-09-16 | P | P | P | Notification to drug manufacturers
13 |  |  |  |  | Project Name: Preschool/School Supportive Health Services (SSHSP) Cost Study Division Lead: DFPP Team Lead: Constance Donohue Description: Increase federal Medicaid funding by determining actual costs incurred by school districts and counties in providing SSHSP services including transportation | -50 | Completed-Jan 2016
| 2011-01-11 | P | P | P | Draft Article VII language
| 2011-02-28 | P | P | P | Transmit final Article VII language to DOB
| 2011-03-15 | P | P | P | Begin drafting solicitation documents
| 2011-03-30 | P | P | P | Public Notice date
| 2011-04-01 | P | P | P | Authorizing legislation passed
| 2011-05-10 | P | P | P | Submit B-1184
| 2011-05-16 | P | P | P | Initiate clearance process
| 5/6/11 5-20-11 6-7-11 6-13-11 7-26-11 | P | P | P | Post solicitation documents on DOH website
| 5/13/11 5/27/11 6-14-11 6-20-11 8-2-11 | P | P | P | Bidders' questions due
| 5/20/11 6-3-11 6-21-11 8-16-11 8-23-11 | P | P | P | DOH responds to bidders' questions
| 6/6/11 6-20-11 7-8-11 7-13-11 8-30-11 9-7-11 | P | P | P | Proposals due (30 days)
| 6/27/11 7-15-11 9-9-11 9/14/11 9-27-11 | P | P | P | DOH completes review/evaluation of proposals
| 7/1/11 7-22-11 7-29-11 9-8-11 9/21/11 10/8/11 10/29/11 11/14/11 | P | P | P | DOH internal approval/contractor; sign contract
| 5/13/11 6-1-11 6-10-11 6-14-11 7/21/11 7/29/11 8-31-11 9-7-11 9/15/11 9-30-11 10-29-11 11-18-11 12-14-11 | P | P | P | Targeted SPA submission date
| 7/2/11 7-25-11 7-29-11 9-15-11 9/22/11 10/3/11 10/8/11 10/29/11 12/1/11 12/6/11 12/19/11 | P | P | P | Meet with contractor/contractor work begins
| 7/15/11 8-1-11 8-15-11 9-29-11 11/10/11 11/30/11 12/30/11 1/18/12 | P | P | P | Conduct cost study (contractor; coordinate with State Education Department)
| 2012-02-14 | P | P | P | Begin meetings with stakeholders to review new SSHSP reimbursement methodology
| 2/15/12 2/24/12 | P | P | P | Submit time study to CMS
| 9/15/11 10-28-11 1-31-12 3/1/12 | P | P | P | Notify SSHSP providers of new reimbursement methodology
| 7/8/11 8-1-11 9-30-11 10-29-11 11/15/11 12/15/11 2/15/12 2/29/12 4/1/12 | P | P | P | Submit (transportation) study design to CMS for review per SPA #09-61
| 9/1/11 9-10-11 10-23-11 1-31-12 2/15/12 | 8 | 8 | 8 | Submit updated proposed rates to CMS
| 9/15/11 10-28-11 1-31-12 2/28/12 | 8 | 8 | 8 | Update rates in eMedNY
| 2012-04-01 | P | P | P | Implement random moment time study in school districts, counties and section 4201 schools
| 10/1/11 11-15-11 1-31-12 2/28/12 4/1/12 6/15/12 7/13/12 | 8 | 8 | 8 | Implement cost-settled SSHSP reimbursement |  | Pending SPA approval, will be implemented retroactively.
| 4/1/12 6/15/12 7/13/12 | 8 | 8 | 8 | SSHSP Certified Public Expenditure Local District Sharing (Part D, Section 37-38) |  | Pending SPA approval, will be implemented retroactively.
| 9/30/11 12-31-11 2-15-12 3/30/12 4/16/12 5/1/12 6/15/12 7/13/12 10/1/12 12/1/12 | 8 | 8 | 8 | SPA approved |  | Sent RAI responses to CMS 5/17/12. Received additional RAIs on 8/2/12. Responses were submitted to CMA 9/17/12. Conference calls TBA with CMS were to begin the week of 9/10/12. CMS grouped call topics; calls will begin in November 2012. CMS-DOH-SED and NYCDOE met on 11/14/12.
Based on discussions with CMS, SPA 11-39 will be separated (SPAs for the rest of the state, counties, and NYC) as follows: SPA 11-39A - Rest of State school districts (school age) - CPE; SPA 11-39B - Rest of State counties (preschool) - CPE; SPA 13-XX - NYC (school district) - TBD; SPA 13-XY (county of NY) -TBD
| 1/3113 2/15/13 2/28/13 | P | P | P | Submit SPA 11-39A and 11-39B to CMS (effective 10/1/11)
| 2013-01-31 | 8 | 8 | 8 | FPN for SPA 13-XX (NYC school districts) and SPA 13-XY (county of NY)
| 2/15/13 2/15/13 2/28/13 | P | P | P | Receive/respond to RAIs
| 2013-05-21 | P | P | P | Meet with CMS to discuss transportation
| 2013-05-22 | P | P | P | Meet with CMS to discuss MAC (Medicaid administrative claiming)
| 2013-06-13 | P | P | P | Meet with SED and PCG to review draft responses to RAIs (2/28/13 comments and April-May RAIs)
| 2013-06-18 | P | P | P | Meet with CMS to discuss transportation cost methodology
| 2013-07-10 | P | P | P | Meet with SED and PCG to review draft responses to RAIs (2/28/13 comments and April-May-June RAIs)
| 2013-08-01 | P | P | P | Meet with CMS to discuss indirect cost rates and transportation
| 5/31/13 6/21/13 8/15/13 8/30/13 9/03/13 | P | P | P | Respond to RAIs (special transportation RAIs received 4/24/13)
| 6/21/13 8/15/13 8/30/13 9/03/13 | P | P | P | Respond to RAIs (additional RAIs received 5/16/13)
| 8/15/13 8/30/13 9/03/13 | P | P | P | Respond to RAIs (additional RAIs received 6/25/13)
| 2013-07-30 | P | P | P | Draft FPN for NYC SPAs
| 8/30/13 9/06/13 10/10/13 11/15/13 12/6/13 8/19/14 | P | P | P | Begin drafting revised NYC SPAs
| 2013-08-27 | P | P | P | Obtain information on indirect cost rates from SED in response to CMS request received 8/21/13
| 2013-09-11 | P | P | P | Meet with CMS on indirect cost rates, other
| 2013-10-01 | P | P | P | Meet with CMS on health related percentage calculation, special transportation allocation method, other
| 2013-12-04 | P | P | P | Meet with CMS on health related percentage calculation, cost report accounting for tuition, contracts, revenue
| 12/6/13 12/10/13 | P | P | P | Develop responses to 11-6-13 and 11-12-13 RAIs
| 12/13/13 12/18/13 1/10/14 | P | P | P | Submit RAI responses to CMS
| 3/14/13 5/17/13 6/12/13 6/28/13 10/11/13 11/15/13 12/13/13 12/18/13 12/23/13 | P | P | P | Submit draft SPAs 13-75 and 13-76 to CMS
| 3/14/13 4/15/13 7/1/13 9/30/13 12/30/13 11/31/14 3/17/14 3/31/14 5/30/14 7/31/14 10/17/14 10/31/14 12/5/14 1/6/15 | P | P | P | SPA approval from CMS for 11-39A and 11-39B
| 2014-01-14 | P | P | P | Complete items on "punch list"/follow-ups from December 4, 2013 meeting and transmit to CMS
| 1/17/2014 3/17/14 4/15/2014 | P | P | P | Complete responses to RMTS questions/transmit to CMS
| 2014-01-29 | P | P | P | Conference call with CMS to review questions on RAI responses transmitted to CMS on 1/10/14
| 2014-02-13 | P | P | P | Internal meeting with contractor (PCG) to develop RAI responses
| 2014-02-24 | P | P | P | Complete responses to 33 additional RAIs received 2/10/14; transmit response to CMS
| 2014-02-26 | P | P | P | Meet with CMS (WebEx) to review Cost Report template and methodology for intergovernmental agreement (public school to public school) costs
| 2014-02-27 | P | P | P | Call from Albany CMS - questions on interim claiming,
| 2014-03-14 | P | P | P | Received 3 additional questions from CMS via email; conference call to discuss; responses transmitted to CMS
| 3/24/14 4/2/14 | P | P | P | Additional RAI to be forwarded from CMS for response
| 2014-04-28 | P | P | P | Responses to 4/2/2014 RAI transmitted to CMS
| 2014-06-05 | P | P | P | Call with CMS to discuss preliminary responses to 4/2/14 RAI responses transmitted to CMS on 4/28/14
| 2014-05-23 | P | P | P | Letter from CMS re: contract issue
| 2014-08-15 | P | P | P | Contract amendment work initiated; Step 1 completed
| 2014-08-15 | P | P | P | Contract amendment work initiated; Step 2 completed and transmitted to BOC
| 2015-10-19 | P | P | P | Contract amendment #2 transmitted to OSC
| 10/31/14 7/15/15 10/28/15 12/28/15 1/11/16 | P | P | P | Contract amendment executed |  | With the Vendor for signature Signed by vendor and returned to DOH on 1/20/15. 1/21/15 Signed contract must be processed.
| 2014-06-05 | P | P | P | Call with CMS to discuss preliminary responses to 4/2/14 RAI responses transmitted to CMS on 4/28/14
| 2014-07-23 | P | P | P | Received RAI from CMS with comments on the 4/28/14 responses
| 2014-08-19 | P | P | P | Questions on RMTS and time study received from CMS (approval of these is separate from but related to SPA approval)
| 2014-09-04 | P | P | P | Responses to 7/23/2014 RAI transmitted to CMS
| 2014-10-14 | P | P | P | Responses to 8/19/2014 time study questions transmitted to CMS
| 2014-10-29 | P | P | P | RAI questions of 10/9/14 received by DOH
| 2014-11-13 | P | P | P | Response to 10/9/14 RAI transmitted to CMS
| 2014-11-04 | P | P | P | RMTS questions received by DOH
| 2014-11-20 | P | P | P | Conference call with CMS re: RMTS questions
| 2014-11-24 | P | P | P | Transmit RMTS responses to CMS
| 2014-12-22 | P | P | P | SPAs 11-39A and 11-39B approved
| 2015-07-28 | P | P | P | Letter to CMS re: cost settlement / modified CPE claim
| 2015-10-05 | P | P | P | CMS approves modified CPE claim
| 2015-10-10 | P | P | P | CPE claim back-up information transmitted to FMG for inclusion on the October to December QER
14 |  |  |  |  | Project Name: Restructure Reimbursement for Proprietary Nursing Homes Division Lead: DHCF Team Lead: Cynthia Treis Description: Effective April 1, 2011 modify the equity capital component of Nursing Home rates | -32.1 | Completed
| 2011-04-01 | P | P | P | Set up designated Capital Rate set for 2011 Rates effective April 1, 2011
| 5/13/11 to 6/15/11 | P | P | P | Receive feedback from Industry about potential alternatives
| 6/1/11 6/30/11 | P | P | P | Submit SPA for CMS approval (SPA #11-49)
| 7/1/11 10/1/11 9/28/11 | P | P | P | SPA has been modified to reflect industry agreement - Upon CMS approval, revise the rates to reflect industry feedback / final decisions
| 2011-09-28 | P | P | P | SPA approval received on 9/28/11
| 7/15/11 10/1/11 12/1/11 12/5/11 | P | P | P | Send DOB rate package for approval
| 7/15/11 10/1/11 12/1/11 12/19/11 | P | P | P | Upon approval of DOB send rate package to Emedny
| 8/1/11 10/1/11 12/1/11 12/22/11 | P | P | P | Mail DAL letter to NHs notifying of rate change
15 |  |  |  |  | Project Name: Consolidate all Pharmacy FFS Proposals into a Comprehensive Reform Package Division Lead: Divison of Financial Planning & Policy (DFPP) Team Lead: Mary Carroll Dan McNamara Description: Consolidates all pharmacy fee-for-service proposals into one reform package which includes several initiatives that optimize rebate opportunities, reduce waste, rationalize coverage and reimbursement, or remove statutory limits that drive cost. | -41.63 | Completed
| 2011-04-01 | P | P | P | Proposal 15-A (see below)
| 2011-04-01 | P | P | P | Proposal 15-B (see below)
| 8/1/11 3/1/12 9/15/12 1/1/13 2/1/14 7/1/14 | 8 | 8 | 8 | Proposal 15-C (see below)
| 2011-05-01 | P | P | P | Proposal 15-E (see below)
| 10/1/11 1/26/12 | 8 | 8 | 8 | Proposal 15-F (see below)
| 10/1/11 | P | P | P | Proposal 15-G (see below)
| 2011-10-01 | P | P | P | Proposal 15-H (see below)
| 10/1/11 8/25/11 | P | P | P | Proposal 15-I (see below)
| 10/1/11 8/25/11 | 8 | 8 | 8 | Proposal 15-J (see below)
| 2011-12-01 | P | P | P | Proposal 15-K (see below)
| 1/1/12 1/1/13 | 8 | 8 | 8 | Proposal 15-L (see below)
15A |  |  |  |  | Project Name: Enhance NYS Leverage for Supplemental Rebates Division Lead: DFPP Team Lead: Mary Carroll Description: Allow the Commissioner of Health more flexibility to add drugs/classes to the PDP and in negotiating with manufacturers. | -0.83 | Completed
| 2011-04-01 | P | P | P | Obtain statute modification to allow the Commissioner more flexibility when directly with drug manufacturers (PHL Article 2-A) section 272 11 (b).
| 2011-04-01 | P | P | P | Obtain enabling legislation allowing Commissioner to add drugs/drug classes to the PDP as preferred until the P&TC may conduct a review. Revised language allows for a class with one drug.
| 2011-04-01 | P | P | P | Identify potential drugs/classes
| 2011-04-01 | P | P | P | Determine staffing needs
| 2011-04-01 | P | P | P | Determine system impact.
| 2011-04-15 | P | P | P | When inititiating SDC process, notify direct contract manufacturers of legislative changes that allow DOH to non-prefer selected drugs of specific manufacturers in the absence of successful negotiations.
| 2011-05-02 | P | P | P | Revise PDL and post on PDP website.
| 2011-05-02 | P | P | P | Implement
15B |  |  |  |  | Project Name: Tighten the Early Refill Process Division Lead: DFPP Team Lead: Mary Carroll Description: Tighten up requirements for obtaining authorization to fill a prescription when it is denied because it has been “refilled too soon.” | -1.05 | Completed
| 2011-04-01 | P | P | P | Draft revised policy for early fill
| 2011-04-01 | P | P | P | Obtain legal approval of proposed policy
| 2011-04-01 | P | P | P | Develop prior authorization procedures for exceptions
| 2011-04-01 | P | P | P | Determine system impact.
| 2011-04-01 | P | P | P | Implement EP 1555
| 2011-04-01 | P | P | P | Determine staffing needs
| 2011-04-01 | P | P | P | Develop and send e-blasts and DUR letters to providers (DUR letters will be mailed 3/18, Medicaid Update article will be published in March, e-blasts will be sent 3/18)
| 2011-04-01 | P | P | P | Develop Medicaid Update articles and publish
| 2011-04-01 | P | P | P | Communicate with stakeholders (PSSNY,MSSNY, OMIG)
| 2011-04-01 | P | P | P | Implement new process with soft edit
| 2011-06-01 | P | P | P | Turn off "04" claims edit override for hard edit.
15E |  |  |  |  | Project Name: Rebuild NY Preferred Drug List Division Lead: DFPP Team Lead: Mary Carroll Description: Change the way the preferred drug list is developed, in order to increase savings. | -11.9 | Completed
| 2011-04-01 | P | P | P | Obtain enabling legislation. Language permitting the Commissioner to designate a member of the department to act on his/her behalf intentionally omitted, as was language calling for the elimination of "prescriber prevails"
| 2011-04-01 | P | P | P | Identify systems impact
| 2011-04-01 | P | P | P | Identify staffing needs.
| 2011-04-01 | P | P | P | Create workgroup to develop strategy to achieve estimated savings.
| 2011-04-02 | P | P | P | Identify State staff designated to chair P&TC
| 2011-04-15 | P | P | P | Develop process for making recommendations to P&TC
| 2011-05-01 | P | P | P | Communicate new procedures to stakeholders
| 2011-05-01 | P | P | P | Implement administrative changes
| 2011-05-01 | P | P | P | Engage Magellan in discussion to increase State's involvement in NMPI bid process
| 2011-05-01 | P | P | P | Implement administrative changes
| 2011-05-01 | P | P | P | Engage Magellan in discussion to increase State's involvement in NMPI bid process
15G |  |  |  |  | Project Name: Eliminate Part D Drug Wrap in Medicaid Division Lead: DFPP Team Lead: Mary Carroll Description: Eliminate Medicaid coverage and reimbursement of drugs that are available to Medicaid/Medicare dual eligible beneficiaries through their Medicare Part D plans. | -2.8 | Completed
| 2011-04-01 | P | P | P | Obtain enabling legislation.
| 2011-04-01 | P | P | P | Determine system impact. Modification to Medicare edit to eliminate bypass.
| 2011-04-01 | P | P | P | Identify staffing needs.
| 2011-09-01 | P | P | P | Develop beneficiary "Reduction in Benefit Notice" and schedule mailing
| 2011-09-01 | P | P | P | Notify stakeholders via Medicaid Update article, e-blasts, etc.
| 2011-09-01 | P | P | P | Develop GIS for local districts
| 2011-09-01 | P | P | P | Communicate with stakeholders (SOAF,HIICAP,MRC,PSSNY,MSSNY,OMRDD, OMH, GNYHA, etc)
| 2011-09-01 | P | P | P | Develop and provide information materials for DOH provider and beneficiary call centers
| 2011-10-01 | P | P | P | Implement system and program changes
15H |  |  |  |  | Project Name: Prior Authorization for Exempt Drug Classes Division Lead: DFPP Team Lead: Mary Carroll Description: Allow prior authorization under the Preferred Drug Program (PDP) for the following drug classes: anti-depressants, atypical anti-psychotics, anti-retrovirals and immunosuppressants. | -6.4 | Completed
| 2011-04-01 | P | P | P | Obtain enabling legislation.
| 2011-04-01 | P | P | P | Determine system impact.
| 2011-05-01 | P | P | P | Create workgroup to identify savings opportunities, strategy and P&TC timeline.
| 2011-06-01 | P | P | P | Notify stakeholders via Medicaid Update article, e-blasts, etc.
| 2011-07-01 | P | P | P | Develop operational procedures for prior authorization that will minimize impact.
| 2011-08-15 | P | P | P | Revise PDL removing PA prohibition language from class and re-post.
| 9/1/11 8/25/11 | P | P | P | Implement system changes to allow grandfathering for patients stabalized on non-preferred and to lengthen the time a PA is valid for to 1 year.
15I |  |  |  |  | Project Name: Implement Preferred Drug Program prior authorization requirements based on effective date Division Lead: DFPP Team Lead: Mary Carroll Description: Accelerate the collection of rebates through immediate enforcement of a drug's non-preferred status. | -0.39 | Completed
| 2011-04-01 | P | P | P | Identify sytems impact. Will require change to enforce PA requirements based on effective date of PA code rather than date written. Work with DOS.
| 9/1/11 7/25/11 | P | P | P | Notify stakeholders (prescribers, pharmacies, manufacturers) via Medicaid Update article, e-blasts, etc.
| 10/1/11 8/25/11 | P | P | P | Implement system changes to correctly enforce PA requirements based on effective date of PA code.
| 10/1/11 8/25/11 | P | P | P | Develop method to track savings.
15K |  |  |  |  | Project Name: Limit opioids to a four prescription fill limit every thirty days. Division Lead: DFPP Team Lead: Mary Carroll Description: Limit opioid prescriptions to a four prescriptions fill limit every thirty days for Medicaid beneficiaries. | -0.2 | Completed
| 2011-04-01 | P | P | P | Obtain enabling legislation.
| 2011-04-01 | P | P | P | Identify systems impact. Consider up front clinical editing system.
| 2011-04-01 | P | P | P | Identify staffing needs
| 2011-06-01 | P | P | P | Develop authorization procedures for exceptions
| 2011-06-01 | P | P | P | Develop Fair Hearing process
| 2011-09-01 | P | P | P | Notify stakeholders (prescribers, pharmacies, manufacturers) via Medicaid Update article, e-blasts, etc.
| 10/1/11 12/1/11 | P | P | P | Implement
| 2011-12-30 | 8 | 8 | 8 | Turn on system edit with 30 day lookback: deny opioid scripts >4
17 |  |  |  |  | Project Name: Reduce fee-for-service dental payment on select procedures Division Lead: DFPP Team Lead: Alan Maughan Description: Fee-for-service dental payments should be reduced to match rates paid by managed care providers on high volume dental procedures. | -26.55 | Completed
| 2011-03-21 | P | P | P | Identify average Manage Care payment for dental procedures billed in NYS Medicaid in CY 2009
| 2011-05-14 | P | P | P | Notify NYSDA, NYSADCs, and Oral Health Coalition of need for final comments by 5-16-11 - no additional comments were received.
| 5/1/11 5/16/11 | P | P | P | Finalize reduced dental fee schedule and provide to DPRUM and provider associations
| 2011-05-18 | P | P | P | Load fees into eMedNY (retro to 5/15/11)
| 5/1/11 5/19/11 | P | P | P | Implement effective 5/15/11
| 5/15/11 5/27/11 | P | P | P | Notify providers via Medicaid Update and eMedNY Provider Communications
| 2011-06-15 | 8 | 8 | 8 | Reprocess affected claims back to 5/1/11
21 |  |  |  |  | Project Name: Streamline the Processing of Nursing Home Rate Appeals Division Lead: DHCF Team Lead: Steve Simmons Description: Streamline the processing of nursing home rate appeals by prioritizing and amending processing timeframes, authorizing negotiated settlements, and temporarily capping the annual dollar amount of appeals authorized to be processed | -20 | Completed
| Ongoing | P | P | P | Continue to update tracking mechanism to monitor appeal expenditures for compliance with $80M cap
| Ongoing | P | P | P | Establish a list of "priority appeals" (budget to cost based appeals, remaining old 1983 rebasings, large capital projects etc.) that are not negotiated settlement candidates
| Ongoing | P | P | P | Update criteria to identify financially challenged/unstable facilities (update for 2010 cost report when available - around October)
| 2011-03-17 | P | P | P | Distribute draft appeals settlement agreement with OMIG. OMIG will review and respond on or before April 13, 2011 quarterly meeting.
| 2011-05-01 | P | P | P | Identify next 25 homes to begin the negotiated settlement process with (Department is in the process of doing a pilot test settlement for two homes)
| 5/15/11 6/1/11 | P | P | P | Finalize "negotiated settlement" document language with both DOH counsel and OMIG, Meet with DAL counsel on 5/3
| 5/15/11 6/1/11 | P | P | P | Expand number of staff working on the "settlement team"
| 2011-05-24 | P | P | P | Begin to contact the homes on the list of 25 to discuss negotiated settlement process, identify agreed to list of open appeals etc.
| 2011-06-01 | P | P | P | Expand list to 50 homes
| 6/8/11 6-15-11 7/22/11 7/29/11 | P | P | P | Send a letter to homes seeking letter of interest, their list of outstanding appeals, and within 40 days estimates of the value of each outstanding appeal
| 2011-08-31 | P | P | P | Hold Webinar for Nursing Homes that have submitted a Letter of Interest (week of Aug. 29)
| 2012-03-01 | 8 | 8 | 8 | Draft Regulation to amend processing timeframes for appeals
24 |  |  |  |  | Project Name: Payment for Enteral Formula with Medical Necessity Criteria Division Lead: DPRUM Team Lead: Jonathan Bick Description: Provide coverage of enteral formula to individuals who cannot obtain nutrition through any other means | -14.7 | Completed
LEGISLATIVE CHANGE
| 2011-04-01 | P | P | P | Legislation enacted
FEDERAL PUBLIC NOTICE
| 2011-03-09 | P | P | P | Draft to DHCF
| 2011-03-30 | P | P | P | Published
STATE PLAN AMENDMENT
| 2011-03-25 | P | P | P | Draft to DHCF
| 2011-04-01 | P | P | P | Effective
| 2011-06-30 | P | P | P | Last approval date
REGULATION CHANGE
| 2011-03-16 | P | P | P | Identify and discuss with legal
| 2011-03-21 | P | P | P | Draft to legal
| 2011-05-01 | P | P | P | Emergency Rule Adopted
| 2011-06-10 | P | P | P | Assessment of public comment to DOH Regulatory Affairs
| 2011-07-01 | P | P | P | Approval of assessment of public comment
| 2011-07-05 | P | P | P | Emergency Rule Extended/Published
| 2011-09-02 | P | P | P | 2nd Assessment of public comment to DOH Regulatory Affairs
| 2011-09-09 | P | P | P | Signoff on Final Rule
| 2011-09-28 | P | P | P | Proposed Rule Adoption/Published
| 2011-11-14 | P | P | P | Expiration of public comment period on proposed rule
STAFF TRAINING
| 2011-04-15 | P | P | P | Prior Approval procedures
| 2011-04-15 | P | P | P | Pended claims procedures
| 2011-04-15 | P | P | P | Provider Inquiries
| 2011-04-15 | P | P | P | CSC Call Center
SYSTEM CHANGES
| 2011-03-18 | P | P | P | Identify procedure file changes required
| 2011-04-01 | P | P | P | PA Routing
PRIOR AUTHORIZATION SYSTEM CHANGES
| 2011-01-31 | P | P | P | Identify changes required
| 2011-02-07 | P | P | P | Estimate from contractor
| 2011-03-21 | P | P | P | Secure funding
| 2011-04-15 | P | P | P | Develop and test changes
| 2011-05-02 | P | P | P | Implement changes
| 6/15/11 7/11/11 | P | P | P | Secure funding for cystic fibrosis bypass (an inborn metabolic disease where a standard oral formula, not an inborn metabolic formula, is needed) and maintenance contract which runs out July 1.
| 7/15/11 8/17/11 8/24/11 | P | P | P | Implement cystic fibrosis bypass
PROVIDER NOTIFICATION
| 2011-03-21 | P | P | P | Develop langauge for coverage criteria and notification
| 2011-03-25 | P | P | P | Notify provider associations
| 2011-04-15 | P | P | P | Pharmacy and DME emedny.org communication
| 2011-04-15 | P | P | P | eMedNY Listserv, DME and Pharmacy email
| 2011-04-01 | P | P | P | Provider Manual - Fee Schedule update
| 2011-04-27 | P | P | P | Provider Manual - Procedure Section update
25 |  |  |  |  | Project Name: Remove Physician Component from Ambulatory Patient Group (APG) Base Rates Division Lead: DFPP Team Lead: Alan Maughan Description: Remove physician related reimbursement from hospital ambulatory patient groups (APGs) payment/rate structure. | -14.25 | Completed
| 2011-06-01 | 8 | 8 | 8 | CMS approval of additional APG investment
| 2011-06-08 | 8 | 8 | 8 | Upon CMS approval of additional APG investment, identify and remove physician component from APG calculation and calculate new base rates
| 2011-06-15 | 8 | 8 | 8 | Notify providers associations and providers of new base rates
| 2011-06-15 | 8 | 8 | 8 | Submit package to DOB
| 2011-07-06 | 8 | 8 | 8 | DOB approves rate package
| 2011-08-15 | 8 | 8 | 8 | Implement (load rates into eMedNY-retroactive to 4/1/11) July-August 2011
| 2011-06-15 | P | P | P | The additional $92M investment now pending approval at CMS is being placed on hold until SFY 12/13. Since the $92M was to be reduced by $30M (to $62M) to accomplish this objective, this project has, in effect, been implemented. The $30M does not need to be removed from the rates because the $92M was never added to the rates. In fact the state share savings for SFY 11/12 is $31M higher than stated, although it is planned that the $62M (92 - 30) will be paid retroactively for SFY 11/12 in SFY 12/13.
26 |  |  |  |  | Project Name: Utilization Controls on Behavioral Health Clinics Division Lead: DFPP Team Lead: Alan Maughan Description: Under this proposal, mental hygiene clinic rates would be subject to either provider specific or patient specific utilization standards or thresholds. | -6.8 | Completed
| 2011-03-12 | P | P | P | Receive draft proposals from Mental Hygeine Agencies
| 2011-03-14 | P | P | P | Begin drafting required EP, SPA, Regulation changes (responsibility of Mental Hygiene Agencies), and Federal Public Notice
| 2011-03-15 | P | P | P | Submit Public Notice
| 2011-03-29 | 8 | 8 | 8 | Submit final EP to eMedNY (EP would only apply to patient speciifc thresholds)
| 2011-05-15 | 8 | 8 | 8 | Notify providers via Medicaid Update and eMedNY Provider Communications
| 2011-05-16 | P | P | P | Submit SPA
| 2011-05-30 | P | P | P | Finalize proposals from Mental Hygeine Agencies
| 5/15/11 6/1/11 | P | P | P | Calculate standards or thresholds (responsibility of Mental Hygiene Agencies)
| 5/1/11 6/1/11 6-23-11 | P | P | P | Submit Regualtion
| 5/15/11 6/15/11 | P | P | P | EP or rate adjustments completed and submitted to DOS for systems work
| 2012-01-26 | P | P | P | Promote OMH portion of EP to system
| 6/1/11 6/15/11 7/15/11 8/15/11 9/15/11 10/15/11 11/1/11 1/1/12 2/2/12 3/15/12 | P | P | P | Begin to implement retroactive to 4/1/11 (pending SPA approval and completion of evolution project)
| 2012-03-01 | P | P | P | Complete reprocessing OMH claims retroactive to 4/1/11
| 4/19/12 6/21/12 | P | P | P | Promote OASAS portion of EP to system
| 2012-07-23 | P | P | P | Reprocess 4/1/11 - 6/30/11 and 4/1/12 - 6/21/12 for OASAS (minimal impact)
| 5/17/12 7/31/12 11/1/12 3/15/13 3/31/13 6/11/13 | P | P | P | Complete reprocessing OASAS claims retroactive to 7/1/11 (more likely completion date is 1/31/12 3/15/13 3/31/13)
29 |  |  |  |  | Project Name: Reduce Transportation Costs through Regional Management Recommended Targeted Fee Actions Division Lead: DFPP Team Lead: Mark Bertozzi Add. Staff: Tim Perry-Coon Description: Achieve savings by State procurement of regional transportation management | -30.5 | Completed - Jan 2016 Salient Analyst: Greg Allen Heidi Seney
Medicaid Transportation Management Initiative below:
| 2010-11-19 | P | P | P | Hudson Valley Transportation Management Procurement - posted on website
| 2011-04-15 | P | P | P | Selection of Hudson Valley management contractor
| 2011-04-30 | P | P | P | Negotiate Hudson Valley Contractor Bid
| 2011-05-03 | P | P | P | Hudson Valley Contractor Award
| 2011-05-20 | P | P | P | Hudson Valley Contractor submits required Work Plan
| 2011-05-25 | P | P | P | DOH Approves Hudson Valley Contractor Work Plan
| 2011-07-01 | P | P | P | Begin FFS management of Albany, Columbia, Greene, Sullivan, Orange, Ulster Counties
| 2011-08-01 | P | P | P | Begin FFS management of Fulton, Montgomery, Putnam, Washington, Warren, counties
| 2011-09-01 | P | P | P | Begin FFS Management of Westchester, Rockland Counties
| 2012-01-01 | P | P | P | Increase Hudson Valley contract by 9 (6 by 1/1/12) additional counties: Broome, Cayuga, Dutchess, Oneida, Onondaga, Saratoga, Schenectady, Schoharie, Rensselaer |  | Increased by 6 counties, two more in March -then Saratoga
| 7/1/11 1/1/12 | P | P | P | Carve out transportation from managed care - Hudson Valley 13 Counties
| 6/1/12 3/1/12 | P | P | P | Carve out transportation from managed care - 9 additional counties
| 2011-04-15 | P | P | P | NYC Transportation Management Procurement - posted on website
| 7/29/11 8/29/11 10/3/11 | P | P | P | Selection of NYC management contractor
| 8/12/11 9/12/11 10/21/11 | P | P | P | Negotiate NYC Contractor Bid
| 8/19/11 9/19/11 10/31/11 12/1/11 12/8/11 12/15/11 | P | P | P | NYC Contractor Award
| 9/2/11 10/2/11 11/7/11 12/8/11 1/5/12 | P | P | P | NYC Contractor submits required Work Plan
| 9/9/11 10/9/11 11/22/11 12/15/11 2/3/12 | P | P | P | DOH Approves NYC Contractor Work Plan
| 2012-04-09 | P | P | P | Begin accepting FFS calls for trips after 5/1/12 in Brooklyn
| 9/16/11 11-1-11 2/1/12 5/1/12 | P | P | P | Begin FFS Management in Brooklyn
| 7/1/12 8/1/12 | P | P | P | Begin FFS management in Queens
| 2012-09-01 | P | P | P | Begin FFS management in Manhattan and Bronx
| 2012-10-01 | P | P | P | Begin FFS management in Staten Island
| 9/16/11 11-1-11 1/1/13 | P | P | P | Carve out transportation from managed care - NYC
Western Region Transportation Management County Participation
| 2011-10-07 | P | P | P | Determine Rest-of-State method of procurement (new FAS? / other method?)
| 4/18/13 2/1/12 12/1/12 7/1/13 7/15/13 8/1/13 8/9/13 | P | P | P | Western Region Procurement Posted on DOH Website
| 8/9/13 6/1/12 3/1/13 11/1/13 12/2/13 12/6/13 1/21/14 | P | P | P | Selection of Western Region Management Contractor
| 8/16/13 6/15/12 3/15/13 11/8/13 11/29/13 12/20/13 1/31/14 | P | P | P | Negotiate Western Region Procurement Bid
| 9/6/13 6/22/12 3/22/13 1/6/14 3/1/14 4/1/14 | P | P | P | Western Region Contractor Award
| 9/16/13 7/7/12 4/7/13 1/20/14 3/17/14 4/15/14 | P | P | P | Western Region Contractor submits required Work Plan
| 10/1/13 7/14/12 4/14/13 2/1/14 3/24/13 4/22/14 | P | P | P | DOH Approves Western Region Contractor Work Plan
| 11/1/13 8/1/12 5/1/13 3/1/14 4/1/14 5/1/14 6/1/14 | P | P | P | Begin FFS management in Western Region
| 1/1/14 1/1/13 11/1/13 5/1/14 10/1/14 1/1/15 | P | P | P | Carve out transportation from managed care - Western Region
Finger Lakes and Northern NY Region Transportation Management County Participation
| 10/1/12 11/14/12 | P | P | P | FL and Northern NY Region Procurement Posted on DOH Website (25 counties)
| 12/3/12 2/1/13 2/25/13 | P | P | P | Selection of FL/NNY Region Management Contractor(s)
| 12/10/12 2/8/13 3/1/13 3/22/13 | P | P | P | Negotiate FL/NNY Region Procurement Bid
| 12/17/12 2/15/13 3/23/13 4/8/13 6/1/13 | P | P | P | Contractor(s) Award
| 12/21/12 2/22/13 4/12/13 4/29/13 6/18/13 | P | P | P | Contractor(s) submits required Work Plan
| 12/31/12 3/8/13 4/19/13 5/6/13 6/18/13 | P | P | P | DOH Approves Contractor(s) Work Plan
| 2/1/13 4/19/13 5/19/13 6/1/13 7/1/13 | P | P | P | Begin FFS management in FL and NNY Regions
| 4/1/13 7/1/13 9/1/13 10/1/13 1/1/14 | P | P | P | Carve out transportation from managed care - FL and NNY Regions
Long Island Transportation Management County Participation
| 2013-07-01 | P | P | P | Determine method of procurement for Nassau and Suffolk counties
| 2/28/14 4/15/14 5/15/14 6/27/14 7/14/14 7/17/14 | P | P | P | LI Procurement Posted on DOH Website (2 counties)
| 9/18/14 12/12/14 3/2/15 | P | P | P | Selection of LI Region Management Contractor
| 10/16/14 1/05/15 2/13/15 3/3/15 | P | P | P | Negotiate LI Region Procurement Bid
| 12/16/14 2/5/15 3/13/15 3/16/15 | P | P | P | Contract Award Execution
| 1/16/15 3/20/15 3/30/15 | P | P | P | Contractor Submits Work Plan
| 1/23/15 3/12/15 3/27/15 4/6/15 | P | P | P | DOH approves Work Plan
| 3/1/15 4/24/15 5/1/15 7/1/15 | P | P | P | Begin FFS management on LI
| 1/1/16 12/1/15 | P | P | P | Carve out transportation from managed care - LI region
Medicaid Transportation fee changes below:
| 2011-05-15 | P | P | P | Medicaid Update to Reduce ambulette dialysis fee to ADHC fee drafted
| 6/1/11 7/1/11 | P | P | P | Reduce ambulette dialysis fee to Adult Day Home Care (ADHC) fee
| 2011-04-01 | P | P | P | Freeze transportation fees at the 4/1/11 level, with limited exceptions
| 2011-12-01 | P | P | P | Hudson Valley , ROS managers development of group rides to major medical centers
| 2011-04-29 | P | P | P | Approval of action plan to redirecting "frequent flyer" 911 users of ambulance transportation to the appropriate transportation mode.
| 2011-06-01 | P | P | P | Implement redirecting "frequent flyer" 911 users of ambulance transportation to the appropriate transportation mode. |  | Estimated at $5 M annually for 860 enrollees with 10 + trips in 2010
30 |  |  |  |  | Project Name: Prescription Footwear Payment and Coverage Division Lead: DPRUM Team Lead: Jonathan Bick Description: Update the Medicaid footwear benefit coverage and payment methodology, reducing over utilization and administrative burden | -7.17 | Completed
LEGISLATIVE CHANGE
| 2011-04-01 | P | P | P | Legislation enacted
FEDERAL PUBLIC NOTICE
| 2011-03-09 | P | P | P | Draft to DHCF
| 2011-03-30 | P | P | P | Published
STATE PLAN AMENDMENT
| 2011-03-25 | P | P | P | Draft to DHCF
| 4/1/11 5/1/11 | P | P | P | Effective
| 2011-06-08 | P | P | P | Reimbursement SPA final to DHCF
| 2011-06-15 | P | P | P | Final SPA to CMS
| 2011-06-30 | 8 | 8 | 8 | Last submission date
| 2011-08-17 | P | P | P | SPA approval
REGULATION CHANGE
| 2011-03-16 | P | P | P | Identify and discuss with legal
| 2011-03-21 | P | P | P | Draft to legal
| 2011-04-01 | P | P | P | Emergency Rule Adopted
| 2011-06-10 | P | P | P | Assessment of public comment to DOH Regulatory Affairs
| 2011-07-01 | P | P | P | Approval of assessment of public comment
| 2011-07-05 | P | P | P | Emergency Rule Extended/Published
| 2011-09-02 | P | P | P | 2nd Assessment of public comment to DOH Regulatory Affairs
| 2011-09-09 | P | P | P | Signoff on Final Rule
| 2011-09-28 | P | P | P | Proposed Rule Adoption/Published
| 2011-11-14 | P | P | P | Expiration of public comment period on proposed rule
STAFF TRAINING
| 2011-03-25 | P | P | P | Update Prior Approval procedures
| 2011-03-25 | P | P | P | Update pended claims procedures
| 2011-03-25 | P | P | P | Provider Inquiries
| 2011-03-25 | P | P | P | CSC Call Center
SYSTEM CHANGES
| 2011-03-18 | P | P | P | Identify procedure file changes required
| 2011-03-31 | P | P | P | Update procedure file with benefit paramters
| 2011-04-30 | P | P | P | Update procedure file with new pricing methodology effective 5/1/11
| 2011-04-01 | P | P | P | PA Routing
PROVIDER NOTIFICATION
| 2011-03-21 | P | P | P | Develop langauge for coverage criteria and notification
| 2011-03-25 | P | P | P | Notify provider associations
| 2011-04-01 | P | P | P | Pharmacy and DME emedny.org communication
| 2011-04-01 | P | P | P | eMedNY Listserv, DME and Pharmacy email
| 2011-04-01 | P | P | P | Provider Manual - Fee Schedule update
| 2011-04-27 | P | P | P | Provider Manual - Procedure Section update
| 2011-04-20 | P | P | P | Solicit MRA input from associations
| 2011-05-01 | P | P | P | Implement new MRA's
31 |  |  |  |  | Project Name: Eliminate worker recruitment and retention Division Lead: DHCF Team Lead: Joseph Sohn Add'l Staff: Description: Eliminate worker recruitment and retention add-on from Medicaid rates of eligible Diagnostic and Treatment Centers (D&TCs) effective 4/1/11. | -6.5 | Completed
|  | P | P | P | Section 2807(17)(a)(x) under Article 28 of the Public Health Law ended WRR add-on on March 31, 2011. If new periods are not added in the law, WRR add-on will be removed from applicable Medicaid rates effective 4/1/11. No FPN or SPA approval is required.
| 2009-12-23 | P | P | P | Based on decision made by the Department, send a transmittal to remove WRR add-on effective 1/1/2010, while waiting for CMS approval that implements a new WRR allocation methodology for the period 7/1/07 - 3/31/11.
| 2011-03-03 | P | P | P | Process a Budget package that adjusts WRR add-on retraoctively for the period 7/1/07-12/31/10 and add a new WRR add-on for the period 1/1/10 -3/31/11. This budget package will reconcile WRR payments based on the new allocation method causing payouts and takebakcs among D&TCs. The Package delivered to the Division of the Budget for their approval on 3/11/2011.
| 2011-04-13 | P | P | P | Remove WRR add-on from the applicable Medicaid rates effective 4/1/11 when preparing a rate transmittal for the WRR Budget package. Savings will be achieved going forward due to elimination of WRR add-on effective 4/1/11, not by the Budget package.
| 2011-04-26 | P | P | P | Rates went to production on 4/26/11 and will be activated on 4/27/11 in cycle 1759.
37 |  |  |  |  | Project Name: Eliminate Case Mix Adj for AIDS Nursing Svcs in CHHA and LTHHCP Programs Division Lead: DHCF Team Lead: Tim Casey with Charles Tobey Description: Eliminate separate rate adjustment for AIDS Nursing Services provided under the CHHA and LTHHCP Programs | -2.01 | Completed
| 2011-04-15 | P | P | P | Process annual 2011 "standard" (non-AIDS) Nursing per visit rates for LTHHCP's. Prepare DOB package.
| 2011-04-19 | P | P | P | Submit State Plan Amendment 11-53 to BHOFA for processing to CMS.
| 2011-05-19 | P | P | P | Request BCSD project to modify CHHA/ LTHHCP rate development systems - MMIS transmittal changes to transmit "standard" nursing rates to eMEDNY on AIDS Nursing rate codes
| 2011-06-01 | P | P | P | Process annual 2011 "standard" (non-AIDS) Nursing per visit rates forCHHA's.Prepare DOB package.
| 2011-08-18 | P | P | P | CMS Approval of SPA
| 11/1/11 9/2/11 | P | P | P | After CMS approval received, Submit LTTHCP Rates for DOH and DOB approvals
| 2011-10-16 | P | P | P | After DOB approval, Transmit "standard" 2011 nursing rates for LTTHCPs to eMedNY for loading to the AIDS nursing rate codes retro to statutory eff date of 4/1/11, and post rates and DAL letters to HPN
| 2011-12-01 | P | P | P | After CMS approval received, Submit CHHA Rates for DOH and DOB approvals
| 2011-12-15 | P | P | P | After DOB approval, Transmit "standard" 2011 nursing rates for CHHAs to eMedNY for loading to the AIDS nursing rate codes retro to statutory eff date of 4/1/11, and post rates and DAL letters to HPN
| 2012-03-01 | P | P | P | Request BCSD project to modify CHHA/ LTHHCP 2011 cost report software to consolidate AIDS and non- AIDS nursing cost for future rate development.
| 2012-09-01 | 8 | 8 | 8 | Request DataMart extract from eMedNY system to track savings target
42 |  |  |  |  | Project Name: Stocking coverage Division Lead: DPRUM Team Lead: Jonathan Bick Description: Limit Medicaid coverage for compression stockings to the Medicare criteria and include coverage during pregancy | -0.93 | Completed
LEGISLATIVE CHANGE
| 2011-04-01 | P | P | P | Legislation enacted
FEDERAL PUBLIC NOTICE
| 2011-03-09 | P | P | P | Draft to DHCF
| 2011-03-30 | P | P | P | Published
STATE PLAN AMENDMENT
| 2011-03-25 | P | P | P | Draft to DHCF
| 2011-04-01 | P | P | P | Effective
| 2011-06-30 | P | P | P | Last approval date
REGULATION CHANGE
| 2011-03-16 | P | P | P | Identify and discuss with legal
| 2011-03-21 | P | P | P | Draft to legal
| 2011-04-01 | P | P | P | Emergency Rule Adopted
| 2011-06-10 | P | P | P | Assessment of public comment to DOH Regulatory Affairs
| 2011-07-01 | P | P | P | Approval of assessment of public comment
| 2011-07-05 | P | P | P | Emergency Rule Extended (7/5)/Published (7/20)
| 2011-09-02 | P | P | P | 2nd Assessment of public comment to DOH Regulatory Affairs
| 2011-09-09 | P | P | P | Signoff on Final Rule
| 2011-09-28 | P | P | P | Proposed Rule Adoption/Published
| 2011-11-14 | P | P | P | Expiration of public comment period on proposed rule
STAFF TRAINING
| 2011-03-25 | P | P | P | Prior Approval procedures
| 2011-03-25 | P | P | P | Provider Inquiries
| 2011-03-25 | P | P | P | CSC Call Center
SYSTEM CHANGES
| 2011-03-18 | P | P | P | Identify procedure file changes required
| 2011-03-31 | P | P | P | Update procedure file
| 2011-04-01 | P | P | P | PA Routing
PROVIDER NOTIFICATION
| 2011-03-21 | P | P | P | Develop langauge for coverage criteria and notification
| 2011-03-25 | P | P | P | Notify provider associations
| 2011-04-01 | P | P | P | Pharmacy and DME emedny.org communication
| 2011-04-01 | P | P | P | eMedNY Listserv, DME and Pharmacy email
| 2011-04-01 | P | P | P | Provider Manual - Fee Schedule update
| 2011-04-27 | P | P | P | Provider Manual - Procedure Section update
49 |  |  |  |  | Project Name: Reimburse Art 28 clinics for HIV counseling/testing using APGs Division Lead: DFPP Team Lead: Alan Maughan Description: Medicaid will incorporate payment to Article 28 clinics for HIV counseling and testing services into the Ambulatory Patient Group (APG) payment structure. | -0.2 | Completed
| 2011-04-11 | P | P | P | Calcute applicable APG rate setting figures and update APG software
| 2011-06-01 | P | P | P | Notify providers via Medicaid Update and eMedNY Provider Communications
| 2011-06-10 | P | P | P | Calculate new FQHC rates and impacts
| 2011-07-01 | P | P | P | Implement in APGs 7/1/11 as discussed with providers and provider assocaitions, no savings possible until Jan 1, 2012
| 2011-07-28 | P | P | P | Notify FQHCs of rate changes
| 10/1/11 11/1/11 12/1/11 | P | P | P | Implementing new rates for FQHCs retroactive to 10/1/11
54 |  |  |  |  | Project Name: Adjust 340B Drug payment in 340B-eligible clinics via Ambulatory Patient Groups (APGs) Division Lead: DFPP Team Lead: Alan Maughan Description: Adjust payment downward under APGs for 340B Drugs in 340B-eligible clinics comparable to the savings inherent in the 340 B drug benefit program. | -0.25 | Completed
| 2011-04-12 | P | P | P | Notify Hospital Associations
| 2011-04-19 | P | P | P | Notify providers via eMedNY Provider Communications
| 2011-04-01 | P | P | P | Implement-all systems work already completed as of 3/15/11
55 |  |  |  |  | Project Name: Increase coverage of tobacco cessation counseling Division Lead: DPDM Team Lead: Donna Haskin Additional staff: Adella Lamb, Mike Dembrosky Description: Smoking cessation counseling services will be available to any Medicaid enrollee. | 0.31 | Completed
| 2011-01-11 | P | P | P | Draft Article 7 language
| 2011-01-13 | P | P | P | Determine if SPA is needed
| 2011-03-31 | P | P | P | Submit Federal Public Notice
| 2011-03-11 | P | P | P | Determine if regulations are needed
| 2011-03-18 | P | P | P | Determine any additional program requirements
| 2011-03-18 | P | P | P | Assess managed care impact
| 2011-04-01 | P | P | P | Obtain legislative authority to provide smoking cessation counseling.
| 2011-04-01 | P | P | P | Expansion implemented.
| 2011-04-08 | P | P | P | Determine system requirements- edits and modifiers can be completed without an EP.
| 2011-04-08 | P | P | P | Initiate payment discussion that will allow FQHCs to bill for SCC outside of their PPS rate.
| 2011-04-21 | P | P | P | Draft policy/billing guidance for Medicaid Update- for May publication.
| 2011-05-01 | P | P | P | Notify stakeholders (American Lung Assn and National Cancer Society) of program expansion
| 2011-05-13 | P | P | P | Finalize payment policy and rates that will allow FQHCs to bill for SCC outside of their PPS rate.
| 2011-05-15 | P | P | P | Notify FQHCs of policy and rate codes for SCC.
| 2011-06-01 | P | P | P | Implement payment policy and rates that will allow FQHCs to bill for SCC outside of their PPS rate.
60 |  |  |  |  | Project Name: Delink Workers Compensation and No Fault (WCNF) Rates from Medicaid Division Lead: DOH / DHCF Team Lead: Janet Baggetta Description: WCNF rates can be delinked from the Medicaid Fee-for-Service inpatient rates and not receive the benefits of the Medicaid reimbursement cuts enacted in Medicaid. | 0 | Completed
| 2011-03-03 | P | P | P | Statute Amended - Part of MRT Article VII. Does not need Federal Public Notice or State Plan Amendment.
| 2010-04-01 | P | P | P | Implement programming in Medicaid FFS rate sheet to separate WCNF -- Since the delink of the rates began 4/1/2010, this programming was implemented at that time.
| 2011-04-20 | P | P | P | Publish Rates effective 4/1/2011 without Medicaid reductions: letter to the Workers Compensation Board required to complete publication -- The January 1, 2011 WCNF rates have been calculated including the 2011 Trend Factor and without the reduction for Potentially Preventable Readmissions. Since there are no changes to the rate method and the 1/1/2011 rates already reflect the 1% 2011 trend, the 4/1/2011 rates do not require any rate changes to the 1/1/2011 rate already calculated.
61 |  |  |  |  | Project Name: Home Care Worker Parity Division Lead: OLTC - DHCBS Team Lead: Mary Ann Anglin Additional Staff: Tim Casey Description: Require living wage for home care workers | 0 | Completed
| 2011-04-15 | P | P | P | DOH to review and modify if necessary CHHA and MLTC cost report to include wage information necessary to monitor compliance with parity requirement for applicable providers
| 2011-04-15 | P | P | P | OLTC to review and modify if necessary LHCSA statistical report to include wage information necessary to monitor compliance with parity requirment for applicable providers
| 2011-04-22 | P | P | P | Research initiated on local districts with Living Wages re: existing contracting and attestation process
| 2011-05-02 | P | P | P | Convene internal meetings to determine content of guidance to implement parity requirement
| 2011-05-15 | P | P | P | Consult with the Department of Labor on developing forms for providers to certify compliance with the parity requirement
| 5/16/11 6/6/11 | P | P | P | Prepare draft attestation form (internally)
| 2011-06-17 | P | P | P | Share draft attestation form with internal workgroup (incl. DLA), solicit comments.
| 6/1/11 6/15/11 | P | P | P | Identify providers that employ home health aides in living wage areas as defined persuant to Art VII language
| 2011-07-01 | P | P | P | Draft forms for provider certification, attestation and reporting related to the parity requirement
| 2011-07-01 | 8 | 8 | 8 | DOH to develop mechanism to determine living wage in respective relevant areas
| 8/1/11 8/5/11 | P | P | P | Draft a DAL to be issued to impacted providers
| 11/1/11 11/1/12 11/1/13 | P | P | P | DOH to issue official notice of minimum rates of home care aid compensation for each applicable area on December November 1 of each year
| annually | 8 | 8 | 8 | DOH to monitor provider compliance via submitted cost reports or other mechanisms
67 |  |  |  |  | Project Name: Assist Safety Net Providers Description: Provide a package of assistance to safety providers MRT 67A: Assist Safety Net Providers (MRT Phase 1) MRT 67B: Essential Communtiy Provider Networks /Vital Access Providers (VAP) | 0 | Completed
67A |  |  |  |  | Project Name: Assist Safety Net Providers Division Lead: OHSM Team Lead: Lora Lefebvre Description: Provide a package of assistance to safety providers MRT 67A: Assist Safety Net Providers (MRT Phase 1) | 0 | Completed
| 2011-04-01 | P | P | P | Identify DOH workgroup members needed
| 2011-04-01 | P | P | P | Determine which specific interventions are available after Budget passes: HEAL allocation, Temp operator authority, Anti Trust oversight, workforce retraining funds; nursing home temporary closure rate , capital restructuring
| 2011-04-08 | P | P | P | Convene internal DOH workgroup to develop initiative requirements and process:
| 2011-04-15 | P | P | P | Identify stakeholders to consult - GNYHA, HANYS, Iroquois, NYSHFA, NYAHSA
| 2011-05-06 | P | P | P | Convene meetings for stakeholder input
| 5/20/11 6/3/11 6/13/11 | P | P | P | Develop defintion of eligible safety provider
| 5/20/11 6/3/11 6/13/11 | P | P | P | Identify criteria and requirements for provider application to Department
| 2011-06-15 | 8 | 8 | 8 | Determine whether to develop recommendation for consideration by the Public Health and Health Planning Council to establish a Planning entity to assist in application assessment
| 2011-06-15 | 8 | 8 | 8 | Establish Planning entity with PHHPC to assist Department
| 6/30/11 7/20/11 | P | P | P | OHIP to establish MA rates for hospitals-- to assist closures and APG rate enhancement for voluntary inpatient bed reductions
| 6/15/11 7/20/11 | P | P | P | Identify DoH process for evaluation of applications and determination of what assistance/intervention will be provided
| 6/15/11 7/20/11 | P | P | P | Identify DoH resources both data and analysts to review applications
| 6/15/11 7/20/11 | P | P | P | Identify DoH resources to implement DoH agreed upon interventions
| 8/31/11 9/15/11 9/30/11 10/7/11 11/25/11 | P | P | P | Complete final review of application draft; approve final version
| 6/1/11 7/31/11 10/21/11 12.1/11 2/15/12 | P | P | P | Develop regs for Hospitals, DT&C, Nursing Home closure rate establishment
HEAL PHASE 21 RFA
| 2011-11-28 | P | P | P | Distribute/post HEAL Phase 21 RFA
| 2012-02-06 | P | P | P | Develop review process, evaluation forms and review teams
| 2012-02-17 | P | P | P | Receive applications, log-in applications and conduct initial eligibility screens
| 2012-03-16 | P | P | P | Conduct initial staff reviews
| 3/30/12 4/6/12 | P | P | P | Conduct selection committee meetings
| 4/2/12 4/23/12 | P | P | P | Determine an award announcment date, develop workplan to reflect that date
67B |  |  |  |  | Project Name: Assist Safety Net Providers: Essential Communtiy Provider Networks /Vital Access Providers (VAP) Division Lead: DFRS Team Lead: John Gahan Additional Staff: Donna Choiniere, Jason Corvino, Maribeth Mizner Description: To provide short term or on going rate adjustments to ensure access to care for patients by assuming an active role in ensuring certain essential community providers (hospitals, nursing homes, DTC's or home health providers) | 0 | Completed
| 2012-03-28 | P | P | P | Federal Public Notice
| 6/1/12 9/30/12 | P | P | P | Meetings with Associations (Hospitals, Nursing Homes, D&TC's)
| 6/15/12 10/30/12 | P | P | P | Draft revised regulations
| 6/30/12 10/30/12 12/15/12 1/25/13 2/8/13 2/28/13 7/15/13 8/30/13 9/30/13 10/31/13 | P | P | P | State Plan Amendment - Hospitals Submission process and Approval
| 6/30/12 10/30/12 12/15/12 1/25/13 2/8/13 2/28/13 3/31/13 6/1/13 6/20/13 6/28/13 | P | P | P | State Plan Amendment - Nursing Homes Approved
| 6/30/12 10/30/12 12/15/12 1/25/13 2/8/13 2/28/13 3/31/13 6/1/13 6/28/13 8/15/13 9/15/13 9/30/13 10/31/13 | P | P | P | State Plan Amendment - Non Institutional Process and Approval
68 |  |  |  |  | Project Name: Repatriation of Out-of-State (OOS) Nursing Home Residents Division Lead: OLTC Team Lead: Jacqueline Pappalardi Add'l Staff: Charlotte Mason, Ana Winans, George Stathidis, Wendy Butz, Eileen Brennan, Martin Dale, Matthew Ceccucci, Denise DiPace, Daniel Tarantino, Mary Ellen Hennessy, Cathleen Bobrick,Valerie Deetz, Jonathan Bick, Patrick Dufresne, Erin Finigan, Paula Grogin, Christine Hall-Finney, Lydia Kosinski, Ruth Leslie, Rick Rees, Margaret Willard Description: This proposal would identify spending on out-of-state placements and seek to repatriate those individuals within three years. | 0 | Completed
PHASE I - RESEARCH, ASSESSMENT AND DEVELOPMENT OF COMPREHENSIVE ACTION PLAN
| 2011-04-01 | P | P | P | Engage internal stakeholders to inform and guide MRT #68.
| 2011-05-01 | P | P | P | Using medicaid expenditure data, identify out-of-state nursing home residents receiving medicaid benefits.
| 2011-05-01 | P | P | P | Assess factors contributing to out-of-state nursing home placements and barriers to in-state placement of residents identified.
| 2011-05-01 | P | P | P | Develop a comprehensive workplan for repatriation of out-of-state nursing home residents. Based on assessment of recipient needs and available/necessary resources, the workplan will include a timeline outlining the action steps and milestones.
| 2011-05-24 | P | P | P | Develop a Medicaid prior-authorization Process for all out of state nursing home placements. Notified stakeholder facilities, hospitals, nursing home providers and discharge planners. Presented education and training for discharge planning workgroup. Drafted policies with discussions from Medicaid and approval granted from executive staff.
| 2011-06-30 | P | P | P | From the internal stakeholders group develop and convene a workgroup to comprise staff from the Department of Health, Office of Mental Health and the Office of People with Developmental Disabilities to develop an accurate roster of NYS Medicaid recipients residing in out-of-state nursing homes.
| 2011-07-01 | P | P | P | Identify current hospital discharge planner assessment methodology to ascertain barriers to instate placement of identified residents.
| 2011-07-12 | P | P | P | Revise Pre Admission Screening Resident Review (prior-authorizationSSR) program to enhance compliance with Omnibus Budget Reconciliation Act 1987,Olmstead and ADA requirements.
PHASE II - COMMUNICATION WITH STAKEHOLDERS AND PROVIDERS
| 2011-06-01 | P | P | P | Select a group of out-of-state providers /residents to begin engaging in repatriation efforts.
| 2011-06-11 | P | P | P | Meet with out of state nursing home providers of the selected group to identify mechanisms needed to return residents to the most integrated setting in NYS.
| 7/18/11 8/01/11 | P | P | P | Communicate provider expectations with the new prior-authorization SCREEN and Level 1 processes through issuance of Dear Administrator Letter (DAL)
| 2011-08-25 | P | P | P | Training and education provided to in state case managers and discharge planners to address identified barriers and to clarify expectations.
| 7/18/11 8/01/11 | 8 | 8 | 8 | Adapt Weekly Bed Census Survey to assess provider ability to deliver care and services for difficult to place individuals.
| 2011-09-23 | P | P | P | Submit eMedNY Evolution project to update and automate out of state prior-authorization letters
| 8/1/11 8/15/11 10/3/11 | P | P | P | Implement the Medicaid prior-authorization process.
| 8/30/11 9/16/11 | P | P | P | Research potential costs of repatriating recipients and creating additional resources, as needed, to return these individuals to NYS, and identify barriers to achieving repatriation goals.
| 2011-10-12 | P | P | P | General Information System (GIS) message released to local districts to instruct on new prior-authorization process.
| 10/1/11 10/13/11 | P | P | P | Convene a meeting with external stakeholders to develop a plan of action to support ongoing repatriation by informing nursing homes and hospitals about alternatives to out of state placement.
| 10/13/11 11/15/11 1/1/12 3/1/12 | P | P | P | Work with the external stakeholders to develop materials and a plan for communicating to nursing homes and hospitals about community based housing and service options for discharge.
| 2012-04-01 | P | P | P | Use the developed materials to communicate and provide presentations regarding options for discharge to health care providers
| 1/1/12 6/30/12 3/1/12 | 8 | 8 | 8 | Internal workgroup will develop an electronic tracking system correlated with the eMedny program to track placement of Medicaid recipients within the long term care system.
| 2012-04-01 | P | P | P | Initiate meetings focused on NYS hospitals referring large numbers of out of state residents to identify barriers placing residents in state.
| 2012-04-01 | P | P | P | Engage local districts to identify barriers to repatriation.
| 2012-04-15 | P | P | P | Monitor out of state placements quarterly to evaluate and report on effectiveness of new prior-authorization process
| 2012-04-30 | P | P | P | Identify options and/or alternatives to repatriation of out of state residents
| 2012-05-01 | P | P | P | Communicate and present alternatives/options to executive staff
| 2012-05-01 | P | P | P | Obtain executive staff approval for distribution of discharge planning materials detailing althernatives to out of state placement.
PHASE III - DEVELOP IMPLEMENTATION INCENTIVE PLAN(S)
| 2012-06-01 | P | P | P | Develop tools and provide training to NYS Providers to ensure the use of alternative options to placing residents within NYS
| 2012-06-01 | P | P | P | Hire a community transition coordinator to build communications between health care partners in the community and provide alternatives to out of state referals for selected groups
| 2012-07-30 | P | P | P | Research legal precedence and state guidelines regarding defining state residency.
| 2012-08-01 | P | P | P | Research federal guidelines regarding Medicaid reimbursement responsibility.
| 2012-08-17 | P | P | P | Office of Medicaid Inspector General (OMIG) audit of top out-of-state billers completed.
| 9/1/12 8/17/12 | P | P | P | Identify and inform non-compliant facilities of prior-authorization process (implemented on 10/3/2011) and initiate monthly review and notification procedure for non-compliant facilities
| 4/1/12 9/20/12 11/30/12 4/30/13 | 8 | 8 | 8 | Develop an incentive plan for NYS long term care providers to ensure the appropriate placement of residents within NYS including community based options. On hold pending a full assessment of Hurricane Sandy on out-of-state repatriation.
| 10/4/12 1/1/13 6/30/13 | 8 | 8 | 8 | Report and discuss recommendations for an incentive plan and prior authorization non-compliance with executive staff. On hold pending a full assessment of Hurricane Sandy on out-of-state repatriation.
| 2012-10-04 | 8 | 8 | 8 | Implement automated prior authorization letters evolution project through EMEDNY
| 2012-10-04 | 8 | 8 | 8 | Post reminder about prior-authorization process on EMEDNY and GIS.
| 10/15/12 1/13/13 4/30/13 12/31/13 | P | P | P | Facilitate the sharing of best practices in the care of hard to place residents amongst nursing homes. On hold pending a full assessment of Hurricane Sandy on out-of-state repatriation. | Meetings are ongoing with providers and associations
| 10/15/12 1/1/13 6/30/12 | 8 | 8 | 8 | Obtain executive staff approval for incentive plan. On hold pending a full assessment of Hurricane Sandy on out-of-state repatriation.
PHASE IV - DEVELOP AND IMPLEMENT REPATRIATION PLAN
| 2013-06-30 | P | P | P | Ensure that Prior Authorization requirement for out-of-state, non-specialized skilled nursing facility placement is not overlooked in the transition to Managed Care.
| 2013-09-30 | P | P | P | Consider methods for following up on individuals approved for initial placement out-of-state through Prior Authorization process.
| 2013-12-31 | P | P | P | Work to expand New York State's capacity to provide specialized care to allow for repatriation of residents receiving specialized care out of state. | Meetings are ongoing with providers and associations
| 11/1/12 12/15/12 5/31/13 12/31/13 | 8 | 8 | 8 | Seek feedback from residents and family to determine interest in repatriation. On hold pending a full assessment of Hurricane Sandy on out-of-state repatriation. Any further action on this task will be based on Executive level review of the White Paper.
| 2012-11-01 | P | P | P | Work with out of state Nursing Homes to provide ongoing assessment for resident discharge to NYS
| 2013-01-01 | P | P | P | Initiate medicaid review and monitoring of out of state Nursing Homes
| 2013-12-31 | P | P | P | Develop and submit "White Paper" to Executive Staff that documents MRT outcomes and provides facts and information to guide the Department’s next steps in this area.
69 |  |  |  |  | Project Name: Uniform Assessment Tool (UAT) for LTC Division Lead: DLTC Team Lead: K. John Russell Description: Deliver electronic uniform assessment tool for long term care recipients | 1.85 | Completed
DEVELOPMENT AND TESTING OF UNIFORM ASSESSMENT SYSTEM
| 2011-04-01 | P | P | P | Department of Health (DOH) submission of GCOM Software contract to Attorney General (AG) for approval.
| 4/11/11 4/8/11 | P | P | P | AG approval of contract with GCOM Software
| 4/11/11 4/8/11 | P | P | P | DOH submission of GCOM Software contract to Office of State Comptroller (OSC) for approval (pending AG approval).
| 4/11/11 4/14/11 4/21/11 | P | P | P | Release announcement of OLTC plans and intentions regarding uniform assessment in NYS.
| 4/1/11 4/8/11 4/15/11 | P | P | P | Department of Budget (DOB) approval of expenditure (B-1184) for NYSTEC to conduct independent verification & validation (IV&V) of delivered solution from GCOM.
| 4/11/11 4/29/11 5/11/11 | P | P | P | DOH submission of NYSTEC contract to OSC for approval.
| 5/15/11 4/26/11 | P | P | P | OSC approval of contract with GCOM Software, Inc.
| 5/15/11 5/24/11 | P | P | P | OSC approval of contract with NYSTEC
| 2011-05-16 | P | P | P | Technology Project Kick-Off -- pending GCOM and NYSTEC contract approvals by AG and OSC: Project kick-off initiates the software development project with technology vendors at the table.
| 7/19/11 8/2/11 | P | P | P | DOH IT Signoff on Software Architecture
| 7/20/11 8/3/11 | P | P | P | Completion of Project Iteration #1 Project Planning
| 10/3/11 10/17/11 11/30/11 12/8/11 | P | P | P | Completion of Project Iteration #2 Technical Architecture
| 2011-06-10 | P | P | P | Computer Readiness Survey to LDSS and Service Providers
| 6/6/11 6/24/11 7/5/11 | P | P | P | Identify Beta/Pilot participants
| 2011-09-06 | P | P | P | Contact and Confirm Beta Participatants
| 10/26/11 11/15/11 | P | P | P | Conclude Beta Partipant Kickoff Meetings
| 4/20/12 5/3/12 | P | P | P | WMS Data for Beta
| 3/28/12 4/27/12 | P | P | P | Kick-Off Beta
| 2012-06-29 | P | P | P | WMS OpenTI Interface WMS Develop detailed requirements for Web Service(s)
| 7/20/12 7/27/12 | P | P | P | WMS Submit SA for Upstate web service
| 7/20/12 7/27/12 | P | P | P | WMS Submit SA for Downstate web service
| 6/1/12 7/5/12 8/14/12 8/24/12 | P | P | P | Conclude Beta
| 4/27/12 7/23/12 8/9/12 9/7/12 9/21/12 | P | P | P | Expanded Capabilities Requirements Definition Concluded (QI, Pediatrics, Care Planning; Hosting transition)
| 9/7/12 10/13/12 11/13/12 12/13/12 4/13/13 | P | P | P | WMS Begin testing Upstate web service
| 9/7/12 10/13/12 11/13/12 12/13/12 4/13/13 | P | P | P | WMS Begin testing Downstate web service
| 10/19/12 12/31/12 6/15/13 | P | P | P | WMS User Acceptance (Upstate web service)
| 10/19/12 12/31/12 6/15/13 | P | P | P | WMS User Acceptance (Downstate web service)
| 2012-11-30 | P | P | P | Hosting Migration (concluded)
| 6/15/12 6/29/12 8/2/12 11/30/12 12/31/12 2/28/13 4/26/13 | P | P | P | Completion of Final Candidate Cycle and System Acceptance
| 2013-02-04 | 8 | 8 | 8 | Web-based Training Available
| 7/2/12 8/3/12 12/3/12 1/2/13 3/1/13 3/18/13 3/22/13 | P | P | P | Pilot Kickoff; Start of Statewide Implementation
| 9/14/12 10/19/12 2/22/13 3/22/13 5/16/13 | P | P | P | Pilot Conclusion
| 11/1/12 2/25/13 5/17/13 | P | P | P | Statewide Implementation Continues and Expands
| 2013-07-01 | P | P | P | MLTC State-wide
| 2014-03-31 | P | P | P | Fee for Service Programs all live on UAS-NY by
70 |  |  |  |  | Project Name: Multi-payer Statewide Patient Centered Medical Home Division Lead: Medical Director/DQE Team Lead: Foster Gesten; Additional Staff: Jackey Matson; Ralph Bielefeldt, Gabrielle Armenia Description: Expand the current Statewide Patient Centered Medical Home Program (PCMH) to more payers. | 8.9 | Completed
COORDINATION WITH INTERNAL DIVISIONS
| 2011-03-11 | P | P | P | CHPLUS INCORPORATION AND PMPM FOR FFS - Meet with CHPlus staff to discuss incorporation of CHPlus. Additional meetings as necessary.
| 2011-03-14 | P | P | P | Determine need for regulation
| 2011-04-13 | P | P | P | DUALS-Reach out to relevent DOH staff also involved with duals to begin discussions on coordinating dual initiatives.
| 5/1/11 9/1/11 | 8 | 8 | 8 | MULTI-PAYER DEMO: Meet with DMC to discuss plan outreach, rate development, MMCOR reporting
| 2011-05-01 | 8 | 8 | 8 | MULTI-PAYER DEMO: Meet with DLA to ensure anti-trust protection.
| 2011-05-01 | P | P | P | CHPLUS INCORPORATION AND PMPM FOR FFS- Develop overall project design: establish general parameters for provider participation and eligible services; identify internal and external stakeholders; establish payment models: risk adjusted global payments and FFS MH payments; identify systems (EP) needs.
| 2011-05-15 | P | P | P | In conjunction with MRT Proposal #217 create advisory group to the Commissioner consisting of payor and provider participants and stakeholders. Advisory group will focus on both primary care objectives and patient centered medical homes.
| 2011-05-02 | P | P | P | MULTI-PAYER DEMO: Assist DFPP with FAS.
DUAL INTEGRATION
| 7/1/11 8/15/11 10/1/11 | P | P | P | Coordinate with Dual Grant
| 7/1/11 8/15/11 10/1/11 | P | P | P | Coordinate with MLTC mandatory program
| 7/1/11 8/15/11 10/1/11 | P | P | P | Coordinate with CMS waiver
| 7/1/11 8/15/11 10/1/11 | P | P | P | Coordinate with Health Home initiative
PUBLIC NOTICE
| 2011-03-09 | P | P | P | Draft Public Notice
| 2011-03-29 | P | P | P | Public Notice Issued
STATE PLAN AMENDMENT
| 2011-03-22 | P | P | P | Draft State Plan Amendment for items: 3) testing new models of payment and 8) changing FFS payment methods. Split SPA for community-based physicians, DTCs, FQHCs and OPDs;
| 4/15/11 6/27/11 | P | P | P | Submit SPA: Testing New Models of Payment to CMS
| 7/1/11 9/1/11 11/1/11 12/13/11 | P | P | P | Answer RAIs in a timely manner
| 2011-04-22 | P | P | P | CHPlus - Draft State Plan Amendment
| 2011-05-06 | P | P | P | CHPlus -Submit SPA to CMS
INCORPORATION OF CHPLUS INTO ADK AND SW
| 2011-03-01 | P | P | P | CHPlus - Meet with Health Plans and their Associations to discuss proposal
| 2011-03-08 | P | P | P | CHPlus - Begin policy/draft requirements development
| 2011-03-31 | P | P | P | CHPlus- Complete policy/task requirements
| 2011-04-29 | P | P | P | CHPlus - Draft change specifications to MMCOR for cost reporting
| 2011-08-15 | P | P | P | CHPlus - Request updated information on current CHPlus enrollees in medical homes
| 2011-08-01 | P | P | P | CHPlus - Issue ADM informing plans of the project and supporting policies and requirements
| 2011-08-01 | P | P | P | CHPlus Draft changes to Plan Manual and contracts
| 2011-09-01 | P | P | P | CHPlus - Receive CMS SPA approval (required for implementation)
| 2011-09-01 | P | P | P | CHPlus - Compute additional payment and modify pmpm rates effective 10/1/2011
| 2011-10-01 | P | P | P | CHPlus - Implement (effective 10/1/11)(Contingent upon implementation of programmatic requirements in CHPlus)
PMPM FOR FFS SW AND ADK
| 2011-05-15 | P | P | P | Begin to develop, programming and testing of attribution methodology. ADK attribution methodology applied to non-dual FFS recipients resulting in 24K individuals attributed to a MH provider. Further work is needed to determine attribution based on a more expanded list of CPT codes and to determine whether those attributed to PCMH providers may be attributed to other non-PCMH providers if the methodology includes all Medicaid providers.
| 6/1/11 7/15/11 | 8 | 8 | 8 | Submit Evolution Request for FFS PMPM MH payments
| 2011-08-01 | 8 | 8 | 8 | Oversee Evolution Request: Set up and attend meetings as necessary with DOIT and CSC. Review FRD. CSC testing.
| 2012-01-01 | 8 | 8 | 8 | Implement eMedNY Systems Change - retroactive to 10/1/11 ?
| 2011-09-01 | 8 | 8 | 8 | Draft Medicaid Update Article for 10/1/11 edition.
LEVEL 3 NEW PAYMENT METHODOLOGIES
| 6/15/11 8/1/201 10/1/11 11/1/11 1/1/12 1/17/12 3/1/12 4/15/12 5/15/12 | 8 | 8 | 8 | Begin to develop and test risk adjustment payment methodologies
| 6/15/11 8/1/11 10/1/11 11/1/11 | 8 | 8 | 8 | Begin to establish any necessary data feed from providers or participants
| 8/1/11 10/1/11 11/1/11 | 8 | 8 | 8 | Modify health plan contracts
| 8/1/11 10/1/11 11/1/11 | 8 | 8 | 8 | Implement changes to MMCOR
NEW MULTI-PAYER DEMONSTRATION
| 9/1/2011 11/1/11 | P | P | P | Identify region and possible payers
| 5/15/2011 9/1/2011 11/1/11 | 8 | 8 | 8 | Implementation - Begin to identify DOH (Medicaid/ CHPlus/OHIT/DLA)/SID/GOER/Civil Service workgroup participants.
EVALUATION OF: SW MH, MULTI-PAYER DEMO; NEW LEVEL PAYMENT METHODS
| 2012-01-01 | 8 | 8 | 8 | Develop an evaluation Plan; Contract with an independent evaluator (?)
| 2012-06-04 | 8 | 8 | 8 | Define/finalize involvement in CMMI's Comprehensive Primary Care initiative (CPCi)
82 |  |  |  |  | Project Name: Reduce reimbursement for Hospital Acquired Conditions and Potentially Preventable Negative Outcomes (PPNOs) Division Lead: DHCF Team Lead: Mark Shutts Additional Staff: Dr. Foster Gesten Description: Reduce or deny payment to hospitals for patient conditions acquired while admitted to a hospital | (2.00) | Completed
RESEARCH AND DEVELOPMENT
HACs | 2011-02-17 | P | P | P | Begin review of Federal policy/draft requirements (CMS HAC Proposed Rule)
| 2011-03-11 | P | P | P | Research current Serious Adverse Events conditions in relation to HAC conditions
| 2011-03-11 | P | P | P | Research side-by-side comparison of HACs/PPCs/PSIs for veracity and effectiveness as quality indicators and cost containers
| 2011-03-14 | P | P | P | Research and analyze POA requirements for HAC implementation and expansion
| 2011-04-01 | P | P | P | Complete policy definition
| 2011-04-01 | P | P | P | Determine eMedNY systems impacts/requirements
| 2011-04-01 | P | P | P | Design eMedNY systems configuration
| 5/6/11 5/27/11 | P | P | P | Complete eMedNY system requirements
| 6/1/11 6/21/11 7/28/11 | P | P | P | Delivery of software from 3M to CSC
| 6/15/11 7/28/11 | P | P | P | Test eMedNY systems configuration
| 2011-10-26 | P | P | P | Delivery of revised software from 3M to CSC that incorporates the Federal Rule changes
| 11/1/11 - 12/31/11 | P | P | P | Retest eMedNY systems configuration
COMMUNICATION
| 3/4/11 3/10/11 4/21/11 4/28/11 | P | P | P | Internal policy discussions
| 3/4/11 4/1/11 | P | P | P | Communications with 3M for APR-DRG grouper changes
| 2011-03-11 | P | P | P | Discussions with associations about Present On Admission Indicator compliance (claims data quality issue)
| 2011-03-11 | P | P | P | Communications with HANYS and GNYHA
| 2011-03-17 | P | P | P | Meeting with 3M and Treo Solutions to discuss comparisons of quality indicators
| 3/4/11 3/18/11 4/1/11 | P | P | P | Communications with eMedNY to determine systems impacts/requirements
| 2011-03-18 | P | P | P | Communications with 3M for APR-DRG grouper changes needed to comply with 7/1/11 HAC implementation date and 10/1/11 APR-DRG revision update
| 2011-04-01 | P | P | P | Meeting with 3M and eMedNY/CSC to discuss APR-DRG grouper software changes to facilitate 7/1 implementation of HACs
| 4/4/11 4/11/11 | P | P | P | Communication with Foster Gesten on Serious Adverse Events program implications
| 2011-04-12 | P | P | P | Communicate with Department legal office for statute guidance on HAC program
| 4/15/11 4/29/11 5/6/11 | P | P | P | Meeting with 3M and eMedNY/CSC to discuss APR-DRG grouper software changes to facilitate 7/1 implementation of HACs
ADMINISTRATIVE
| 2011-03-08 | P | P | P | Draft Federal Public Notice
| 2011-03-15 | P | P | P | Review current Serious Adverse Events State Plan Amendment
| 2011-03-30 | P | P | P | Public Notice Issued
| 2011-04-01 | P | P | P | Draft State Plan Amendment
| 2011-04-07 | P | P | P | Draft and submit clarifying Federal Public Notice
| 2011-04-27 | P | P | P | Clarifying Federal Public Notice Issued
| 3/21/11 3/30/11 4/1/11 4/5/11 | P | P | P | Design/Draft/Submit evolution project for eMedNY systems changes
| 2011-04-15 | P | P | P | State Plan Amendment Completed
| 2011-05-23 | P | P | P | Approved Evolution Project FRD
| 2011-05-24 | P | P | P | Completed draft HAC/PPNO regulations
| 2011-06-01 | P | P | P | Revise State Plan Amendment and regulation package to account for the new changes to the Federal Rule
| 6/15/11 7/15/11 | P | P | P | Submit HAC/PPNO regulation package
| 6/15/11 7/15/11 | P | P | P | State Plan Amendment submitted to CMS
| 7/1/11 8/1/11 1/1/12 | 8 | 8 | 8 | HAC Implementation
RESEARCH AND DEVELOPMENT
PPNOs | 2011-02-15 | P | P | P | Internal policy discussions
| 2011-03-01 | P | P | P | Begin policy/draft requirements development
| 2011-03-08 | P | P | P | Review literature from other States
| 2011-05-01 | P | P | P | Preliminary analysis of Potentially Preventable Complications (PPC) and Potentially Preventable Readmission (PPR) rates using 2009 paid claims data and 3M software.
| 2011-06-01 | P | P | P | Determine eMedNY systems impacts/requirements
| 6/30/11 1/1/12 | 8 | 8 | 8 | Metric for tracking savings
COMMUNICATION
| 2011-04-20 | P | P | P | Meet with Hospital Associations (HANYS and GNYHA) to discuss options to meet savings target
| 2011-06-22 | P | P | P | Meet with Hospital Associations (HANYS and GNYHA) to discuss options to meet savings target
| 7/29/11 10/1/11 10/15/11 12/1/11 12/7/11 | 8 | 8 | 8 | Agree on the final methodology for the blend of PPRs and PPCs with the Hospital Associations
ADMINISTRATIVE
| 2011-03-08 | P | P | P | Draft Federal Public Notice
| 2011-03-30 | P | P | P | Public Notice Issued
| 2011-04-07 | P | P | P | Draft and submit clarifying Federal Public Notice
| 2011-04-27 | P | P | P | Clarifying Federal Public Notice Issued
| 6/10/11 7/18/11 11/1/11 12/15/11 | 8 | 8 | 8 | Recalculate the PPR and PPC expected rates and develop the final reduction percentage to achieve targeted savings
| 6/1/11 8/1/11 9/20/11 | P | P | P | Draft State Plan Amendment
| 7/1/11 8/15/11 9/30/11 | P | P | P | State Plan Amendment sent to CMS
| 7/1/11 9/1/11 1/1/12 | 8 | 8 | 8 | PPNOs implemented
83 |  |  |  |  | Project Name: Expand SBIRT Division Lead: DPDM Team Lead: Priscilla Smith Description: Expand SBIRT (Screening, Brief Intervention and Treatment) for alcohol/drug use to allow services in additional settings (hospital ER, clinic and office settings) | -0.85 | Completed
| 2011-03-18 | P | P | P | Draft Article 7 language
| 2011-04-01 | P | P | P | Obtain legislative approval
| 2011-04-08 | P | P | P | Determine need for EP to add rate codes, set reimbursement amounts and program edits
| 2011-04-11 | P | P | P | Initiate analysis of impact on MC capitation rates
| 2011-05-03 | P | P | P | Hold meeting to discuss rates for payment in office settings (APGs already in place for ER/clinic settings)
| 2011-05-14 | P | P | P | Submit draft provider qualifications, billing and and coverage guidance to OASAS/MMC
| 2011-06-01 | P | P | P | Finalize provider qualifications, billing and coverage guidance
| 2011-06-02 | P | P | P | Inititate updates to practioner fee schedules
| 2011-06-15 | P | P | P | Finalize practioner fee schedules
| 2011-08-08 | P | P | P | Publish Medicaid Update
| 2011-08-24 | P | P | P | Submit updates for Provider Manuals
| 2011-09-01 | P | P | P | Implement expansion
89 |  |  |  |  | Project Name: Health Homes for High Cost, High Need Enrollees Division Lead: DFPP Team Lead: Deirdre Astin, Add'l Staff: Lana Earle, Barry Kinlan, Vallencia Lloyd, Patrick Roohan Description: Provide care coordination to high cost/need enrollees to reduce cost & hsp admissions, ER visits & admits to SNF | 0 | Completed
HEALTH HOME IMPLEMENTATION PHASE 1
| 2011-01-11 | P | P | P | Draft Article 7 language
| 2011-03-31 | P | P | P | Submit FPN
| 2011-04-01 | ü | ü | ü | Obtain State legislative authority
| 2011-04-13 | ü | ü | ü | Meet with NYCHRA, NYCDOHMH, NYC Dept. of Homeless Services, OASAS, and OMH on homelessness and health homes
| 2011-04-14 | ü | ü | ü | Develop central interested parties list to facilitate program updates, solicit suggestions and feedback
| 2011-04-14 | ü | ü | ü | Meet with OMH to discuss approaches for coordinating and integrating programs/services for beneficiaries with mental health illness
| 2011-04-20 | ü | ü | ü | Identify workgroup teams and team leaders to address key issues including data, reporting, quality measures, HIT, enrollment, etc.
| 2011-04-20 | ü | ü | ü | Discuss payment methodology & reimbursement for health homes Phase 1 internally
| 2011-04-22 | ü | ü | ü | Explore development of interagency team for health home development & implementation
| 2011-04-22 | ü | ü | ü | Initiate development and design of DOH Health Home website to share program information
| 2011-04-22 | ü | ü | ü | Initiate development of Phase 1 Health Home Program to include CIDP and non-TCM patient populations
| 2011-04-22 | ü | ü | ü | Initiate development of payment methodology and reimbursement amounts for Phase 1 programs
| 2011-04-22 | ü | ü | ü | Initiate identification and development of data requirements for Phase 1
| 2011-04-22 | ü | ü | ü | Initiate identification and development of Phase 1 population selection criteria
| 2011-04-22 | ü | ü | ü | Initiate development of evaluation methodology for Phase 1
| 2011-04-27 | ü | ü | ü | Discuss SPA preprint internally
| 2011-04-29 | ü | ü | ü | Initiate identification and development of federal and State reporting requirements for Phase 1
| 2011-05-03 | ü | ü | ü | Discuss SPA pre-print requirements for quality measures and development of HIT requirements for health homes
| 2011-05-03 | ü | ü | ü | Meet with OPWDD to discuss approaches for coordinating and integrating programs/services for beneficiaries with intellectual/developmental disabilities
| 2011-05-05 | ü | ü | ü | Discuss SPA preprint with TREO
| 2011-05-06 | ü | ü | ü | Initiate discussion on duals
| 2011-05-06 | ü | ü | ü | Meet with OASAS to discuss approaches for coordinating and integrating programs/services for beneficiaries with substance abuse
| 2011-05-06 |  |  |  | Initiate development of a mechanism to accept referrals for a health home from hospitals and other providers
| 2011-05-09 | ü | ü | ü | Meeting with DOH, OMH, OASAS, OPWDD and select providers on development of Health Home Provider Qualifications
| 2011-05-13 | ü | ü | ü | Finalize Health Home website design to share information
| 5/13/11 5/20/11 |  |  |  | Initiate the development of a process for enrollee auto assignment based on Phase 1 selection criteria
| 2011-05-20 | ü | ü | ü | Finalize a core set of general requirements that applies to all health home providers
| 2011-05-23 |  |  |  | Implementation of Health Home website to share information
| 2011-05-25 |  |  |  | Initiate discussion with CMS (Center for Medicare & Medicaid Intervention, Federal Coordinated Health Care Office) on inclusion of dual eligible in HH
| 2011-05-25 | ü | ü | ü | Initiate discussion with CMS on HH model for enrollees with behavioral health and/or chronic medical conditions
| 2011-05-25 | ü | ü | ü | Initiate identification of system needs related to claims editing and payment for Phase 1
| 2011-05-26 | ü | ü | ü | Initiate development of Phase 1 SPA submission
| 2011-06-01 |  |  |  | Finalize set of Phase 1 HH provider specific enrollment and operational requirements
| 2011-06-01 | ü | ü | ü | Finalize draft of payment options and circulate to HCF, MC, DQE for comment
| 2011-06-01 |  |  |  | Finalize process for enrollee auto assignment based on Phase 1 selection criteria
| 2011-06-01 |  |  |  | Finalize draft evaluation methodology for Phase 1
| 5/25/11 6/2/11 | ü | ü | ü | Initiate discussion with CMS (Center for Medicare & Medicaid Intervention, Federal Coordinated Health Care Office) on inclusion of dual eligible in HH
| 6/1/11 6/8/11 | ü | ü | ü | Finalize draft evaluation methodology for Phase 1
| 2011-06-10 | ü | ü | ü | Finalize initial HIT requirements for health homes
| 2011-06-10 | ü | ü | ü | Finalize system needs related to claims editing and payment for Phase 1
| 2011-06-10 | ü | ü | ü | Finalize plan to incorporate the dual eligibles in health homes
| 2011-06-15 | ü | ü | ü | Consult with SAMHSA prior to Phase 1 SPA submission
| 5/23/11 6/3/11 6/17/11 | ü | ü | ü | Implementation of Health Home website to share information
| 2011-06-24 | ü | ü | ü | Finalize strategies for submission of subsequent TCM conversion to HH SPAs (AI, OMH, OPWDD, OASAS)
| 6/16/11 6/30/11 | ü | ü | ü | Reach agreement on a single multi-agency patient consent form for health home use
| 2011-06-30 | ü | ü | ü | Submit Phase 1 SPA draft
| 6/1/11 6/15/11 7/22/11 | ü | ü | ü | Finalize payment methodology and reimbursement amounts for Phase 1 programs
| 7/18/11 8/1/11 | ü | ü | ü | Notify Phase 1 HH potential providers that applications are being accepted by DOH and coordinate notification with sister agencies and associations to facilitate notification to potential providers, members, and interested parties.
| 6/1/11 6/15/11 7/22/11 8/1/11 | ü | ü | ü | Finalize set of Phase 1 HH provider specific enrollment and operational requirements
| 6/10/11 6/17/11 7/29/11 8/4/11 | ü | ü | ü | Continued discussion with CMS on SPA submission for enrollees with behavioral health and or/chronic medical conditions and to discuss hospital referrals of recipients to health homes requirement
| 6/10/11 6/17/11 7/15/11 8/10/11 8/26/11 | ü | ü | ü | Finalize federal and State reporting requirements for Phase
| 6/20/11 7/29/11 8/26/11 | 8 | 8 | 8 | Receive SAMHSA approval for submission of Phase 1 SPA
| 8/12/11 8/30/11 | 8 | 8 | 8 | Submit freedom of choice waiver for mandatory enrollment in health homes
| 2011-08-30 | ü | ü | ü | Submitted revised OHIP/DCE Systems Change request for WMS
| 8/12/11 8/26/11 9/2/11 | ü | ü | ü | Submit freedom of choice waiver for mandatory enrollment in health homes
| 9/1/11 9/7/11 | ü | ü | ü | Prospective health home applicants must submit a Letter of Intent
| 2011-09-12 | ü | ü | ü | Determination made to implement health homes in phases by geographic region and submit multiple HH SPAs
| 9/23/11 9/26/11 | ü | ü | ü | Finalize federal and State reporting requirements for Phase 1
| 6/1/11 6/24/11 7/15/11 8/10/11 8/26/11 9/2/11 9/30/11 | ü | ü | ü | Finalize Phase 1 population selection criteria
| 9/26/2011 10//7/11 10/28/11 | ü | ü | ü | Submit Phase 1 SPA
| 10/13/11 10/5/11 11/1/11 | ü | ü | ü | Applications due date for Phase 1 counties
| 9/1/11 10/5/11 10/24/11 11/18/11 | ü | ü | ü | Finalize development of HH/ RHIO consent form
| 7/1/11 7/29/11 8/25/11 9/26/11 10/17/11 11/18/11 12/2/11 | ü | ü | ü | Finalize HH enrollee notification letter for Phase 1
| 8/1/11 12/1/11 12/9/11 1/18/12 | ü | ü | ü | Begin provider enrollment of health home entities for Phase 1
| 8/15/11 9/15/11 10/24/11 12/18/11 1/18/12 1/25/12 | ü | ü | ü | Receive SPA approval for Phase 1
| 5/6/11 6/8/11 6/24/11 7/29/11 9/9/11 11/10/11 2/1/12 | ü | ü | ü | Initiate development of a mechanism to accept referrals for a health home from hospitals and other providers.
| 2012-02-10 | ü | ü | ü | System Specifications/Assessment is Provided to WMS
| 6/10/11 6/17/11 7/15/11 8/10/11 8/26/11 9/16/11 12/2/11 12/16/11 1/18/12 2/1/12 2/15/12 | ü | ü | ü | Finalize data requirements for Phase 1
| 10/1/11 11/1/11 1/9/12 1/1/12 2/1/12 2/15/12 2/27/12 | ü | ü | ü | Implement Phase 1counties
| 8/19/11 9/15/11 12/9/11 1/9/12, 2/1/12 2/15/12 2/27/12 | ü | ü | ü | Begin enrollment of Medicaid enrollees into Phase 1 HH
| 12/1/2011 12/15/11 12/30/11 2/28/12 3/1/12 | ü | ü | ü | Prepare system specification related to Welfare Management System (WMS) Completed in preparation for Phase 1 of HH
| 1/31/2012 3/31/12 4/6/12 4/29/12 | ü | ü | ü | Programing of system Specifications WMS completed
| 4/2/12 7/16/12 11/1/12 12/1/12 1/15/13 2/15/13 3/15/13 4/15/13 5/15/13 | ü | ü | ü | Complete development of program manuals
| 2013-06-12 | ü | ü | ü | Forward Manual to OHIP Prov. Manual Unit for final editing.
| 2013-06-28 | ü | ü | ü | OHIP Provider Manual Unit forwards Prov. Manual to eMedNY for final production/posting.
| 2012-07-20 | ü | ü | ü | Finalize WMS system changes to needed to support Health Homes
| 2012-07-24 | ü | ü | ü | Submit revised SCR starting system support requirements
| 2012-07-31 | ü | ü | ü | Submit SAs for WMS changes needed to support Health Homes
| 2012-08-07 | ü | ü | ü | Revised requirements (SCR) provided to systems
| 2012-08-21 | ü | ü | ü | Revised system specifications related to Welfare Management System (WMS) completed
| 6/8/11 6/20/11 8/26/11 12/16/11 1/18/12 2/1/12 7/2/12 8/15/12 9/17/12 | ü | ü | ü | Finalize development of a mechanism to accept referrals for a health home
| 4/2/2012 4/16/12 4/1/12 10/1/12 11/1/12 11/15/12 12/15/12 | ü | ü | ü | Implement Phase 2 counties
| 6/3/12 6/18/12 7/1/12 10/1/12 11/1/12 11/15/12 12/15/12 | ü | ü | ü | Implement Phase 3 counties
| 6/10/11 6/17/11 8/12/11 9/15/11 10/26/11 12/9/11 2/1/12 3/15/12 5/15/12 8/1/12 8/30/12 10/1/12 11/15/12 | ü | ü | ü | Discussion with GNYHA and HANYS to discuss procedures for hospital referrals of recipients to health homes
| 4/2/12 7/16/12 11/1/12 12/1/12 1/15/13 2/15/13 3/15/13 4/15/13 5/15/13 | ü | ü | ü | Complete development of program manuals
| 5/1/12 7/15/12 9/3/12 9/17/12 12/31/12 3/15/13 4/5/13 | 8 | 8 | 8 | WMS Unit Testing Commences - ON HOLD
| 2/29/12 5/15/12 6/15/12 8/15/12 10/15/12 2/15/13 5/14/13 | 8 | 8 | 8 | WMS Unit Testing Completed - ON HOLD
| 3/5/12 6/1/12 6/18/12 9/1/12 10/22/12 2/16/13 5/15/13 | 8 | 8 | 8 | WMS Migration Completed - ON HOLD
| 2014-01-01 | 8 | 8 | 8 | Survey and interim report due to CMS
HEALTH HOME IMPLEMENTATION PHASE 2 TCM CONVERSION PHASE 1 & 2 MERGED
| 2011-06-13 | ü | ü | ü | Initiate development of Phase 2 SPA for TCM conversion to HH (AI, OMH, OPWDD, OASAS) including transition plans, population criteria selection, federal and State reporting requirements, payment methodology and reimbursement amounts, system needs, data needs, evaluation method, and enrollee assignment.
| 2011-07-05 | ü | ü | ü | Initiate discussion with CMS regarding Phase 2 Health Home SPA submission
| 2011-07-15 | ü | ü | ü | Consult with SAMHSA prior to Phase 2 SPA submission
| 2011-07-15 | 8 | 8 | 8 | Finalize federal and State reporting requirements for Phase 2 TCM conversion
| 2011-07-15 | 8 | 8 | 8 | Finalize Phase 2 TCM conversion data requirements
| 2011-07-15 | 8 | 8 | 8 | Finalize Phase 2 TCM conversion population selection criteria
| 2011-07-22 | 8 | 8 | 8 | Finalize process for enrollee auto assignment based on Phase 2 TCM conversion selection criteria
| 2011-07-22 | 8 | 8 | 8 | Finalize evaluation methodology for Phase 2 TCM conversion
| 2011-07-22 | 8 | 8 | 8 | Finalize Phase 2 TCM conversion population selection criteria
| 7/5/2011 7/29/11 | 8 | 8 | 8 | Finalize process for enrollee auto assignment based on Phase 2 TCM selection criteria
| 7/5/2011 7/29/11 | 8 | 8 | 8 | Finalize payment methodology and reimbursement amounts for Phase 2 TCM programs
| 2011-07-29 | 8 | 8 | 8 | Finalize system needs related to claims editing and payment for Phase 2 TCM conversion
| 2011-07-29 | 8 | 8 | 8 | Finalize draft evaluation methodology for Phase 2 TCM conversion
| 2011-08-26 | 8 | 8 | 8 | Receive SAMHSA approval for submission of Phase 2 SPA
| 2011-08-26 | 8 | 8 | 8 | Finalize strategies for submission of subsequent TCM conversion to HH SPAs (OPWDD)
| 6/1/11 9/30/11 9/8/11 | 8 | 8 | 8 | Submit Phase 2 SPA for TCM conversion to HH (AI, OMH, OPWDD, OASAS)
| 2011-09-09 | 8 | 8 | 8 | Finalize process for enrollee auto assignment based on Phase 1 selection criteria
| 2011-10-01 | 8 | 8 | 8 | Finalize HH enrollee notification letter for Phase 2 TCM conversion
| 1/30/12 10/1/11 | 8 | 8 | 8 | Receive SPA approval for Phase 2 TCM conversion SPA
| 2014-01-01 | 8 | 8 | 8 | Implement Phase 2 program TCM conversion
VENDOR CONTRACT FOR HH/PCMH IMPLEMENTATION ASSISTANCE
| 2011-05-05 | ü | ü | ü | Initiate development of a vendor contract to utilize a vendor for assistance with program implementation, management and operations activities.
| 5/6/11 5/16/11 5/20/11 | ü | ü | ü | Submission of BB1184
| 5/17/11 5/22/11 | ü | ü | ü | Complete development of a vendor contract to utilize a vendor for assistance with program implementation, management and operations activities.
| 5/13/11 5/27/11 6/3/11 6/15/11 | ü | ü | ü | Initiate clearance process of solicitation document
| 5/20/11 6/3/11 6/10/11 6/22/11 7/12/11 | ü | ü | ü | Post vendor contract for HH/PCMH implementation assistance for 30 days
| 5/27/11 6/10/11 6/17/11 6/29/11 7/19/11 | ü | ü | ü | Bidder's questions received on vendor HH/PCMH implementation assistance contract
| 6/13/11 6/27/11 7/3/11 7/15/11 8/5/11 | ü | ü | ü | DOH response to HH/PCMH implementation assistance bidder questions
| 6/21/11 7/11/11 7/18/11 8/5/11 8/19/11 | ü | ü | ü | Bid proposals due for vendor contract for HH/PCMH implementation assistance
| 6/29/11 7/22/11 7/29/11 8/12/11 8/30/11 9/30/11 | ü | ü | ü | Complete evaluation and selection of vendor contract for HH/PCMH implementation assistance
| 7/5/11 8/1/11 8/8/11 8/19/11 9/7/11 11/23/11 | ü | ü | ü | Complete DOH internal approval and sign contract for vendor contract for HH/PCMH implementation assistance
|  | ü | ü | ü | Vendor for HH/PCMH implementation assistance begins work
COLOCATION OF SERVICES
| 2011-06-01 | ü | ü | ü | Meet with OHSM, OMH, OASAS, and OPWDD to identify areas for streamlining licensing requirements for colocation and discuss future roles and responsibilities.
| 2011-06-06 |  |  |  | Develop interagency MOU outlining roles and responsibilities of agencies in colocating services.
| 6/16/11 6/21/11 |  |  |  | Finalize initial development of a single set of license requirements for multiagency co-located services
| 6/16/11 6/30/11 | ü | ü | ü | Continue discussion on colocation issues with agencies
| 6/611 7/15/11 8/15/11 | ü | ü | ü | Reach agreement on a single multi-agency patient consent form for health home use
| 2011-09-01 | ü | ü | ü | Continue discussion with OMH and OASAS on initial development of a single set of license requirements for multiagency co-located services
| 6/30/11 7/15/11 8/26/11 10/30/11 12/2/11 1/31/12 1/12/12 | 8 | 8 | 8 | Finalize development of RHIO consent form
| 6/1/11 8/4/11 8/21/11 9/30/11 11/18/11 1/13/12 2/15/12 3/1/12 | ü | ü | ü | Continue discussion on colocation issues with agencies and mulit-licensed providers
| 8/1/11 9/1/11 11/30/11 12/28/11 2/17/12 4/15/12 8/15/12 10/15/12 | ü | ü | ü | Develop interagency roles and responsibilities of agencies in colocating services.
| 8/8/11 10/1/11 10/20/11 1/11/12 3/2/12 6/15/12 9/1/12 10/15/12 12/1/12 2/4/13 | ü | ü | ü | Complete interagency colocation MOU outlining roles and responsibilities of agencies in colocating services.
| 10/30/12 12/1/12 2/4/13 | ü | ü | ü | Initiate implementation activities related to co-locating services as identified in the MOU.
EXPAND MATS
MATS tasks are covered by Health Home plan
90 |  |  |  |  | Project Name: Mandatory Enrollment in MLTC/ Plans / Health Home Conversion Division Lead: DLTC Team Lead: Mark Kissinger Additional Staff: Margaret Willard, Deborah Conley Flora, James DeMatteo, Pavel Terpelets Description: Transition Medicaid Recipients age 21 and older in need of community-based long term care services into MLTC plans, and convert MLTC plans to Health Homes. Phase 1 to begin to remove LDSS from enrollment process; target implementation 9/1/11. Phase 2 to begin Mandatory enrollment July 2012 in NYC, including transition of current users of community based long term care services. Target for transition is 5/2015. Expansion Upstate will roll out as capacity is achieved. |  | Completed
| 2011-03-24 | P | P | P | Meeting with MLTC Plans. Dialogue on proposal.
| 5/30/11 6/8/11 6/15/11 | P | P | P | Establish Membership of Workgroup
| 2011-07-08 | P | P | P | First Workgroup meeting
| 2011-08-16 | P | P | P | Second Workgroup meeting
| 2011-09-19 | P | P | P | Workgroup Hearing
| 2011-09-28 | P | P | P | Third Workgroup meeting
| 2011-11-01 | P | P | P | Workgroup recommendations presented to MRT
CONVERT MLTC TO HEALTH HOME
| 5/1/11 6/30/11 | P | P | P | Establish Health Home Standards. Determine if plan operations need modification.
| 5/13/11 6/30/11 | P | P | P | Submit draft State Plan Amendment to CMS. | Based on workplan #89
| 6/1/11 6/15/11 8/15/11 | P | P | P | Identify any systems / claiming issues
| 5/20/11 6/1/11 8/15/11 10/1/11 | 8 | 8 | 8 | Incorporate necessary Health Home MLTC plan contract changes with Phase 1 amendment
| 8/1/11 8-15-11 10-1-11 10/15/11 11/1/11 | ▲ | ▲ | ▲ | Response to CMS Questions, State Plan Approval
| October 2011 - March 2013 | 8 | 8 | 8 | Enhanced federal share
PHASE ONE - ELIMINATE LDSS
| 2011-04-01 | P | P | P | Issue Revised Service Area Expansion Application
| 2011-04-29 | P | P | P | Draft amendment to MTLC contract to adress changes to LDSS and benefit package changes into internal review
| 2011-04-30 | P | P | P | Anticipate receipt of Service Area Expansion applications for review
| 2011-05-11 | P | P | P | Discuss MLTC and proposed changes with MCARP
| 6/11 - ongoing | P | P | P | Anticipate receipt of first new MLTC COA applications Review and processing of new MLTC COA Applications
| 4/22/11 5/26/11 6/14/11 | P | P | P | Issue revised Certificate of Authority application and application to add another line of business for a plan with a COA
| 7/15/11 7/20/11 | P | P | P | Training of Enrollment Broker and other entities which may assist with education/enrollment
| 2011-08-15 | P | P | P | Collect feedback through discussions with plans and counties
| 2011-09-01 | P | P | P | Commence enrollment activities without LDSS for 10/1/11 enrollments
| 8/1/11 9/15/11 11/15/11 | P | P | P | Revised MLTC plan materials finalized including handbooks, member notices, marketing materials
| 5/20/11 6/20/11 8/15/11 10/1/11 10/15/11 11/1/11 11/21/11 12/5/11 | P | P | P | MLTC 2012 contract sent to CMS for approval
| 6/1/11 7/1/11 8/23/11 10/22/11 11/15/11 11/30/11 12/15/11 12/22/11 2/1/12 | P | P | P | MLTC 2012 contract approved by CMS. Sent to plans
| 7/1/11 8/1/11 9/1/11 10/29/11 11-30-11 12/15/11 12/29/11 4/1/12 | P | P | P | Contract complete DOH clearance and sent to OSC
| 8/15/11 10/15/11 11/1/11 11/15/11 12/15/11 1/15/11 8/1/12 10/1/12 1/1/13 4/1/13 | P | P | P | Finalize parameters and processes for post enrollment review
PHASE TWO - MANDATORY MLTC ENROLLMENT
1115 Waiver
| 2011-04-22 | P | P | P | Submit 1115 Waiver amendment to CMS
| 2012-02-02 | P | P | P | Sent draft terms and conditions
| 2012-02-07 | P | P | P | Submission of DRAFT Education Materials – completed
| 2012-02-27 | P | P | P | Submit materials to Stakeholders
| 2012-03-23 | P | P | P | Response to CMS programmatic questions if warranted (ongoing)
| 2012-02-21 | P | P | P | Budget Neutrality information to CMS
| 6/29/12 8/31/12 | P | P | P | Secure official CMS approval
| 2012-09-05 | P | P | P | Submitted request to CMS for expansion to Nassau, Suffolk, Westchester January 2013
WAIVER - IMPLEMENTATION
| 2012-06-08 | P | P | P | Announcement letter to recipients in NYC
| 7/2/12 8/31/12 9/17/12 | P | P | P | Information provided to new applicants for CBLTC, informed of requirement to join MLTC plan
| 2012-07-09 | P | P | P | Notice issued to first group for transition with 60 day choice period
ENROLLMENT PLAN
| 2012-07-09 | P | P | P | Transition commences with first group of Personal Care recipients in Manhattan, continues as per CMS approved plan
| 2012-08-01 | P | P | P | Continue to transition personal care cases in New York County
| 9/1/12 10/1/12 | P | P | P | Continue transition of personal care cases in New York County. Begin transition of personal care in Bronx. Begin Kings County.
| 10/1/12 11/1/12 | P | P | P | Continue transition of personal care and CDPAP in New York, Bronx, and Kings. Begin transition of CDPAP.
| 2012-12-01 | P | P | P | Continue transition of personal care and CDPAP in New York, Bronx, Kings. Begin Queens and Richmond
| 1/1/13 1/25/13 | P | P | P | Initiate transition citywide of ADHC not enrolled under personal care case activity
| 1/1/13 1/25/13 2/15/13 | P | P | P | Initiate transition of home health over 120 days
| 2013-03-15 | P | P | P | Initiate transition of private duty nursing cases not enrolled under personal care case activity.
| 2013-04-01 | P | P | P | Initiate transition of LTHHCP (Pending 1915 waiver approval)
| 2013-02-01 | P | P | P | Ongoing until all people in service in NYC Counties are enrolled
| 1/1/13 1/25/13 | P | P | P | PHASE II - Anticipated for Nassau Suffolk and Westchester counties
| 2013-06-01 | P | P | P | PHASE III - Anticipated for Rockland and Orange
| 2013-12-01 | P | P | P | PHASE IV - Anticipated for Albany, Erie, Onondaga and Monroe
PHASE V - REMAINDER OF STATE
| 2014-04-15 | P | P | P | Columbia, Putnam, Sullivan, Ulster
| 2014-05-15 | P | P | P | Rensselaer, Cayuga, Herkimer, Oneida
| 6/15/14 6/25/14 | P | P | P | 6/15/2014 for Greene, Schenectady, Washington, 6/25/2015 for Saratoga
| 2014-07-15 | P | P | P | Schedule for the rest of the counties was revised in July 2014!
| 2014-08-15 | P | P | P | Dutchess, Montgomery, Broome, Fulton, Schoharie
| 2014-09-15 | P | P | P | Delaware, Warren
| 2014-10-15 | P | P | P | Niagara, Madison, Oswego
| 2014-11-15 | P | P | P | Chenango, Cortland, Livingston, Ontario, Steuben, Tioga, Tompkins, Wayne
| 2014-12-15 | P | P | P | Genesee, Orleans, Otsego, Wyoming
| 1/15/14 2/4/15 2/27/15 | P | P | P | Chautauqua, Chemung, Seneca, Schuyler, Yates Allegany, Cattaraugus
| 3/15/15 3/31/15 5/29/15 | P | P | P | Clinton, Essex, Franklin, Hamilton, Essex, Lewis, St. Lawrence, Chautauqua, Chemung, Seneca, Schuyler, Yates, Allegany
| 2015-06-30 | P | P | P | Clinton, Allegany, Franklin, Jefferson, Lewis, St. Lawrence
| 5/1/15 12/13/15 | P | P | P | Statewide complete transition of CBLTC users into MLTC
SYSTEMS MODIFICATIONS
| 2011-04-30 | P | P | P | Begin system modifications for auto-assignment algorithm
| 2012-02-07 | P | P | P | Evolution Project Submitted and project meeting held
| 2012-02-15 | P | P | P | EP #1675 finalized - Awaiting estimates for system change requests and testing
| 2012-02-27 | P | P | P | Impacts to WMS for R/E code 93 (new users)
| 2012-02-28 | P | P | P | Impacts to emedny for indicator (transition group)
| 2012-04-01 | P | P | P | WMS ROS R/E Code 93 completed
| 2012-04-23 | P | P | P | WMS NYC R/E code 93 testing with partner file exchange
| 2012-06-18 | P | P | P | WMS NYC R/E code 93 to production
| 2012-05-01 | P | P | P | eMedNY submits test files to Enrollment Broker for AA indicator (transition group) and code 93
| 2012-05-22 | P | P | P | eMedNY to production with AA indicator
| 2012-06-28 | P | P | P | Systems request to add CDPAP rate codes to AA indicator
| 2012-07-20 | P | P | P | Project meeting: WMS/Emedny for non EB districts
| 8/1/12 8/24/12 9/14/12 10/15/12 11/15/12 12/14/12 | P | P | P | Systems request to add remaining CBLTC groups to AA
| 2012-07-02 | P | P | P | Mandatory mailings commence, auto assignment clock begins
RATES
| 2011-05-01 | P | P | P | Begin discussions with Actuary re: rate development for 4/12 rate cycle | Will be achieved without need for systems request.
| 2012-02-16 | P | P | P | Discussion with industry Op Issues Meeting
CALCULATE EXISTING PREMIUM RATES
| 2012-06-13 | P | P | P | Implement all changes to existing rate cell effective 4/1/12
| 2012-06-15 | P | P | P | Submit rates to DOB
| 2012-06-29 | P | P | P | Submit rates to CMS
| 2012-06-13 | P | P | P | Mail rates to plans in draft form
| 2012-06-29 | P | P | P | Mercer rate certification letter
| 2012-07-06 | P | P | P | DOB Approval
| 7/13/12 9/7/12 | P | P | P | CMS Approval
| 7/20/12 9/14/12 9/21/12 | P | P | P | Post rates and notify plans rates are final
IMPLEMENT NEW PREMIUM RATES
| 2012-02-09 | P | P | P | Submit EP request for new rate codes for new premium groups
| 2012-03-05 | P | P | P | Finalize specs for EP #1678
| 2012-05-10 | P | P | P | Add new rate codes on the system
| 7/13/12 9/28/12 11/30/12 12/31/12 1/18/13 2/1/13 2/28/13 | P | P | P | Calculate new premium rates effective 7/1/12 and risk corridor PMPMs
| 7/13/12 9/28/12 11/30/12 12/31/12 1/18/13 2/1/13 2/28/13 3/29/13 5/31/13 | P | P | P | Submit rates to DOB
| 7/13/12 9/28/12 11/30/12 12/31/12 1/18/13 2/1/13 2/28/13 3/29/13 5/14/13 | P | P | P | Submit rates to CMS
| 7/13/12 9/28/12 11/30/12 12/31/12 1/18/13 2/1/13 2/28/13 | P | P | P | Mail rates to plans in draft form
| 7/13/12 9/28/12 11/30/12 12/31/12 1/18/13 2/1/13 2/28/13 3/29/13 5/31/13 | P | P | P | Mercer rate certification letter
| 7/27/12 10/12/12 12/31/12 1/31/13 2/22/13 3/22/13 4/30/13 5/31/13 6/18/13 7/5/13 | P | P | P | DOB Approval
| 7/27/12 10/12/12 12/31/12 1/31/13 2/22/13 3/22/13 4/30/13 5/31/13 6/18/13 7/5/13 7/31/13 | P | P | P | CMS Approval
| 7/27/12 10/12/12 12/31/12 1/31/13 2/28/13 3/29/13 5/7/13 6/24/13 7/12/13 7/31/13 8/31/13 10/05/13 | P | P | P | Post rates and notify plans rates are final
RISK CORRIDOR SETTLEMENT
| 2012-08-31 | P | P | P | Develop risk share settlement report
| 2012-08-31 | P | P | P | Track risk corridor settlement program-wide and calculate overall due to plans/due to State (monitor on a monthly basis)
| 4/30/13 6/3/13 7/19/13 10/15/13 11/15/13 11/19/13 12/3/13 12/18/13 1/15/14 3/15/14 4/25/14 6/6/14 6/30/14 7/31/14 9/26/14 10/26/14 | P | P | P | Calculate the final risk share settlement
| 5/31/13 6/24/13 8/9/13 11/1/13 12/1/13 12/17/13 12/31/13 1/31/14 3/31/14 5/15/14 7/15/14 10/31/14 11/30/14 | P | P | P | Implement cash settlement with plans. There will be no cash settlement.
COST REPORT MODIFICATIONS
| 2012-06-01 | P | P | P | Spec out cost report changes and design new tables to be added
| 2012-07-30 | P | P | P | Finalize all cost report changes
| 2012-08-01 | P | P | P | Submit all changes and edits to BCSD
| 9/7/12 9/25/12 | P | P | P | Test changes and finalize cost reports
| 2012-10-01 | P | P | P | Post 3rd qtr cost report to HPN
DEVELOPMENT OF CARE COORDINATION MODEL (CCM) RATE (ONGOING AS NEEDED)
STAKEHOLDER ENGAGEMENT
| 2011-05-11 | P | P | P | Discuss MLTC and proposed changes with MCARP
| 2012-01-26 | P | P | P | Weekly meeting with MLTC Implementation group - ongoing
| 2011-12-08 | P | P | P | Weekly meeting with HRA - ongoing
| 2011-12-29 | P | P | P | Weekly meeting with Enrollment Broker - ongoing
| 2011-03-29 | P | P | P | Marketing - Draft Guidelines distributed for comment
| 7/9/12 8/24/12 9/17/12 11/1/12 11/15/12 1/1/13 3/15/13 | P | P | P | Finalize Marketing Guidelines
| 8/1/12 9/21/12 1/1/13 3/1/13 4/1/13 5/1/13 5/15/13 6/1/13 6/14/13 7/15/13 8/15/13 9/1/13 | P | P | P | Identify Disenrollment Issues - State to develop Guidelines
TARGETED TRAINING AND INFORMATION ACTIVITIES
| 2011-12-15 | P | P | P | Maximus Staff
| 2012-05-18 | P | P | P | Fair Hearing Staff
| 2012-05-06 | P | P | P | Medicaid Update Article Released: Guidance for Providers on Enrollment Plan
LOCAL DISTRICT COMMUNICATIONS
| 2012-01-31 | P | P | P | NYPWA Presentation
| 7/6/12 9/7/12 10/1/12 11/1/12 | P | P | P | GIS message specific for Upstate LDSS outlining current framework
| 7/6/12 9/7/12 10/15/12 11/15/12 | P | P | P | Follow up GIS with detail as necessary
| 2012-07-10 | P | P | P | NYPWA Presentation
CARE COORDINATION MODEL DEVELOPMENT
| 6/1/11 7/1/11 | P | P | P | Provide staff assistance to MRT workgroup regarding development of guidelines for other care coordination models
| 2011-11-15 | P | P | P | Posting of care coordination model guidance on DOH website
| 2011-12-15 | P | P | P | Certification of Authority application - completed
| 2011-12-15 | P | P | P | Review of applications, as submitted
MLTC CONTRACT PROCESS
| 2012-05-11 | P | P | P | Draft MLTC contract amendment changes for mandatory enrollment and inclusion of CDPAP effective 9/1/12 | No applications received
| 2012-05-01 | 8 | 8 | 8 | Partial Cap Contract to contain autoassignment criteria
| 2012-05-01 | 8 | 8 | 8 | MAP and PACE specific to choice, align with Medicare processing and specific program features
| 2012-07-01 | 8 | 8 | 8 | Complete amendment for inclusion of CDPAP in MLTC
| 7/2/12 8/31/12 10/1/12 11/15/12 | P | P | P | Forward Partial Cap amendment to CMS for approval
| 7/2/12 8/31/12 10/1/12 12/1/12 1/1/13 2/15/13 | P | P | P | Forward Partial Cap amendment to DLA/FMG
| 7/9/12 9/7/12 11/1/12 12/14/12 1/1/13 2/15/13 3/15/13 4/12/13 | P | P | P | Partial cap amendment approved at CMS
| 7/16/12 9/14/12 11/8/12 12/21/12 1/15/13 3/1/13 4/1/13 4/15/13 | P | P | P | Partial cap amendments Issued to Plans for execution
| 7/25/12 9/21/12 11/15/12 1/2/13 1/31/13 3/15/13 4/15/13 5/1/13 | P | P | P | Partial cap complete internal DOH clearance
| 8/1/12 9/28/12 12/1/12 2/1/13 4/15/13 5/1/13 6/1/13 6/21/13 | P | P | P | Partial Cap OSC approval
| 12/20/12 3/1/13 4/1/13 4/19/13 6/1/13 7/1/13 7/22/13 12/1/13 3/1/14 5/30/14 7/1/14 9/1/14 | P | P | P | Forward MAP amendments to CMS for approval
| 7/2/12 8/31/12 10/1/12 12/1/12 3/1/13 4/1/13 4/19/13 6/1/13 7/1/13 7/22/13 9/1/13 12/1/13 3/1/14 5/30/14 7/1/14 9/1/14 | P | P | P | Forward MAP and PACE amendments to DLA/FMG
| 7/9/12 9/7/12 11/1/12 12/14/12 4/1/13 4/15/13 5/1/13 7/1/13 8/1/13 10/1/13 1/1/14 4/1/14 6/30/14 8/1/14 10/1/14 12/1/14 12/22/14 5/29/15 | P | P | P | MAP amendment approved at CMS 8/1/14 will go to 10/1/2014
| 7/25/12 9/21/12 11/15/12 1/2/13 1/31/13 5/1/13 5/15/13 8/1/13 8/15/13 10/15/13 1/15/14 4/15/14 7/15/14 8/15/14 12/12/14 6/12/15 6/19/15 | P | P | P | MAP and PACE complete internal DOH clearance
| 7/16/12 9/14/12 11/8/12 12/21/12 1/15/13 4/15/13 5/15/13 5/22/13 7/15/13 9/1/13 11/1/13 2/1/14 5/1/14 7/30/14 8/30/14 10/30/14 12/18/14 12/29/14 5/29/15 6/30/15 | P | P | P | MAP and PACE amendments Issued to Plans for execution 8/30/14 will go to 10/30/2014
| 8/1/12 9/28/12 12/1/12 2/1/13 6/1/13 6/15/13 8/15/13 10/1/13 11/15/13 3/1/14 6/1/14 8/30/14 9/30/14 11/30/14 2/1/15 7/30/15 | P | P | P | MAP and PACE OSC approval 9/30/14 will go to 11/30/2014
NYC MLTC PLANS ELECTRONIC ENROLLMENT TO MAXIMUS
| 2012-01-24 | P | P | P | Specifications sent to NYC plans
| 2012-02-09 | P | P | P | Open for Testing - ongoing
| 2012-02-29 | P | P | P | HRA/State/Maximus workgroup convenes
| 2012-04-03 | P | P | P | Plan/HRA/Maximus/State Meeting
| 2012-05-21 | P | P | P | Live File Submission - (target)
NYC PLANS - HRA - ELECTRONIC MEDICAID ELIGIBILITY TRANSFER VIA EDITS
| 2012-02-14 | P | P | P | HRA and NYC MLTCP initial presentation
| 2012-06-01 | P | P | P | Operational - target date
MLTC PLANS PROVIDER NETWORK REPORTING TO HCN
| 2011-11-30 | P | P | P | MMC/MLTC plan training for file changes
| 2012-01-23 | P | P | P | MLTC File Development and Submission Q & A
| 2012-01-24 | P | P | P | Internal meeting to discuss TREO specifications
| 2012-03-01 | P | P | P | Test submissions anticipated
| 2012-03-26 | P | P | P | Finalize TREO reporting specifications
| 2012-04-23 | P | P | P | Full network submission
DUAL GRANT IMPLEMENTATION - PHASE TWO (FORMERLY MRT #101) - FIDA - FULL WORKPLAN OUTLINED IN MRT PHASE 3 - #6010
| 4/1/11 4/18/11 | P | P | P | Anticipate receiving planning contract from CMS for planning activities
| 3/30/11 5/30/11 8/1/11 | P | P | P | Receive Medicare part D data from CMS
| 8/30/11 11/15/11 | P | P | P | Receive Medicare A/B data from CMS
| 4/1/11 5-30-11 8/1/11- 10/31/12 | P | P | P | Conduct data analysis of Medicare and Medicaid data on dual eligibles (ongoing)
| 6/1/11 6/17/11 7/23/11 | P | P | P | Select vendor for actuarial work
| 6/1/11 6/17/11 7/23/11 | 8 | 8 | 8 | Select vendor for analytic work
| 6/1/11 6/17/11 7/23/11 9/1/11 10/15/11 10/31/11 | P | P | P | Select vendor for assistance with stakeholder meetings
| 7/1/11 12/15/11 1/15/12 2/13/12 | P | P | P | Recruit, hire and train staff
| 2012-03-22 | P | P | P | Posting of draft proposal for public comment
| 2012-04-10 | P | P | P | 1st Public Consumer Meeting
| 2012-05-04 | P | P | P | Revised proposal posted for comment
| 2012-05-18 | P | P | P | Public meeting conducted
| 2012-05-25 | P | P | P | Revision to CMS
| 2013-08-30 | P | P | P | Readiness Reviews completed, plans finalize policies and procedures
| 2013-08-31 | P | P | P | Three way contract document finalized
CONSUMER DIRECTED PERSONAL ASSISTANCE PROGRAM - PHASE TWO (FORMALLY MRT #1427, PROCESS TO ALIGN WITH #1458)
| 2011-03-15 | P | P | P | OHIP to review implementing regulations to determine if change is required
| 6/1/11 12/1/11 3/1/12 7/23/12 8/31/12 9/14/12 9/28/12 | P | P | P | Develop contracting requirements for MLTC plans and Fiscal Intermediaries | Implementation of FIDA demonstration is outlined in MRT Phase 3 - 6010.
| 1/30/12 3/12/12 5/1/12 6/15/12 8/7/12 9/28/12 | P | P | P | CDPAP Workgroup convened
| 2012-03-12 | P | P | P | Next Meeting
| 2012-04-27 | P | P | P | Internal Meeting to discuss contracting and credentialing issues
| 7/23/12 8/31/12 | P | P | P | Internal Meeting with Legal to discuss noticing criteria
| 7/23/12 8/31/12 9/7/12 | P | P | P | Consult with CMS regarding applicability to PACE Model
| 2012-05-15 | P | P | P | Formulate guidance
| 7/23/12 9/7/12 | P | P | P | Meet with MLTC plans to discuss impact
| 7/23/12 9/7/12 | P | P | P | Assess impact on provider network directory format
| 7/23/12 9/7/12 | P | P | P | Train enrollment broker on addition of benefit
| 7/23/12 9/7/12 10/15/12 | P | P | P | Train LDSS on impact
| 7/23/12 9/7/12 10/1/12 10/15/12 12/1/12 | P | P | P | MLTC submit amended member materials to reflect change in benefit package (ongoing)
| 7/15/12 8/31/12 9/17/12 10/15/12 | P | P | P | Medicaid Update Article Submitted
| 7/23/12 9/7/12 | P | P | P | Outreach completed to providers, plans, advocacy groups (ongoing)
| 7/23/12 9/7/12 9/17/12 9/20/12 | P | P | P | Training completed for Fair Hearing Staff
| 8/1/12 9/6/12 9/20/12 10/1/12 | P | P | P | Announcement letter to CDPAP users
| 9/1/12 10/1/12 11/1/12 | P | P | P | Implementation September October November 2012 new users
| 9/1/12 9/6/12 9/27/12 11/1/12 | P | P | P | Begin noticing CDPAP Users according to Enrollment Plan
MLTC LEGISLATIVE REPORT
| 2012-06-01 | P | P | P | Identify Data to meet legislative report requirements
| 2012-07-02 | P | P | P | Initiate draft report for internal review
| 2012-07-22 | P | P | P | Resolve any issues with draft report raised during internal review
| 8/1/12 8/24/12 | P | P | P | Draft report into Executive Clearance
| 9/1/12 10/1/12 11/15/12 12/4/12 | P | P | P | Report delivered to the Legislature
| 11/1/12 12/1/12 | P | P | P | Begin revisions to data gathering, reporting format and strategy, as warranted
| 1/15/13 1/22/13 | P | P | P | Draft quarterly report for internal review
| 2013-02-01 | P | P | P | Draft report into Executive Clearance
| 3/1/13 3/15/13 4/1/13 4/12/13 | P | P | P | Report delivered to the Legislature
| TBD |  |  |  | Additional Activities For 1115 Terms and Conditions (TBD)
93 |  |  |  |  | Project Name: Establish behavioral health organizations (BHOs) to manage carved-out behavioral health services Division Lead: DFPP Team Lead: Bob Myers (OMH) Add'l staff: Priscilla Smith, Lauren Tobias, Cynthia Buswell, Jackie Allaman, Mark Tremblay Description: Use BHOs to manage behavioral health services that are provided outside of managed care. OASAS lead: Rob Kent | -4 | Completed
| 2011-03-31 | P | P | P | Submit FPN
| 2011-04-01 | P | P | P | Obtain State legislative authority
| 2011-04-11 | P | P | P | DOH/OMH/OASAS meeting scheduled to determine roles and responsibillities
| 2011-05-12 | P | P | P | Meet with stakeholders
| 2011-05-16 | P | P | P | Meet with stakeholders
| 2011-05-13 | P | P | P | Determine BHO program requirements including relationship to health homes
| 2011-05-27 | P | P | P | Determine eMedNY system requirements
| 5/27/11 6/17/11 | P | P | P | Determine BHO payment methodology
| 6/3/11 7/1/11 | P | P | P | Begin development of interagency MOU identifying each agencies roles and responsibilities in administering and managing the BHO initiative
| 2011-06-10 | P | P | P | Develop BHO contract award criteria including min. network, financial, information systems
| 2011-06-24 | P | P | P | Post contract requirements on web
| 2011-06-24 | P | P | P | Solicit bids
| 2011-07-07 | P | P | P | Bidders conference
| 2011-08-05 | P | P | P | Review bids
| 8/19/11 8/23/11 | P | P | P | Select vendors
| 9/15/11 10/15/11 | P | P | P | Complete readiness reviews
| 10/1/11 11/1/11 | P | P | P | Implement program
| 8/26/11 9/30/11 10/8/11 11/25/11 | P | P | P | Finalize contracts with BHOs (NYC, Central Region, Western Region, Hudson Valley)
| 2011-12-23 | P | P | P | Finalize contracts with Long Island BHO
| 2011-10-01 | 8 | 8 | 8 | Implement eMedNy system edits
| 2012-01-01 | P | P | P | Full BHO implementation (NYC, Central Region, Western Region, Hudson Valley)
| 2012-02-01 | P | P | P | Full BHO implementation (Long Island)
| 2013-04-01 | 8 | 8 | 8 | Determine capacity and financial ability of NYC Special Needs Plans (SNPs) to be designated as regional BHO
102 |  |  |  |  | Project Name: Centralize Responsibility for Medicaid Trauma & Estate Recovery Process Division Lead: OMIG Portfolio Manager: Katherine Napoli / Alicia Whitlingum Project Lead: Jeff Flora Description: Statewide responsibility for making Medicaid recoveries from the estates of deceased recipients, in personal injury actions and in legally responsible relative refusal cases. | -10 | Completed
DRIVE METHODOLOGY FOR SAVINGS
| 2011-04-29 | P | P | P | Develop methodology
| 2011-05-06 | P | P | P | Complete Budget Savings Form
| 2011-05-20 | P | P | P | Approval by BBFM
| 2011-04-28 | P | P | P | Update MRS in FACTS
| 2011-05-27 | P | P | P | Derive Methodology for Savings Completed
OUTREACH ACTIVITIES
| 2011-06-02 | P | P | P | Submit to NYPWA Presentation Description
| 2011-07-31 | P | P | P | Conduct presentation at NYPWA in July
| 2011-07-01 | P | P | P | Review Rockefeller study
| 2011-05-24 | P | P | P | OMIG Finalize Local Commissioners Memorandum (LCM)
| 2011-05-24 | P | P | P | Submit to OHIP for distribution
| 2011-05-26 | P | P | P | M-Tag Meeting
IMPLEMENTATION SEPTEMBER OCTOBER NOVEMBER 2012 NEW USERS
VOLUNTARY (IN PROCESS)
| 2011-04-25 | P | P | P | Identify interested counties
| 2011-06-01 | P | P | P | Initiate negotiations with Implement with first interested counties
| 6/1/11 7/1/11 | P | P | P | Start reporting recoveries
LEGISLATION ENACTMENT
| 2011-03-14 | P | P | P | Identify state statutes • Social Services Law §§104, 104-b, 369 • Administrative Directive 02 OMM/ADM - 3
| 2011-05-31 | P | P | P | Review and obtain clarification on statutory authority for OMIG to collect Public Assistance recoveries.
| 2011-08-15 | P | P | P | Finalize Explore the feasibility of drafting a MOU with OTDA regarding access to PA data
CONCEPT REGULATION
| 12/30/11 6/1/12 | 8 | 8 | 8 | Propose regulation changes, if needed
| 4/2/12 7/1/12 | 8 | 8 | 8 | Obtain approval of regulation changes
| 4/2/12 9/1/12 | 8 | 8 | 8 | Implement Regulation changes
| 2011-12-30 | 8 | 8 | 8 | If necessary, expand OMIG enabling Statute regarding to include Public Assistance.
| 2011-12-30 | 8 | 8 | 8 | Amend state regulatory and statutory authority to perform estate and casualty for medical assistance data. Social Services Law §§104, 104-b, 369 language. Purpose is to provide statutory authority at State level to perform estate and casualty recovery of public assistance and medical care.
| 2011-12-30 | 8 | 8 | 8 | Develop consistent State authority policy language required within 02 OMM/ADM - 3 and administrative directive, as needed
| 2011-12-30 | 8 | 8 | 8 | Create new legislation under SSL §369 -req notice of estate and casualty filings be given to the State by attorneys, workers' compensation, liability & no-fault carriers. May include penalty language consistent with Medicare, Medicaid, Medicaid, and SCHIP. Review current state and casualty requirements to state certain estate and casualty matters and expand regulation, as needed
| 2011-12-30 | 8 | 8 | 8 | Create new leg allowing State to hold PIA (Personal Incident Account) funds as the probate jurisdiction administering the estate. Purpose of legislation is to avoid payment of fees and commissions to the PA for appointment to handle all PIA funds.
| 2011-12-30 | P | P | P | Social Services Law §369(6) - Expand definition of "estate" to include non-probate assets (MRT#132). Purpose of law is to increase available assets for recovery
| 2011-12-30 | 8 | 8 | 8 | Propose Legislation changes
| 2012-04-02 | 8 | 8 | 8 | Obtain approval of legislation changes
| 2012-04-02 | 8 | 8 | 8 | Implement Legislative changes
Improve Medicaid Lien Recovery
| 2012-12-31 | P | P | P | Establish database system of claimants
| 2012-12-31 | P | P | P | Establish mechanism for recovery of funds
103 |  |  |  |  | Project Name: Reduce Inappropriate Use of Certain Services Division Lead: DHCF Team Lead: Ann Heilmann Add'l Staff: Laura Grassmann Description: This proposal would institute financial incentives to reduce inappropriate use of cesarean deliveries. | -12.1 | Completed
ADMINISTRATIVE
| 2011-03-25 | P | P | P | Full policy definition to clarify services and actions: -Initial denial of c-section claims / quality incentives on others
| 2011-03-30 | P | P | P | Federal Public Notice publication
| 2011-04-01 | P | P | P | Regulations
| 2011-04-01 | P | P | P | Draft State Plan Amendment to CMS
| 5/30/11 6/30/11 | P | P | P | Revise Draft State Plan Amendment and send to CMS
| 2011-06-15 | P | P | P | Revise Regulations
| 5/30/11 6/15/11 | P | P | P | Revise Federal Public Notice publication
| 2011-06-15 | 8 | 8 | 8 | Assessment of public comment from obgyn doctor regarding email dated 4/20/11 (Karla)
| 7/1/11 7/15/11 | P | P | P | Model reduction to Statewide Base Price for $24.2M savings and provide to Managed Care and BPACR
| 8/31/11 11/30/11 12/15/11 | P | P | P | Implement reduction to Statewide Base Price
RESEARCH AND DEVELOPMENT
| 2011-03-25 | P | P | P | Discuss with 3M an appropriate DRG and severity level assignment for the initial claim default payment
| 2011-04-15 | P | P | P | Discuss clinical standards for 'medically necessary' cases with Department Medical Directors
| 2011-04-12 | P | P | P | Meet with Department Medical Director and Division of Quality and Evaluation to discuss alternatives to using an appeal process: standard payment for all deliveries
| 2011-04-20 | P | P | P | Meet with IPRO and OHSM to begin appeal process discussions.
| 2011-04-28 | P | P | P | Analyze option to adjust SIW's as an alternative to appeals
| 2011-04-28 | P | P | P | Meet with IPRO, DPR and DOIT to discuss details on appeal process/systems issues
| 2011-04-29 | P | P | P | Meet with DQE and Medical Director to discuss all available implementation options
| 2011-05-05 | P | P | P | Key decision to be made whether or not to include Managed Care
| 5/5/11 5/30/11 | 8 | 8 | 8 | Meet with IPRO and Medical Directors to discuss clinical details for appeals
| 2011-06-30 | P | P | P | Meet with OB workgroup to discuss next steps
SYSTEM ISSUES
| 2011-03-21 | P | P | P | Discuss timeframe / steps for systems requirements with Division of Information Technology
| 4/30/11 5/30/11 | 8 | 8 | 8 | Submit evolution project for eMedNY program changes - on hold
| 5/15/11 5/30/11 | 8 | 8 | 8 | Retroactive appeals need to be considered - on hold
COMMUNICATION WITH STAKEHOLDERS
| 2011-05-17 | P | P | P | Meet with Associations to discuss impact on providers - conference call held to discuss alternative options, agreement reached
| 5/15/11 6/15/11 | 8 | 8 | 8 | Develop a Q & A Document - on hold
| 2011-05-30 | 8 | 8 | 8 | Notify Providers through the Medicaid Update - on hold
| 2011-05-30 | 8 | 8 | 8 | Work with Provider Relations to develop communication strategy - on hold
SAVINGS METRIC
| 2011-05-01 | 8 | 8 | 8 | Identify a process to identify savings including effect on appeals and develop a metric for calculating and tracking savings
ADDITIONAL QUALITY INITIATIVES
| 5/30/11 6/30/11 | 8 | 8 | 8 | Begin discussions with the Division of Quality and Evaluation to identify additional cost saving services (including CABG & PCI procedures)
| 5/30/11 6/30/11 | 8 | 8 | 8 | Meet with Department Medical Directors and Division of Quality and Evaluation to discuss options for quality incentives
| 5/30/11 6/30/11 | 8 | 8 | 8 | Identify measures to be put into place to improve quailty and reduce utilization
| 5/30/11 6/30/11 | 8 | 8 | 8 | Identify a means to relay the quality measures to providers
| 5/30/11 6/30/11 | 8 | 8 | 8 | Implement plan to inform providers of quality measures
109 |  |  |  |  | Project Name: Requires Hospitals and Nursing Homes to provide Patient Centered Palliative Care Division Lead: OHSM - DPSQ Team Lead: Anna D. Colello, Esq., additional staff Karen Lipson Description: To inform patients about palliative care and pain management options in hospitals, nursing homes, home care, special needs assisted living residences and enhanced assisted living residences pursuant to PHL 2997-d | 0 | Completed
| 2011-03-15 | P | P | P | Task 1 - Develop project management plan (the plan will include stakeholders within the department, provider associations and appropriate palliative care council members who have expertise in this area.
| 2011-03-15 | P | P | P | Task 2 - Review tools developed for the implementation of Palliative Care Information Act which can be used to inform all providers.
| 2011-03-21 | P | P | P | Task 3 - Schedule meeting with Department staff in the hospital, nursing home, home care and assisted living programs. (Mary Ellen Hennessy/Ruth Leslie/Jackie Pappalardi/Val Deetz/Mary Ann Anglin/Becky Fuller-Gray and Mary Hart) To discuss: (a) the development of standards for compliance with PHL 2997-d (b) the development of guidance tools based on these standards which can be used by surveillance staff to monitor compliance (c) the development of a dissemination plan for this information using such department communication formats such as "Dear Administrator" letters (d) the processes that already exist in each of these settings to provide health information to the patient/resident/consumers for whom they care.
| 2011-04-11 | P | P | P | Task 4 -2nd call with DOH program staff
| 2011-04-25 | P | P | P | Task 5 - Meet with Hospital Associations (HANYS-Kathy Ciccone/Mary Therriault and Greater New York-Lorraine Ryan) on 4/25/11 to review requirement and seek input as to what systems exist in hospitals and nursing homes to convey patient information: (a) how would they identify appropriate patients to receive the information (b) how would they document the information was given (c) what information (resources found on DOH website, Palliative Care page)
| 2011-04-25 | P | P | P | Task 6 - Meet with Nursing Home Associations (NYASA-Elliot Frost, NYSHFA-Nancy Leveille and HANYS-Deb LeBarron) Discuss same questions as above.
| 2011-04-25 | P | P | P | Task 7 - Meet with Home Care and Assisted Living Associations (HCA-Andrew Koski, HCP-Margaret Gorman/Christina Miller-Foster and ESAAL-Lisa Newcomb). Discuss same questions as above.
| 2011-04-27 | P | P | P | Task 8 - Palliative Care Council meeting already scheduled. This topic could be added to agenda to seek input from experts on the council in hospitals, nursing homes and home care. Discuss same questions as above.
| 2011-05-10 | P | P | P | Task 9 - Met with Hospice and Palliative Care Association. Discussed services available in each county and collaborations which can be developed among providers in community.
| 2011-05-31 | P | P | P | Task 10- Meet with Dr Diane Meier to discuss how the Center to Advance Palliative Care can assist in being a resource to entities required by PHL 2997-d to facilitate access to palliative care services.
| 2011-06-27 | P | P | P | Task 11 - Meeting with associations of Hospitals, Nursing Homes, Home Care, Assisted Living to review first draft of Questions and Answers. Response due date is July 8th
| 2011-07-13 | P | P | P | Task 12 - meeting of the Palliative Care Education and Training Council. Seeking guidance on FAQs
| 2011-09-14 | P | P | P | Task 13 - Train DOH regional surveillance staff who will be investigating complaints relative to violations of this law.
| 9/10/11 9/23/11 | P | P | P | Task 14 - Develop Dear Administrator letter setting forth the requirements, which includes how information will be provided, how DOH programs will monitor compliance and what resources are available.
| 9/6/11 9/23/11 9/26/11 | P | P | P | Task 15 - OLTC executive approval
| 2011-09-26 | P | P | P | Task 16 - Submit FAQs for OHSM
| 2011-09-27 | P | P | P | Task 17 - Law effective
| 2011-10-03 | P | P | P | Task 18 - OHSM Approval
| 2011-10-19 | P | P | P | Circulate IPR of FAQs for DOH website and HCS
| 2011-10-31 | P | P | P | Present to the Palliative Care Education and Training Council
| 11/14/11 11/25/11 12/8/11 12/15/11 | P | P | P | Guidance posted to DOH website
116 |  |  |  |  | Project Name: Accelerate IPRO Review of Medically Managed Detox Division Lead: DPDM Team Lead: Priscilla Smith Description: Refocus Island Peer Review Organization (IPRO) reviews of medically managed withdrawal cases from those based on DRG rates to those using the new rate codes | -1.1 | Completed
| 2011-03-25 | P | P | P | Discuss scope of project with OASAS staff
| 2011-05-02 | P | P | P | Contact DOH IPRO coordinator to determine options for refocused review models, given scope of current contract
| 2011-05-06 | P | P | P | Consult with OASAS staff to determine optimal model for refocused reviews
| 2011-05-06 | P | P | P | Contact IPRO to discuss timeline for implementation of new review methodology
| 2011-05-16 | P | P | P | Determine whether contract amendment is required
| 2011-06-27 | P | P | P | Review (with OASAS and IPRO ) protocol and tools for refocused IPRO reviews
| 6/27/11 7/20/11 | P | P | P | Finalize (with OASAS and IPRO) protocol and tools for refocused IPRO reviews
| 2011-10-01 | P | P | P | Effective implementation date
129 |  |  |  |  | Project Name: Minimize Anti-Trust Exposure by Supervising Integration of Providers Division Lead: OPCHSM Team Lead: Elsie Chun Description: Implement regulatory framework to provide active supervision and confer anti-trust immunity on providers that are merging, consolidating, integrating operations. |  | Completed
| 2011-04-01 | P | P | P | Enactment of legislation
| 2011-04-30 | P | P | P | Assemble internal work group
| 2011-05-02 | P | P | P | Consult with NYS attorney general's office
| 2011-06-30 | P | P | P | Draft regulations
| 2011-07-15 | P | P | P | Consult with stakeholders
| 7/15/11 7/26/11 | P | P | P | Present regulations to Governor's Counsel's Office
| 2011-07-21 | 8 | 8 | 8 | Present draft regulations to PHHPC committee for discussion
| 2011-08-04 | 8 | 8 | 8 | Brief PHHPC on regulations
| 2011-09-22 | P | P | P | Discuss regulations at PHHPC committee
| 2011-10-06 | 8 | 8 | 8 | Discuss regulations at PHHPC Full Council
| 2011-02-15 | P | P | P | Work with AG's office to address stakeholder comments
| 2013-03-01 | P | P | P | Work with AG's office, Governor's Counsel's office and stakeholders to resolve open issues.
| 8/22/11 9/15/11 10/11/11 11/14/11 12/15/11 1/15/11 3/15/12 5/15/12 10/1/12 1/7/13 3/4/13 6/15/13 7/1/13 8/30/13 | P | P | P | Secure Governor's Counsel's Office approval of regulations
| 12/28/11 4/15/12 6/27/12 10/31/12 12/15/12 2/15/13 3/20/13 4/24/13 5/15/13 7/10/13 9/25/13 9/18/13 | P | P | P | Publish in State Register for 45-day comment period
| 12/28/11 4/15/12 6/27/12 10/31/12 1/02/13 2/28/13 3/25/13 4/29/13 5/20/13 8/24/13 11/9/13 12/6/13 1/31/14 3/31/14 6/2/14 | P | P | P | Prepare response to public comments, if any
| 1/15/12 4/30/12 7/14/12 11/15/12 01/15/13 3/15/13 3/29/13 5/6/13 6/3/13 | 8 | 8 | 8 | Present to PHHPC Codes Committee and Council for adoption.
| 6/18/14 8/27/14 | P | P | P | Publish in Notice of Revised Rulemaking in State Register - 30 day comment period
| 12/28/11 1/18/12 2/18/12 3-28-12 5-28-12 8/8/12 12/20/12 4/10/13 6/5/13 6/19/13 9/18/13 11/27/13 12/21/13 03/12/14 4/16/14 5/16/14 7/9/14 12/10/14 12/17/14 | P | P | P | Publish Notice of adoption in State Register (Send to DOS on 12/2/14)
131 |  |  |  |  | Project Name: Reform Medical Malpractice and Patient Safety Division Lead: OHSM Team Lead: Lora Lefebvre Description: Create a neurologically impaired inant medical indemnity fund and establish a cap on non-economic damages in medical malpractice cases in addition to exploring other alternatives. | -43 | Completed
[5 empty] | Project Name: Medical Malpractice Reform Division Lead: Insurance /Health Team Lead: Sapna Maloor/Lora Lefebvre Description: Medical Indemnity Fund |  | Completed
| 2011-04-30 | P | P | P | Identify and start scheduling meetings with stakeholders (GNYHA, HANYS,Mediciad Matters, ACOG, MSSNY, UCP,March of Dimes, Med Mal insurers, other insurers, Office of Court Adminsration, Bar Association)
| 2011-04-30 | P | P | P | Conduct internal state stakeholder meetings (DoH- Early Intervention, OLTC Waiver program; OPWDD, ACCES, Tax Department, Education Department
| 2011-05-01 | P | P | P | Start selection process for a fund administrator
| 2011-05-01 | P | P | P | Initiate development of regulations relating to: claims process and form development, definition of medically necessary costs (refer to Medicaid and Medicaid waiver projects); dispute resolution/appeal process; Medicaid lien identification; expense certification to Tax & Finance
| 2011-05-15 | P | P | P | Begin website development (Fund Administrator or Departments)
| 2011-05-30 | P | P | P | Begin to identify consumer advisory committee members/schedule meetings; add to fund administrator responsibliites
| 5/15/11 5/22/11 8/1/11 | P | P | P | Explicit directions on HCRA transfer to Fund
| 6/1/11 7/15/11 8/30/11 9/13/11 | P | P | P | Intiate notification of consumers, providers of service and insurers about Indemnity Fund
| 6/15/11 7/15/11 8/22/11 9/6/11 10/1/11 10/8/11 | P | P | P | Choose fund administrator
| 6/15/11 7/15/11 8/22/11 9/6/11 10/1/11 10/8/11 | P | P | P | Identify actuarial resources
| 7/1/11 9/1/11 10/1/11 10/8/11 | P | P | P | Establish fund with Tax & Finance
| 6/15/11 7/15/11 8/22/11 9/6/11 10/1/11 10/8/11 11/25/11 1/1/12 2/1/12 4/1/12 8/28/12 | P | P | P | Establish current year's actuarial estimate for fund
[5 empty] | Project Name: Hospital Quality Initiative - develop the Hospital Safety Insititute Team Lead: Pat Roohan Additional Staff: Joe Anarella, Hope Plavin |  | Completed
| 2011-05-15 | P | P | P | Meet with stakeholders (GNYHA, HANYS, MSSNY, ACOG,Art Levin)
| 2011-05-30 | P | P | P | Recommend stakeholders to Commissioner
| 8/15/11 9/15/11 10/1/11 10/15/11 12/15/11 2/15/12 5/1/12 7/30/12 11/13/12 2/14/13 3/14/13 4/15/13 | P | P | P | Finalize membership
| 6/30/11 9/30/11 11/1/11 1/1/12 5/15/12 7/30/12 12/13/12 2/14/13 3/14/13 5/15/13 | P | P | P | Hold organizing meeting to identify ob safety programs
| 8/30/11 11/30/11 1/30/12 6/30/12 7/30/12 2/15/13 3/15/13 5/15/13 6/15/13 | P | P | P | Develop a multi-year plan on programs to intiate with provider community
| 9/30/11 12/30/11 2/28/12 7/30/12 3/15/13 4/15/13 5/15/13 9/15/13 | P | P | P | Identify first year projects and resources
| 10/15/11 1/15/12 3/15/12 8/15/12 4/15/13 5/15/13 9/15/13 11/5/13 | P | P | P | Convene stakeholders group to develop program and discuss implementation
Hospital Quality Contribution Assessment
| 2011-03-31 | P | P | P | Discuss how to incorporate into the current Health Facility Cash Assessment Program (HFCAP) for hospitals. Collections have to be reported and deposited separately.
| 2011-03-31 | P | P | P | Schedule conference call with Pool Administrator to discuss program
| 2011-05-02 | P | P | P | Create Hospital list
| 2011-05-20 | P | P | P | Design electronic report
| 2011-05-20 | P | P | P | Develop reporting due date schedule
| 2011-05-20 | P | P | P | Create instructions for report
| 5/31/11 6/15/11 | P | P | P | Notify Providers of Hospital Quality Contributions assessment using letters\website.
| 2011-06-15 | P | P | P | Conclude discussions with the Hospital Associations about the assessable revenue and the rates of the Hospital Quality Contribution
| 2011-06-15 | P | P | P | Confirm accounts for transferring funds/e-mail notification
| 5/31/11 6/30/11 | P | P | P | Test electronic report
| 2011-06-30 | P | P | P | Process State Regulation package to change the HFCAP rate from 1.6% to 3.2% 2.4% to ensure that the mandated $30M is collected
| 5/31/11 6/30/11 7/12/11 | P | P | P | Post all appropriate materials to DOH website
| 6/6/11 6/30/11 7/31/11 | P | P | P | Incorporate into existing HFCAP database but account for reporting and payments separately
| 7/15/11 8/15/11 | P | P | P | Develop required reports for budgeting purposes for collections/transfers etc.
| 7/15/11 8/30/11 | P | P | P | Develop Cost Estimates based on ICR data for billing
| 2011-12-01 | P | P | P | Evalutate if the current HQC rate (1.6%) is adequate to collect the $30M tartget.
| ongoing, beginning Dec 2011 | P | P | P | Bill Delinquent Hospitals Quarterly - the initial billing cycle will likely have issues requiring immediate attention and will likely result in a significant increase in phone calls from the hospitals.
| ongoing, beginning Jan 2012 | P | P | P | Send Delinquent Hospitals billings to MA for Recoupment
| ongoing | P | P | P | Answer provider phone calls
| ongoing | P | P | P | Reconcile to make sure outstanding balance in Medicaid matches outstanding balance on database
132 |  |  |  |  | Project Name: Expand the Definition of Estate Division Lead: DCE Team Lead: Wendy Butz Description: Expand definition of "estate" to include assets that bypass probate in order to recover more assets from the estate of a deceased Medicaid recipient. Estate recoveries are pursued from the estate of deceased Medicaid recipients who were permanently institutionalized and from the estate of deceased Medicaid recipients over age 55. Expand the definition of estate to allow recovery against non-probate assets (assets that fall outside of the estate, e.g. joint bank accounts, life estate interest) | 0 | Completed
POLICY AND PROCEDURE
| 2011-04-15 | P | P | P | Complete review of policy issues
| 5/16/2011 5-20-11 | P | P | P | Submit draft ADM for clearance
| 6/1/2011 6/17/11 7-25-11 8-5-11 8-26-11 9/30/11 | P | P | P | Issue ADM
STATE PLAN AMENDMENT
| 2011-04-22 | P | P | P | Submit draft SPA to DHCF for submission to CMS for informal review
REGULATION AMENDMENT
| 6/1/11 6/17/11 6/28/11 | P | P | P | Submit emergency regulation change (package in clearance)
| 7/22/11 8/5/11 8/26/11 9/8/11 | P | P | P | Adopt regulation
ESTATE RECOVERY REPORTING
| 2011-03-31 | P | P | P | Complete review of quarterly reports for estate recoveries
| 5/30/11 6/10/11 7/22/11 | P | P | P | Submit proposed changes to estate recovery reporting - quarterly report identifies amounts recovered from non-probate assets in order to track savings.
133 |  |  |  |  | Project Name: Administrative Renewal for Aged, Blind, and Disabled and Medicare Savings Program (MSP) Participants Division Lead: DCE Team Lead: Wendy Butz Description: Allow aged, blind and disabled with fixed incomes to be automatically renewed based on cost of living increases. | -0.3 | Completed
POLICY AND PROCEDURE
| 2011-04-30 | P | P | P | Complete review of policy issues
| 7/1/11 7/22/11 8/15/11 9/23/11 10/7/11 | P | P | P | Submit draft ADM for clearance
| 10/1/11 10/14/11 | P | P | P | Issue ADM - effective 1/01/2012
SYSTEMS UPDATES
| 2011-04-01 | P | P | P | Submit System Change Request
| 2011-04-15 | P | P | P | Finalize system change requirements
| 5/17/11 6-10-11 7/26/11 | P | P | P | Finalize System Action Request - Aged, Blind, Disabled
| 5/17/11 6/10/11 8/1/11 8/15/11 9/5/11 10/15/11 | P | P | P | Finalize System Action Request - MSP
UPSTATE
Phase 1 - Aged, Blind, Disabled
CNS
| 2011-05-17 | P | P | P | Submit new CNS renewal notices
| 8/22/11 11/18/11 | P | P | P | Development/coding changes
| 10/7/11 1/2/12 | P | P | P | Unit testing
| 10/12/11 1/2/12 | P | P | P | User Acceptance
WMS
| 8/22/11 11/18/11 | P | P | P | Development/coding changes
| 10/7/2011 1/2/12 | P | P | P | Unit testing
| 10/12/11 1/2/12 | P | P | P | User Acceptance
MBL
| 8/22/11 11/18/11 | P | P | P | Development/coding changes
| 10/7/11 1/2/12 | P | P | P | Unit testing
| 10/12/11 1/2/12 | P | P | P | User Acceptance
| 2012-01-07 | P | P | P | Migrate system changes (October 17 2011 .. 11.3 migration) First run is 1st weekend in January for cases expiring 3/31/12
Phase 2 - MSP QMB & SLIMB
CNS
| 2012-03-02 | P | P | P | Submit new CNS renewal notices
| 2012-04-09 | P | P | P | Development/coding changes
| 2012-05-14 | P | P | P | Unit testing
| 2012-05-25 | P | P | P | User Acceptance
WMS
| 2012-04-09 | P | P | P | Development/coding changes
| 2012-05-14 | P | P | P | Unit testing
| 2012-05-25 | P | P | P | User Acceptance
MBL
| 2012-04-09 | P | P | P | Development/coding changes
| 2012-05-14 | P | P | P | Unit testing
| 2012-05-25 | P | P | P | User Acceptance
| 2012-06-02 | P | P | P | First run is 1st weekend in June 2012 for cases expiring 8/31/12
Phase 3 - MSP QI
CNS
| 2012-03-02 | P | P | P | Submit new CNS renewal notices
| 2012-04-09 | P | P | P | Development/coding changes
| 2012-05-14 | P | P | P | Unit testing
| 2012-05-25 | P | P | P | User Acceptance
WMS
| 2012-04-09 | P | P | P | Development/coding changes
| 2012-05-14 | P | P | P | Unit testing
| 2012-05-25 | P | P | P | User Acceptance
MBL
| 2012-04-09 | P | P | P | Development/coding changes
| 2012-05-14 | P | P | P | Unit testing
| 2012-05-25 | P | P | P | User Acceptance
| 2012-06-09 | P | P | P | Run is 2nd weekend in June 2012. These are done yearly from a flat file.
DOWNSTATE
PHASE 1 - AGED, BLIND, DISABLED
CNS
| 2011-05-17 | P | P | P | Submit new CNS renewal notices
| 8/22/11 11/18/11 | P | P | P | Development/coding changes
| 2012-01-18 | P | P | P | Unit Testing begin
| 1/27/12 2/28/12 6/30/12 9/30/12 11/3/12 1/15/13 2/28/13 5/31/13 | P | P | P | Unit testing completed
WMS
| 8/22/11 11/18/11 | P | P | P | Development/coding changes
| 2012-01-18 | P | P | P | Unit Testing begin
| 1/27/12 2/28/12 6/30/12 9/30/12 11/3/12 1/15/13 2/28/13 5/31/13 | P | P | P | Unit testing completed
MBL
| 8/22/11 11/18/11 | P | P | P | Development/coding changes
| 2012-01-18 | P | P | P | Unit Testing begin
| 1/27/12 2/28/12 6/30/12 9/30/12 11/3/12 1/15/13 2/28/13 5/31/13 | P | P | P | Unit testing completed
LOCAL DISTRICT INTERFACES
| 2011-04-25 | P | P | P | Define changes to existing renewal interfaces (i.e. EDITS, MRT, CHEM)
| 8/22/11 11/18/11 | P | P | P | Development/coding changes
| 2012-01-18 | P | P | P | Unit Testing begin
| 1/27/12 2/28/12 6/30/12 9/30/12 11/3/12 1/15/13 2/28/13 5/31/13 | P | P | P | Unit testing completed
| 2/4/12 3/3/12 4/7/12 9/30/12 10/6/12 11/3/12 1/2/13 3/2/13 6/1/13 | P | P | P | First pull normal cases expiring 6/30/12 9/30/12 3/31/13 8/31/13
| 2/4/12 3/3/12 4/7/12 7/31/12 10/6/12 12/1/12 3/2/13 6/1/13 | P | P | P | Implementation - Aged, Blind, Disabled
PHASE 2 - MSP - ALL REFERENCES TO WMS/CNS/MBL HAVE BEEN DELETED AS THIS WILL BE IMPLEMENTED ON THE HEALTH EXCHANGE
CNS
| 7/16/12 10/1/12 11/1/12 1/2/13 3/2/13 | 8 | 8 | 8 | Development/coding changes completed
| 7/18/12 10/5/12 2/1/13 4/1/13 6/1/13 | 8 | 8 | 8 | Unit Testing begin
| 8/30/12 12/31/12 4/30/13 6/30/13 8/30/13 | 8 | 8 | 8 | Unit testing completed
WMS
| 7/16/12 10/1/12 11/1/12 1/2/13 3/2/13 | 8 | 8 | 8 | Development/coding changes completed
| 7/18/12 10/5/12 2/1/13 4/1/13 6/1/13 | 8 | 8 | 8 | Unit Testing begin
| 8/30/2012 12/31/12 4/30/13 6/30/13 8/30/13 | 8 | 8 | 8 | Unit testing completed
MBL
| 7/16/12 10/1/12 11/1/12 1/2/13 3/2/13 | 8 | 8 | 8 | Development/coding changes completed
| 7/18/12 10/5/12 2/1/13 4/1/13 6/1/13 | 8 | 8 | 8 | Unit Testing begin
| 8/30/12 12/31/12 4/30/13 6/30/13 8/30/13 | 8 | 8 | 8 | Unit testing completed
LOCAL DISTRICT INTERFACE WITH HIX
| 7/1/12 6/1/15 | 8 | 8 | 8 | Define changes to existing renewal interfaces with HIX for implementation through HIX (i.e. EDITS, MRT, CHEM)
| 7/16/12 10/1/12 11/1/12 1/2/13 3/2/13 | 8 | 8 | 8 | Development/coding changes completed
| 7/18/12 10/5/12 2/1/13 4/1/13 6/1/13 | 8 | 8 | 8 | Unit Testing begin
| 8/30/12 12/31/12 4/30/13 6/30/13 8/30/13 | 8 | 8 | 8 | Unit testing completed
| 9/1/12 10/6/12 12/31/12 5/1/13 7/1/13 9/1/13 10/3/15 | 8 | 8 | 8 | Implementation - MSP automated renewal on the HIX
134 |  |  |  |  | Project Name: Audit of Cost Reports submitted by hospitals; replacing CPA certifications Division Lead: DHCF Team Lead: Jane Casale Description: Contract with independent certified public accounting firms licensed in NYS to conduct annual field and desk audits of the Institutional Cost Reports | -0.75 | Completed
| 2011-03-30 | P | P | P | Federal Public Notice
| 2011-04-01 | P | P | P | SPA submission date
| 2011-04-01 | P | P | P | Draft regulation to collect audit fees for review by Administration
| 2011-04-04 | P | P | P | Briefing the industry on the tentative Audit plan
| 2011-04-08 | P | P | P | Draft FAS (Funding Availability Solicitation) RFP for review by OHIP administration
| 7/29/11 5/23/11 5/01/11 | P | P | P | RFP FAS submitted for DOH review (Including Form 2333 and EDC Form)
| 6/17/11 5/23/11 5/1/11 | P | P | P | Deliver fee schedule for billing and collection. Post to DOH Website.
| 7/20/11 6/01/11 5/1/11 | P | P | P | Attachment A approval (Dependent upon budget approval)
| 6/20/11 5/31/11 | P | P | P | Due Date of Cost Report
| 8/04/11 8/26/11 7/1/11 | P | P | P | Release of RFP through Contract Reporter and to designated list. Release of FAS to designated list. Release of RFP through Contract Reporter
| 8/15/11 9/07/11 7/10/11 | P | P | P | Written questions due from bidders
| 8/25/11 9/19/11 7/21/11 | P | P | P | Response to written questions from the Department to the bidders
| 9/15/11 9/08/11 9/28/11 8/01/11 | P | P | P | Proposal due from bidders to the Department
| 10/12/11 11/15/11 | P | P | P | Evaluation completed; return to OHIP Contracting for approval
| 10/23/11 10/17/11 10/24/11 9/1/11 |  |  |  | Negotiation of contract terms after award. Finalization of form 2333.
| 10/27/11 9/15/11 | P | P | P | Finalization of Audit Plan - Present to industry
| 12/28/11 2/3/12 2/29/12 | P | P | P | Set up account for payments from hospitals. Notify hospitals of procedure.
| 2012-02-14 | P | P | P | Form B1184 - # 12000-1314-2011
| 2/14/12 1/26/12 1/03/12 11/07/11 | P | P | P | Award of Contract
| 3/02/12 1/20/12 12/12/11 11/1/11 4/25/12 | P | P | P | Commencing of Audit (ICR 2010)
139 |  |  |  |  | Project Name: Implement the new waiver for LTHHCP Division Lead: OLTC - DHCBS Team Lead: Lydia Kosinski Add'l Staff: Tim Casey, Vicki Rockefeller Description: To implement the new enhancements of the LTHHCP waiver, initiating the opportunities for increased Medicaid cost-savings and performance. | 0 | Completed
| 2011-05-01 | P | P | P | Issue Implementation guidance to LDSS (ADM) and LTHHCP (DAL) agencies
| 2011-05-18 | P | P | P | Conference call with local districts for questions related to issued guidance
| 2011-06-03 | P | P | P | Draft Medicaid Update article with claiming instructions for LTHHCP providers related to new/expanded services
| 6/15/11 7/1/11 | P | P | P | Rates officially established for new waiver services, contingent on issuance of final rates
| 7/15/11 8/15/11 | P | P | P | Preliminary review and comment of of the revised LTHHCP provider manual by selected local districts
| 2011-09-15 | P | P | P | Internal review of draft of revised LTHHCP provider manual
| 10/15/11 12/15/11 | P | P | P | Coordinate final draft of revised LTHHCP provider manual with CCM principles from MRT MLTC Work Group
| 2011-08-15 | 8 | 8 | 8 | Rates for new services available in eMedNY to allow claims processing
| 2011-08-15 | 8 | 8 | 8 | Implement new/expanded services
| 1/1/12 2/1/12 4/1/12 5/18/12 | P | P | P | issue Revised LTHHCP Reference manual
137 |  |  |  |  | Project Name: Disregard Retirement Assets Such as 401K Plans for MBI-WPD Division Lead: DCE Team Lead: Wendy Butz Description: Raise the resource standard and disregard retirement accounts for the MBI-WPD program as an incentive to participation in the program. | 0.5 | Completed
POLICY AND PROCEDURE
| 2011-04-30 | P | P | P | Complete review of policy issues
| 7/1/11 7/22/11 | P | P | P | Submit draft ADM for clearance
| 9/1/11 9/23/11 | P | P | P | Issue ADM
STATE PLAN
| 2011-05-13 | P | P | P | Submit draft SPA to DHCF for submission to CMS for informal review
SYSTEMS UPDATES
| 2011-04-01 | P | P | P | Submit System Change Request
| 2011-04-25 | P | P | P | Finalize system change requirements
| 2011-05-01 | P | P | P | Finalize System Action Request
MBL
| 2011-08-22 | P | P | P | Development/coding changes
| 2011-10-07 | P | P | P | Unit testing
| 2011-10-12 | P | P | P | User Acceptance
CEM/WMS
| 2011-08-22 | P | P | P | Development/coding changes
| 2011-10-07 | P | P | P | Unit testing
| 2011-10-12 | P | P | P | User Acceptance
CNS
| 2011-04-11 | P | P | P | Finalize and submit CNS notices
| 2011-08-22 | P | P | P | Development/coding changes
| 2011-10-07 | P | P | P | Unit testing
| 2011-10-12 | P | P | P | User Acceptance
| 2011-10-17 | P | P | P | Migrate system changes (October 17 2011 .. 11.3 migration) First run is 1st weekend in January for cases expiring 3/31/12
WEBSITE
| 2011-08-01 | P | P | P | Submit revisions for MBI-WPD website, including Toolkit, for DOH clearance
| 2011-09-30 | P | P | P | Post revisions to MBI-WPD website
| 2011-10-22 | P | P | P | Implementation
141 |  |  |  |  | Project Name: Accelerate State Assumption of Medicaid Program Division Lead: DMC Team Lead: Jennifer Dean Additional Staff: Linda Gowdy Description: Accelerate State Assumption of Medicaid program authorization for Managed Long Term Care; State takeover of Medicaid managed care contracting process statewide | 0 | Completed
Part A: Take over Medicaid Managed Care Contracts from NYC
| 2011-03-01 | P | P | P | Review NYC Specific sections of the MMC contract for input into statewide contract
| 2011-03-15 | P | P | P | Meet with NYC and plan associations to discuss changes proposed
| 2011-04-01 | P | P | P | Review NYC Specific sections of the SNP contract for input into statewide contract
| 2011-04-15 | P | P | P | Draft dual eligible Medicaid managed care contract language for Medicaid Advantage Plans NYC service areas included with the effective date of 1/1/11.
| 2011-04-20 | P | P | P | Dual eligible Medicaid Managed care contract language for Medicaid Advantage to CMS for approval
| 2011-06-01 | 8 | 8 | 8 | SNP state contract approved by CMS. SNP state contract sent to OSC for approval.
| 2011-06-01 | P | P | P | Dual eligible Medicaid Managed care contract language for Medicaid Advantage approved by CMS - sent to plans
| 2011-06-10 | 8 | 8 | 8 | New state SNP contracts for SNP only to CMS for approval
| 2011-06-15 | P | P | P | Dual eligible Medicaid Managed care contract language for Medicaid Advantage approved by CMS - returned by plans
| 5/25/11 6/30/11 | P | P | P | Draft SNP managed care state contract changes for consolidation into 7/1/11 8-1-11 combined MMC/FHP/SNP state contract for plans that are MMC and SNP
| 5/10/11 5/30/11 6/6/11 7/1/11 | P | P | P | MMC statewide contract amendment including service area language effective 8-1-2011 drafted
| 5/10/11 5/30/11 6/10/11 6/30/11 7/15/11 | P | P | P | Draft mainstream managed care contract termination for MCOs with NYC contracts effective 6/30/11 7-31-11
| 6/15/11 7/20/11 7/30/11 8/30/11 10/14/11 10/31/11 11/30/11 12/18/11 12/16/11 | P | P | P | CMS approval of MMC/NYC contract terminations and MMC amendments
| 6/30/11 8/10/11 9/10/11 12/16/11 1/5/12 | P | P | P | MMC/NYC contract terminations and MMC contract amendment approved by CMS and OSC.
144 |  |  |  |  | Project Name: Eliminate Duplicative Behavioral Health Hosp Surveys Division Lead: OHSM - with OMH and OASAS Team Lead: Mike Holley (OMH) Additional Staff: Chuck Monson (OASAS), Ruth Leslie (DOH) Description: The granting of "deemed status" in lieu of state licensing surveys to hospitals accredited by The Joint Commission or other nationally accrediting body assessing NYS specific concerns. | 0 | Completed
| 2011-03-31 | P | P | P | Discussions among DOH, OASAS and OMH to fully appreciate the nature of the different deemed status agreements/plans with The Joint Commission (TJC).
| 2011-03-31 | P | P | P | Continue discussions with TJC regarding readiness to begin deemed OMH surveys including the potential role of OMH in training behavioral health surveyors in the OMH addendum.
| 2011-03-31 | P | P | P | Review with TJC the scope of psychiatric inpatient services in NYS. Prepare list with # units per hospital, # of beds and population type of units to inform decision on additional surveyor day(s) to conduct the behavioral health addendum.
| 2011-03-31 | P | P | P | Commence conversations with TJC regarding the use of a deemed status arrangement to satisfy OASAS certification requirements for hospital-based medically managed withdrawal (1st priority) and inpatient rehabilitation (2nd priority).
| 2011-03-31 | P | P | P | Initiate discussions with Det Norske Veritas (DNV) and American Osteopathic Association’s Healthcare Facilities Accreditation Program (AOA) regarding the use of a deemed status arrangement to satisfy OMH and OASAS licensing requirements.
| 2011-04-30 | P | P | P | After careful review of the DOH Collaborative Agreement, develop a Collaborative Agreement between NYS OMH and TJC which describes the responsibilities of each party.
| 2011-04-30 | P | P | P | Identify required regulatory changes to implement deemed status arrangement.
| 2011-04-30 | P | P | P | Develop regulatory language (text of rule) to amend applicable Parts in Title 14 NYCRR.
| 2011-04-30 | P | P | P | Review and if necessary revise the surveyor addendum to ensure it reflects the most recent TJC standards and OMH NYS rules and regulations.
| 2011-04-30 | P | P | P | Conduct a comparison of standards utilized by AOA against the OMH licensing tool.
| 2011-05-31 | P | P | P | Update hospital associations re readiness to begin deemed surveys. Identify additional issues, barriers, and solutions.
| 2011-05-31 | P | P | P | Develop an addendum to AOA survey, if needed, to include high risk and/or New York State OMH specific items.
| 2011-05-31 | P | P | P | Conduct a comparison of standards utilized by DNV against the OMH licensing tool.
| 2011-06-30 | P | P | P | Compare TJC Survey Standards against OASAS Program Regulations -- medically managed withdrawal and inpatient rehabilitation.
| 2011-06-30 | P | P | P | Develop and sign collaborative agreement/memorandum of understanding between the Joint Commission and NYS Office of Mental Health.
| 2011-06-30 | 8 | 8 | 8 | Determine if rule change should be filed as a Notice of Proposed Rulemaking or Emergency Rulemaking.
| 2011-06-30 | 8 | 8 | 8 | Secure Governor’s Office approval to file an emergency rule (per Executive Order 17), if applicable.
| 2011-06-30 | P | P | P | Prepare accompanying regulatory paperwork.
| 2011-06-30 | P | P | P | Circulate rule with completed regulatory filing paperwork internally for approval.
| 2011-06-30 | P | P | P | Submit Notice of Proposed Rulemaking to Governor’s Office for approval.
| 2011-06-30 | P | P | P | Determine which OMH providers will be eligible to apply to TJC for deemed status. Share information with TJC.
| 2011-06-30 | P | P | P | Work with TJC to develop interim procedure for hospitals to opt-in or opt-out of deemed status survey process, including consent to share report with OMH. Develop process for OMH to be notified of hospital decision.
| 2011-06-30 | P | P | P | Develop an addendum to DNV survey, if needed, to include high risk and/or New York State OMH specific items.
| 2011-07-31 | P | P | P | Distribute Dear Provider letter to inform hospitals of OMH deemed status procedures.
| 2011-07-31 | P | P | P | Continue to conduct surveys and issue licenses to non-accredited hospitals and those opting out of deemed survey.
| 2011-08-31 | P | P | P | Upon receipt of successful TJC reports, issue 3 year OMH licenses.
| 2011-08-31 | P | P | P | Meet with Standards Compliance and Field staff to identify quality of care and safety issues and the areas where OASAS has specific regulations not covered by TJC. Develop potential list of areas to be included in an addendum to TJC Survey Standards.
| 2011-08-31 | P | P | P | Submit proposed rule to Department of State for publication in the NYS Register.
| 2011-08-31 | P | P | P | Develop parameters and protocols for rapidly deploying OMH staff to conduct on site for cause surveys.
| 7/31/11 9/16/11 | P | P | P | Brief Mental Health Services Council on the proposed rule and conduct vote.
| 7/31/11 9/30/11 | P | P | P | Coordinate with DOH to achieve OMH participation in validation surveys in hospitals with licensed psychiatric units; Develop protocol to validate survey of NYS/OMH addendum.
| 2011-09-30 | P | P | P | Meet with hospital associations' membership to review opportunities, options, procedures and protocols for deemed surveys.
| 2011-10-31 | P | P | P | Assess Public Comment if received, and prepare assessment paperwork. Submit 101-A letters to appropriate legislative leaders.
| 2011-10-31 | P | P | P | Update OMH website to inform public of deemed status arrangement.
| 2011-10-31 | P | P | P | Add accrediting body information to OMH Provider Directory for hospitals.
| 9/30/11 11/16/11 | P | P | P | Discussions between OASAS and TJC leadership to develop a list of New York State specific concerns to be included in a TJC chemical dependence addendum.
| 2012-01-31 | P | P | P | Work with DNV and with the hospital associations to conduct pilot surveys.
| 2012-01-31 | P | P | P | Identify providers eligible to participate in a deemed status agreement with DNV and develop a schedule of certification due dates.
| 2012-02-28 | P | P | P | Review results of DNV pilot surveys, modify protocols as needed.
| 12/31/11 2/29/12 | P | P | P | Work with AOA and with the hospital associations to conduct pilot surveys.
| 1/31/12 3/8/12 | P | P | P | Review results of AOA pilot surveys, modify protocols as needed.
| 1/31/12 3/8/12 4/5/12 | P | P | P | Identify providers eligible to participate in a deemed status agreement with AOA and develop a schedule of certification due dates.
| 10/31/11 12/31/11 3/15/12 3/31/12 5/15/12 | P | P | P | Discussions between OASAS and TJC leadership to agree on steps and timetable for implementation.
| 2012-03-31 | P | P | P | Adoption of enabling regulations
| 2012-03-31 | P | P | P | Identify providers eligible to participate in a deemed status agreement with DNV and develop a schedule of certification due dates.
| 2012-05-17 | P | P | P | Present TJC Deeming Process to Hospital Associations
| 2012-06-30 | P | P | P | Notify Field of TJC Deeming Opportunity for OASAS Certified Hospital-Based Inpatient Rehabilitation and Detoxification Programs
| 3/31/12 5/1/12 7/1/12 | 8 | 8 | 8 | Work with DNV to develop procedure for hospitals to opt-in or opt-out of deemed status survey process, including consent to share report with OMH. Develop process for OMH to be notified of hospital decision.
| 1/31/12 4/5/12 7/1/12 | 8 | 8 | 8 | Work with AOA to develop procedure for hospitals to opt-in or opt-out of deemed status survey process, including consent to share report with OMH. Develop process for OMH to be notified of hospital decision.
| 2012-09-01 | P | P | P | OASAS to Implement TJC Deeming for Eligible Hospitals on a phased-in basis
| 3/31/12 12/31/12 | P | P | P | Complete steps necessary to implement deeming of OMH inspections of hospital inpatient units with DNV and with HFAP by 12-31-12.
147 |  |  |  |  | Project Name: Eliminate or Modify Unnecessary Regulations Division Lead: OHSM Team Lead: Karen Lipson/Charlie Abel Description: There are a number of suggested initiatives that require both statutory and regulatory actions to reduce burdens on hospitals and other health care facilities and expand access to capital. | 0 | Completed
IMPLEMENT A POLICY TO ALLOW APPROVED NURSE AIDE TRAINING PROGRAM SPONSORS TO PROVIDE TRAINING AT NURSING HOME SITES WHICH CURRENTLY DO NOT SPONSOR THEIR OWN TRAINING
| 2011-03-25 | P | P | P | 1. Clarify scope of required changes
| 2011-04-08 | P | P | P | 2. Ascertain whether there are federal/state statutory/regulatory barriers to the changes
| 2011-04-29 | P | P | P | 3. Assuming no federal/state statutory/regulatory barriers, post advisory announcing the changes on HCS:
| 2011-04-29 | P | P | P | 3.1 Develop application and application process. Train staff.
| 2011-04-29 | P | P | P | 3.2 Draft advisory (includes application)
| 2011-05-13 | P | P | P | 3.3 Circulate for internal approval; modify as required; re-circulate for internal approval
| 2011-05-27 | P | P | P | 3.4 Circulate for stakeholder approval; modify as required; recirculate for MRT approval
| 2011-06-03 | P | P | P | 3.5 Post on HCS
| 2011-06-03 | P | P | P | 3.6 Distribute to non-DOH stakeholders.
DEVELOP A UNIFORM INCIDENT REPORTING SYSTEM FOR NURSING HOMES
| 2011-03-01 | P | P | P | Create Project Proposal and Business Design Document
| 2011-04-01 | P | P | P | Present Proposal to Internal Stakeholders
| 2011-05-02 | P | P | P | Develop Prototype of Incident Form
| 7/1/11 9/1/11 | P | P | P | Design and Test Electronic Form via the Health Commerce System (HCS), and Receive Form Approval
| 7/1/11 9/15/11 9/23/11 10/4/11 | P | P | P | Develop, Receive Executive Clearance and Approvals, Send Dear Administrator Letter (DAL) to Nursing Home Administrators
| 8/31/11 9/23/11 10/4/11 | P | P | P | Post DAL; Reporting Manual; Online Form Tutorial; and PPT on DOH website and HCS.
| 9/30/11 10/4/11 | P | P | P | Develop Database to receive form data, and software interface to easily view incident. Create features to copy and paste incident data into Federal Software System (ACTS).
| 8/1/11 10/1/11 10/5/11 | P | P | P | Develop Policies and Procedures to Receive Electronic Incident Form and Train Staff
| 8/15/11 10/15/11 | P | P | P | Implement Electronic Incident Form for Nursing Homes
AUTHORIZE OBSERVATION UNITS AS ADJUNCT TO EMERGENCY DEPARTMENTS AND CREATE MEDICAID RATE
| 2011-04-01 | P | P | P | Finalize development of Medicaid rate for observation units
| 2011-04-20 | P | P | P | Present regulations to DOH Regulatory Advisory Committee
| 2011-04-30 | P | P | P | Circulate regulations to Stakeholders for comment
| 2011-05-04 | P | P | P | Finalize draft Observation Unit operating regulations
| 2011-05-31 | P | P | P | Publish Medicaid Update article on observation unit rate for waiver units
| 2011-05-31 | P | P | P | Launch Medicaid rate for existing observation units
| 2011-07-21 | P | P | P | Present proposed regulations to PHHPC Committee for discussion
| 2011-08-04 | P | P | P | Present proposed regulations to PHHPC for discussion
| 5/31/11 6/30/11 7/15/11 8/15/11 9/15/11 | P | P | P | Secure Governor's Counsel's approval of draft regs
| 6/30/11 8/24/11 10/5/11 9/28/11 | P | P | P | Publish proposed regulations in State Register
| 10/15/11 11/19/11 11/14/11 | P | P | P | 45-day comment period
| 2011-12-08 | P | P | P | Present regulations to PHHPC Codes Committee for recommendation (11/17/11) and to full Council for adoption.
| 2011-12-28 | P | P | P | Publish Notice of Adoption in State Regiser
| 12/31/11 1/30/12 | P | P | P | Train regional office staff
| 12/31/11 2/14/12 | P | P | P | Disseminate information via HPN to hospitals regarding new operating standards for observation units and availability of Medicaid reimbursement.
| 12/28/11 2/20/12 | P | P | P | Publish Medicaid Update article regarding availability of rate for new operating standards for new observation units
ALLOW HOME HEALTH AIDE TRAINING PROGRAMS TO HAVE A SINGLE QUALIFIED SUPERVISOR RN FOR MULTIPLE TRAINING PROGRAMS
| 2011-04-10 | P | P | P | Draft policy guidance in the Home Health Aide Guidelines for Home Health Training Programs
| 6/1/11 6/15/11 7/1/11 8/15/11 | P | P | P | Draft Dear Administrator Letters (DALs) informing home health aide training programs of the revised guidance on RN supervision
| 6/1/11 6/15/11 7/1/11 8/15/11 | P | P | P | Draft modifications to surveillance and monitoring tools
| 6/15/11 7/15/11 8/15/11 9/1/11 | P | P | P | Seek feedback from stakeholders and interested parties re: content and clarity of draft documents including State Education Department
| 6/15/11 7/15/11 8/15/11 9/1/11 | P | P | P | Revise surveillance training to surveyors and disseminate revised materials to regional offices
| 10/15/11 1/3/12 | P | P | P | Develop home care worker registry technical specifications with the Bureau of CSD that conform to the changes made to the home health aide training program guidelines
| 6/15/11 7/15/11 8/15/11 9/1/11 9/30/11 12/1/11 2/1/12 | P | P | P | Post DAL's to the HPN to home care agencies and training programs
| 7/15/11 8/15/11 10/15/11 1/15/12 2/28/12 3/31/12 | P | P | P | Work with stakeholder organizations to develop FAQ document(s) to respond to questions, if needed.
| 3/15/12 4/15/12 6/1/12 9/1/12 10/1/12 | P | P | P | Develop provider training for impending registry changes
| 5/1/12 6/15/12 10/1/12 12/1/12 | P | P | P | Conduct provider training as necessary regarding changes to be made to registry through webinar and other means
| 6/1/12 7/1/12 10/15/12 12/1/12 | P | P | P | Implement changes to registry that conform to the changes made to the home health aide training program guideline changes
ELMINATE THE REQUIREMENT FOR A PHYSICIAN TO BE ON THE QUALITY IMPROVEMENT(QI) COMMITTEE OF LICENSED HOME CARE SERVICES AGENCIES (LHCSAs)
| 2011-04-15 | P | P | P | Draft revised licensed home care regulation 766.9 (k)(1)
| 5/1/11 6/10/11 | P | P | P | Prepare notice to state register for publication of regulations
| 8/1/11 9/30/11 | P | P | P | Develop and draft revised surveillance protocols and inform surveyors of new protocols
| 8/4/11 10/6/11 12/8/11 2/2/12 | P | P | P | Present to PHHPC for discussion
| 5/30/11 6/30/11 8/15/11 9/15/11 10/15/11 3/2/12 5/8/12 7/31/12 10/15/12 10/9/12 | P | P | P | Secure Governor's Counsel's Office approval of revised regulations.
| 8/15/11 10/6/11 12/15/11 3/16/12 5/22/12 8/15/12 10/30/12 10/9/12 | P | P | P | Revise regulations, if necessary
| 8/31/11 10/12/11 12/21/11 4/4/12 6/13/12 8/13/12 11/14/12 10/24/12 | P | P | P | Publish proposed regulations in State Register
| 10/15/11 11/28/11 2/4/12 5/19/12 7/28/12 9/30/12 12/29/12 12/10/12 | P | P | P | 45-day comment period
| 12/8/11 3/30/12 5/24/12 9/20/12 11/15/12 1/24/13 | P | P | P | Present regulations to PHHPC Codes Committee for recommendation
| 6/7/12 10/11/12 12/06/12 1/31/13 2/7/13 | P | P | P | Present regulations to full Council for adoption
| 12/28/11 4/15/12 6/27/12 10/31/12 12/15/12 2/15/13 3/20/13 4/24/13 5/15/13 | P | P | P | Publish Notice of Adoption in State Register
| 12/28/11 4/15/12 6/27/12 10/31/12 01/02/13 2/28/13 3/25/13 4/29/13 5/20/13 | P | P | P | Draft DAL informing LHCSA of revised requirement and effective date
| 1/15/12 4/30/12 7/14/12 11/15/12 1/15/13 3/15/13 3/29/13 5/6/13 6/3/13 6/3/13 | P | P | P | Post DAL's to the HCS informing providers of the revised regulation policy and procedure
NYPORTS REFORM IMPLEMENTATION
| 2011-03-10 | P | P | P | Establish workgroup
| 2011-03-10 | P | P | P | Set meeting calendar dates
| 2011-03-18 | P | P | P | Review NQF reporting structures
| 2011-03-18 | P | P | P | Develop cross-walk to current NYPORTS
| 2011-03-18 | P | P | P | Assign draft codes to those NQF unique fileds
| 2011-04-22 | P | P | P | Meet with executive staff to discuss implementation plan
| 2011-04-30 | P | P | P | Convene stakeholders
| 2011-05-30 | P | P | P | Draft revised regulations
| 2011-05-30 | P | P | P | Revise reporting manual
| 2011-05-30 | P | P | P | Plan educaton and training schedule
| 2011-05-30 | P | P | P | Development of training materials
| 2011-06-30 | P | P | P | Development of policy/ procedures
| 2011-06-30 | P | P | P | Conduct trainings for DOH staff and regulated providers
| 2011-06-30 | P | P | P | Finalize regulations
| 2011-07-05 | P | P | P | Modified reporting approach implemented
| 6/30/11 7/15/11 | P | P | P | Circulate regulations to Stakeholders for comment
| 2011-07-21 | P | P | P | Present proposed regulations to PHHPC Committee for discussion
| 2011-08-04 | P | P | P | Present regulations at PHHPC
| 7/15/11 7/30/11 8/29/11 9/9/11 9/22/11 10/5/11 12/11/11 | P | P | P | Submit regulations to Governor's Office for Approval
| 8/15/11 9/15/11 10/5/11 1/11/12 2/11/12 | P | P | P | Revise regulations, if necessary
| 8/31/11 9/28/11 10/19/11 2/1/12 2/29/12 | P | P | P | Publish regulations in State Register
| 10/15/11 11/12/11 12/3/11 3/17/12 4/16/12 | P | P | P | 45-day comment period
| 10/10/12 12/5/12 2/13/13 3/20/13 | P | P | P | Publish revised regulation in response to public comment
| 11/9/12 1/4/13 3/15/13 4/22/13 | P | P | P | 30-day comment period
| 12/28/11 4/4/12 5/9/12 7/30/12 11/28/12 1/30/13 4/3/13 5/22/13 5/29/13 | P | P | P | Publish Notice of Adoption in State Regiser
| 1/30/12 4/15/12 5/23/12 7/30/12 11/28/12 1/30/13 4/3/13 5/31/13 6/21/13 7/11/13 | P | P | P | Disseminate information via HPN to hospitals regarding revised adverse event reporting regulations
FACILITATE ACCESS TO CAPITAL FINANCING THROUGH OBLIGATED GROUPS, INCLUDING MULTI-STATE OBLIGATED GROUPS
| 2011-04-01 | P | P | P | Identify DOH workgroup members needed
| 2011-04-08 | P | P | P | Convene internal DOH workgroup to discuss and begin developing initiative requirements
| 2011-05-30 | P | P | P | Begin drafting of needed policy guidance and regulation(s), as needed
| 7/21/11 | 8 | 8 | 8 | Introduction of potential policy change to the Public Health and Health Planning Council Establishment and Project Review Committee
| 2011-08-04 | P | P | P | Present policy change to PHHPC
| 2011-08-15 | 8 | 8 | 8 | Revise policy guidance and regulations in response to PHHPC discussion.
| 2011-08-15 | 8 | 8 | 8 | Submit draft policy document and possible regulatory language for executive review
| 9/13/11 9/20/11 10/31/11 11/30/11 1/31/12 2/29/12 3/31/12 5/30/12 | P | P | P | Executive sign-off of draft policy/regulation
| 2011-09-28 | 8 | 8 | 8 | Publish proposed regulation, if needed, in the State Register for 45 day public notice
| 2011-11-17 | 8 | 8 | 8 | Public Health and Health Planning Council Codes Committee review of proposed regulation for adoption
| 2011-12-08 | 8 | 8 | 8 | Update the Public Health and Health Planning Council on revised policy
| 2011-12-28 | 8 | 8 | 8 | Publish Notice of Adoption in State Register
| 1/15/13 3/31/13 4/30/13 11/30/13 1/31/14 6/30/14 12/31/14 6/30/15 | P | P | P | Assess the draft policy for impact of CON reform initiatives.
| 1/15/13 3/31/13 4/30/13 11/30/13 1/31/14 6/30/14 12/31/14 6/30/15 | P | P | P | Brief PHHPC and Implement policy change and needed regulation changes
150 |  |  |  |  | Project Name: Develop an Automated Exchange/Medicaid Eligibility System Division Lead: Systems/DCE Team Lead: Judy Arnold Description: Execute Contract to Begin Development | 0 | Completed
| 2011-04-01 | P | P | P | Statute enacted to permit mini-procurement for Early Innovator
| 5/15/11 7/15/11 | P | P | P | Post Requirements on Web
| 4/30/11 9/30/11 10/7/11 | P | P | P | Submit APD to CMS for Medicaid funding
| 10/1/11 12/1/11 1/1/12 2/15/12 3/15/12 4/1/12 | P | P | P | Submit Contract to OSC
| 10/30/11 2/1/12 4/15/12 6/1/12 | P | P | P | Execute Contract
153 |  |  |  |  | Project Name: Develop Innovative Telemedicine Applications by Reducing Regulatory Barriers and Providing Payment Incentives Division Lead: DFPP Team Lead: Joan Sicard Add'l Staff: Ronald Bass Description: Promote and enhance coverage of telemedicine by providing payment incentives and reducing coverage barriers | -0.23 | Completed
| 2011-05-09 | P | P | P | Research Medicare's telemedicine policy including, but not limited to, credentialing arrangements, professional accountability/malpractice implications and coverage guidelines
| 2011-05-01 | P | P | P | Research other State Medicaid programs' policy and coverage guidelines for telemedicine (including credentialing arrangements, etc.)
| 2011-06-15 | P | P | P | Meet with key stakeholders and organizations to gather information and identify advantages and barriers to implementation of telemedicine, telehealth, teleradiology and telepsych.
| 2011-06-15 | P | P | P | Determine, with staff from the Office of Technology and Dept of Legal Affairs, security issues related to health information exchange, patient confidentiality, etc.
| 2011-06-15 | P | P | P | Meet with OMH to explore telepsych coverage.
| 2011-06-30 | P | P | P | Explore allowing certified diabetes and asthma educators (CDEs and CAEs) to provide telemedicine services
| 2011-07-15 | P | P | P | Explore telemedicine models currently in operation (Univeristy of Rochester Health e Access Telemedicine Network model; Fingerlakes Migrant Health Telemedicine Model, etc.) Set up conference calls with key staff.
| 2011-07-30 | P | P | P | Move ahead with expanding telemedicine coverage to D&TCs
| 7/15/11 7/30/11 | P | P | P | Establish payment criteria and develop reimbursement amounts
| 8/15/11 8/30/11 | P | P | P | Develop payment protocol and reimbursment methodology
| 7/15/11 7/30/11 8/15/11 8/30/11 9/15/11 9/22/11 | P | P | P | Facilitate coverage with Medicaid Managed Care plans
| 2011-07-30 | 8 | 8 | 8 | Initiate regulatory process (concept paper, complete regulatory package, DLA review, publish proposed rule in the State Register, public comment period, respond to public comments, finalize regulation)
| 9/1/11 9/15/11 9/22/11 | P | P | P | Prepare a Medicaid Update article outlining telemedicine policy, coverage and billing guidelines
| 9/15/11 9/22/11 9/30/11 | P | P | P | Update provider manuals and guidance documents
| 2011-09-30 | 8 | 8 | 8 | Regulation filed as final
| 2011-09-30 | P | P | P | Educate Helpline and CSC staff to ensure that accurate policy information is communicated when responding to telemedicine inquiries
| 2011-10-01 | P | P | P | Implement policy
154 |  |  |  |  | Project Name: Enhance and Improve the State's Medicaid Program Integrity Efforts. Division Lead: OMIG Portfolio Manager: Katherine Napoli/Alicia Whitlingum | -148 | Completed
154-3 |  |  |  |  | Pharmacy Signature- Require Identification and Signature for Home Delivery and for Receipt of Prescriptions at Pharmacies Project Lead: Sharon Conway Description: Require government issue ID and signature in order to receive prescriptions/fiscal orders at pharmacy and for home delivery. Maintain ID and signature log records for a period of 6 years | 0 | Completed
| 2011-04-21 | P | P | P | Reach out to DOH OHIP for history of signature and opinion on proposal
| 2011-04-22 | P | P | P | Meet with OMIG legal staff to explain/discuss proposal
| 4/29/11 5/13/11 | P | P | P | OHIP legal staff to consult with DOH OHIP counsel Jane McCloskey
| 2011-05-20 | P | P | P | OHIP Policy / Legal Schedule meeting w. Stakeholders to determine validality
DERIVE METHODOLOGY FOR THE SAVINGS
| 4/15/11 4/22/11 | P | P | P | Develop methodology
| 2011-04-22 17:00 | P | P | P | Complete Budget Savings Form
| 5/6/11 4/26/11 | P | P | P | Approval by BBFM
| 5/27/11 4/28/11 | P | P | P | Update MRS in FACTS
| 2011-05-20 | P | P | P | Internal Controls for initial review (audit of methodology)
EMERGENCY REGULATORY CHANGE
| 2011-06-10 | 8 | 8 | 8 | Conduct emergency rule adoption process
| 2011-07-29 | 8 | 8 | 8 | Emergency Rule Adopted
FORMALLY ADOPT REGULATION
| 2011-05-20 | P | P | P | Draft Programmatic Regulatory Language 18NYCRR505.3
| 2011-05-20 | P | P | P | Draft concept paper and prepare package to Legal
| 2011-06-03 | 8 | 8 | 8 | Legal Review
| 2011-07-22 17:00 | 8 | 8 | 8 | GO review and approval
| 2011-07-22 17:00 | 8 | 8 | 8 | Outreach meetings
| 2011-08-05 17:00 | 8 | 8 | 8 | Submit Proposal to DOS
| 2011-10-07 17:00 | 8 | 8 | 8 | Comment period
| 2011-10-14 17:00 | 8 | 8 | 8 | Draft public commentary assessment
| 2011-10-28 17:00 | 8 | 8 | 8 | Adoption of regulatory change (assume no provisions are needed)
| 2011-11-01 17:00 | 8 | 8 | 8 | Publish to Register
| 2011-11-02 17:00 | 8 | 8 | 8 | Regulation approved
NOTIFY PROVIDERS
| 2011-07-15 | P | P | P | Prepare Medicaid Update Article pertaining to signature requirement. Article sent to OHIP for approval
| 2011-08-20 | P | P | P | OHIP draft Update Article approved
| 9/1/11 10/31/11 | P | P | P | Update article published • Publish Medicaid Update Article - September or October Issue 10/1/11 e-Blast went out 9/1/11
| 2011-12-31 | P | P | P | Develop Audit Finding and Protocol
| 2012-01-01 | P | P | P | Consult with OHIP Pharmacy Policy and County Demo on protocol development
| 2012-04-01 | 8 | 8 | 8 | Implement Protocol
REVISE AUDIT PROTOCOLS & FINDINGS
| 2011-09-01 | 8 | 8 | 8 | Publish update article
| 2011-10-01 | 8 | 8 | 8 | Implement policy
| 2011-07-22 | 8 | 8 | 8 | Consult w. County demo
| 2012-01-25 | 8 | 8 | 8 | Implement protocol for audit periods consistent with effective date of regulation
NOTIFY PROVIDERS
| 2011-07-27 | 8 | 8 | 8 | Develop and distribute notification letter to all enrolled pharmacies
| 2011-09-07 | 8 | 8 | 8 | Develop and publish Medicaid Update article
| 2011-12-14 | 8 | 8 | 8 | Notification to PSSNY
PREPARING PROVIDER FOR THE CHANGE
| 5/20/11 4/22/11 | P | P | P | Explore the idea of using CardSwipe as method for obtaining signatures (if so, this should be part of the reg)
| 2011-12-14 | 8 | 8 | 8 | Provide template signature log
| 2011-12-14 | 8 | 8 | 8 | Provide template notice for signage within the pharmacy
| 2012-03-07 | 8 | 8 | 8 | Implement change with Pharmacies
MEASURE SAVINGS $0.6 M
| 2012-03-08 | 8 | 8 | 8 | Update MRS monthly in FACTS (cost avoidance)
| 2012-03-08 | 8 | 8 | 8 | Submit to BBFM
| 2012-07-12 | 8 | 8 | 8 | Measure cash savings (Audit findings)
154-5 |  |  |  |  | Access DOH BNE - Allow Access to the Department of Health (DOH) Bureau of Narcotics Enforcement (BNE), New York State Prescription Information Database Project Lead: Angelo Ruperto Project Description: Allow the OMIG access to DOH BNE data, which provides information on the cash purchase of controlled substances, to improve OMIG’s RRP targeting capabilities. Currently RRP targeting is limited to Medicaid payment data only. |  | Completed
DERIVE METHODOLOGY FOR THE SAVINGS
| 6/17/11 4/28/11 | P | P | P | Update MRS in FACTS
| 5/20/11 5/13/11 4/29/11 | P | P | P | Complete Budget Savings Form
| 5/27/11 | P | P | P | Approval by BBFM
| 2011-06-04 | P | P | P | Internal Controls for initial review (audit of methodology)
| 2011-08-30 | P | P | P | Discuss alternative option related to Article VII
| 2011-09-30 | P | P | P | Continue stakeholder discussions
| 2011-10-31 | P | P | P | Reach decision - Access Granted
| 12/23/11 2/29/12 | P | P | P | Work with DOH to pursue legislative changes to allow for full access to this data
FORMALLY ADOPT LEGISLATION
| 12/22/11 6/30/11 | 8 | 8 | 8 | Enact Legislation DOH Departmental #45 05-11
FORMALLY ADOPT REGULATION
| 6/17/11 | 8 | 8 | 8 | OMIG Staff/DOH Discussions ongoing
SYSTEM ACCESS
| 12/23/11 9/9/11 | 8 | 8 | 8 | Obtain access to DOH BNE system data
| 1/3/12 10/17/11 | 8 | 8 | 8 | Determine rrp candidate restrictions
| 2/3/12 10/17/11 | 8 | 8 | 8 | SMRT Review required
| 3/2/12 10/17/11 | 8 | 8 | 8 | Determine referral to law enforcement
MEASURE SAVINGS 0.1M
| 4/2/12 11/18/11 | 8 | 8 | 8 | Update MRS monthly in FACTS (cost avoidance)
| 4/2/12 11/18/11 | 8 | 8 | 8 | Submit to BBFM
154-8 |  |  |  |  | Project Name: Duplicate Claims- Medicare Coordination of Benefits with Provider Submitted Duplicate Claims Project Lead: Julie DeRubertis, Cathy McCulskey Project Description: Review claims approved and paid by Medicare for dual eligible recipients, which are also submitted to Medicaid for payment, and refine existing edit logic (#02112) to prevent such duplication. Existing edit logic is not always adequate to identify such duplication, which results in the payment of same claims by both Medicare and Medicaid. Potential duplicate claims will be reviewed and recoveries made when appropriate. Finding/recovery validation will help further refine the current edit logic criteria to appropriately reflect Medicare participation prior to authorizing Medicaid payments. | -30 | Completed
EDIT CHANGE 02113
| 2011-04-15 17:00 | P | P | P | Edit Calculation 02113
DERIVE METHODOLOGY FOR THE SAVINGS
| 2011-04-01 17:00 | P | P | P | Develop methodology
| 4/20/11 4/29/11 | P | P | P | Complete Budget Savings Form
| 5/6/11 5/3/11 | P | P | P | Approval by BBFM
| 2011-05-16 17:00 | P | P | P | Internal Controls for initial review (audit of methodology)
| 2011-05-17 | P | P | P | Update MRS in FACTS
CHANGE TO PAYMENT PROCESS FOR ALL CROSSOVER CLAIMS
IMPLEMENT EDIT
| 2011-04-11 17:00 | P | P | P | Request Edit Logic Change
| 4/25/11 4/20/11 | P | P | P | Obtain DOH Policy approval of Evolution Request
| 5/20/11 5/30/11 | P | P | P | Prioritize as e-MedNY Evolution
| 2011-07-22 17:00 | P | P | P | Functional Requirements Document Developed
| 5/30/11 8/22/11 | 8 | 8 | 8 | Technical evaluation of system
| 6/1/11 9/1/11 | 8 | 8 | 8 | Obtain project implementation date
| 2011-06-01 17:00 | 8 | 8 | 8 | Schedule of Edit Runs by OHIP and Systems
| 6/6/11 10/20/11 | 8 | 8 | 8 | Construction/Testing
| 8/2/11 11/15/11 | P | P | P | Project Implementation
| 2011-11-01 17:00 | 8 | 8 | 8 | New Data warehouse Training
| 2011-10-03 17:00 | 8 | 8 | 8 | User Acceptance Testing
| 10/31/11 11/30/11 1/26/12 2/23/12 | P | P | P | Rollout system changes to e-Med NY
DERIVE METHODOLOGY FOR THE SAVINGS
| 4/15/11 4/29/11 | P | P | P | Develop methodology
| 5/2/11 4/29/11 | P | P | P | Complete Budget Savings Form
| 5/16/11 5/3/11 | P | P | P | Approval by BBFM
| 2011-05-30 17:00 | P | P | P | Internal Controls for initial review (audit of methodology)
| 2011-05-17 | P | P | P | Update MRS in FACTS
OBTAIN RECOVERIES (CHECKS, VOIDS, AND WITHHOLDS)
| 2011-05-27 | P | P | P | Calculate Medicaid savings to support Edit and submit to BBFM
| 2011-05-27 | P | P | P | Share with Medicaid director (Jason Helgerson)
| 2011-06-07 | P | P | P | Run Recoveries against J. Flora files
| 2011-06-15 | P | P | P | Medicaid update article
| 2011-12-23 17:00 | P | P | P | Track recoveries
| 2011-12-23 17:00 | P | P | P | Conduct system match of Medicare crossover claims (4 way match)
| 2012-01-31 17:00 | P | P | P | Send out letters to providers
|  | P | P | P | Obtain staffing
SYSTEM MATCH
MEDICAID CROSSOVER
| 2011-10-03 17:00 | P | P | P | Send provider notice
| 2011-12-23 17:00 | P | P | P | Recover savings
| 2011-12-26 17:00 | P | P | P | Identify system matches (12/31/10)
| 2012-12-31 17:00 | P | P | P | Repeat as needed (until edits are implemented)
DERIVE METHODOLOGY FOR THE SAVINGS
| 4/1/11 4/29/11 | P | P | P | Develop methodology
| 5/2/11 4/29/11 | P | P | P | Complete Budget Savings Form
| 5/16/11 5/3/11 | P | P | P | Approval by BBFM
| 2011-05-31 17:00 | P | P | P | Internal Controls for initial review (audit of methodology)
| 2011-05-17 | P | P | P | Update MRS in FACTS
UPDATE ENROLLMENTS FOR OWNERSHIP CHANGES & MERGERS (ENTITY ID)
| 2011-06-15 | P | P | P | Medicaid update article submitted
| 6/30/11 7/30/11 | P | P | P | Meet with OHIP enrollment
| 12/31/11 6/60/12 | P | P | P | Coordinate and rectify NPI and Entity IDs
| 12/30/11 5PM 12/30/12 | P | P | P | Recovery of funds (VOIDS)
DERIVE METHODOLOGY FOR THE SAVINGS
| 4/1/11 4/29/11 | P | P | P | Develop methodology
| 5/2/11 4/29/11 | P | P | P | Complete Budget Savings Form
| 5/16/11 5/3/11 | P | P | P | Approval by BBFM
| 2011-05-31 17:00 | P | P | P | Internal Controls for initial review (audit of methodology)
| 2011-05-17 | P | P | P | Update MRS in FACTS
UPDATE ENROLLMENTS FOR OWNERSHIP CHANGES & MERGERS (ENTITY ID)
| 2011-06-15 | P | P | P | Medicaid update article submitted
| 6/30/11 7/30/11 | P | P | P | Meet with OHIP enrollment
| 2011-12-31 | P | P | P | Coordinate and rectify NPI and Entity IDs
| 2011-12-30 17:00 | P | P | P | Recovery of funds (VOIDS)
MEASURE SAVINGS
| 2011-12-30 17:00 | P | P | P | Track recoveries
| 2011-12-30 17:00 | P | P | P | Update MRS monthly in FACTS Savings (cost avoidance)
MRT # 164 |  |  |  |  | Project Name: Align Medicare Part B clinic coinsurance with Medicaid coverage and rates Division Lead: DFPP Team Lead: Ron Bass Description: Ensure that Medicare B coinsurance payment does not exceed Medicaid allowed amount | -8.55 | Completed
| 2011-03-31 | P | P | P | Draft Federal Public Notice
| 2011-03-31 | P | P | P | Draft revisions to State Plan
| 2011-04-15 | P | P | P | Determine policy changes
| 2011-04-15 | P | P | P | Initiate regulatory process (concept paper, complete regulatory package, DLA review, publish proposed rule in State Register, public comment period, respond to public comments, finalize regulation)
| 2011-04-15 | P | P | P | Initiate eMedNY system changes (develop Evolution Project Request to update/develop edit(s))
| 2011-04-22 | P | P | P | Submit State Plan Amendment
| 2011-05-18 | P | P | P | Regulatory Reform Committee meeting
| 8/15/11 9/1/11 9/15/11 | P | P | P | Provider notification via Medicaid Update
| 2011-09-15 | P | P | P | Train staff (including DOH staff, CSC staff, Helpline staff) to respond to provider and enrollee inquiries
| 2011-10-01 | P | P | P | Implementation of new policies and associated system changes. - physician
| 8/1/11 9/1/11 9/30/11 10/7/11 11/1/11 12/1/11 | P | P | P | Receive SPA approval
| 10/1/11 12/29/11 | P | P | P | Implementation of new policies and associated system changes - clinic
191 |  |  |  |  | Project Name: Decrease the Incidence and Improve Treatment of Pressure Ulcers Division Lead: OLTC Team Lead: Jackie Pappalardi Add'l Staff: Mary Ellen Hennessy,Ruth Leslie,Valerie Deetz, Jonaca Martin Description: This proposal provides financial support for the development of regional collaboratives to improve communications in care transitions across the healthcare continuum and for the development of measurement systems to show the reduction of pressure ulcers. | 0.35 | Completed
| 2010-06-01 | P | P | P | Convene Stakeholders across health care settings to develop a plan to reduce the incidence and improve the treatment of pressure ulcers.
| 2010-07-15 | P | P | P | Develop regional collaboratives for the reduction of pressure ulcers through improving communications and sharing evidenced based resources to build care transitions across health care settings.
| 2010-08-15 | P | P | P | Send a letter of introduction to the Gold Stamp:Reduction of Pressure Ulcer Initiative to providers across health care settings.
| 10/04/10-2/28/11 | P | P | P | Communicate plan to providers and industry stateholders through Webinars, informational brochures and regional conferences.
| 7/1/11 8/1/11 9/1/11 10/1/11 10/8/11 | P | P | P | Complete all aspects of the funding process.
| 9/1/11 10/15/11 11/1/11 | P | P | P | Engage regional health care leaders to commit staff time and resources to work together in regional collaboratives.
| 10/1/11 11/30/11 2/1/12 | P | P | P | Provide funding and technical support for the facilitation of new regional coalitions and the development of a tool to measure the reduction of pressure ulcers.
| 12/15/11 2/1/12 | P | P | P | Implement the Evaluation Plan to measure performance.
196 |  |  |  |  | Project Name: Supportive Housing Division Lead: OLTC Team Lead: Mark Kissinger Description: Create a supportive housing interagency work group with a goal of a proposal submitted to the MRT by October 1, 2011. The goal of the workgroup is to create between 5000 and 10,000 housing opportunities for persons at risk of nursing home or other institutional placements. This will be a $75M increase starting with SFY 12-13. | 0 | Completed
| 5/8/11 9/10/11 | P | P | P | Conduct research on prior state efforts at supportive housing.
| 6/1/11 7/1/11 8/1/11 8/22/11 9/22/11 | P | P | P | Establish the MRT Affordable Housing work group.
| 7/1/11 8/1/11 8/30/11 9/15/11 10/24/11 | P | P | P | First meeting of the workgroup.
| 9/11/11 10/01/11 10/12/11 | P | P | P | Meeting internally and with external stakeholders on options.
| 2012-12-31 | P | P | P | Affordable Housing Work Group Recommendations finalized, approved by MRT, and will be implemented in Phase 2 MRT Process.
| 9/1/11 11/1/11 12/1/11 12/8/11 1/17/12 | P | P | P | Finalize the 2012-13 Budget Proposal
| 12/1/11 1/17/12 | P | P | P | Meet with Executive Chamber and the Division of Budget on the proposal.
200 |  |  |  |  | Project Name: Change in scope of practice for mid-level providers to promote efficiency and lower Medicaid costs Division Lead: OLTC Team Lead: Mary Hart (parts B and C) Add'l Staff: Karen Westervelt, Barry Gray, Caleb Wistar Description: Expand the scope of practice for RNs, LPNs, and home health aides to improve access to services and decrease associated costs in delivering services | 0 | Completed
WORKFORCE FLEXIBILITY/CHANGE OF SCOPE OF PRACTICE WORK GROUP
| 6/1/11 7/1/11 8/15/11 9/15/11 | P | P | P | Set schedule and outcomes for workgroup
| 6/15/11 7/15/11 8/30/11 10/3/11 | P | P | P | Convene first workgroup meeting
| 2011-10-27 | P | P | P | Convene second workgroup meeting
| 2011-11-07 | P | P | P | Convene third workgroup meeting
| 10/1/11 11/15/11 | P | P | P | Final work group recommendations submitted to MRT
| 2011-12-13 | P | P | P | Work group recommendations presented to MRT and voted on
PART A - PERMIT NURSES/PATIENT S(UNDER THEIR SCOPE OF PRACTICE EXEMPTION) TO ORIENT/DIRECT HHAS AND PC WOKERS TO PROVIDE NURSING CARE AS IS CURRENTLY ALLOWED IN THE CONSUMER DIRECTED PERSONAL ASSISTANT PROGRAM
| 2011-04-15 | P | P | P | Convene internal meetings to determine next steps for revising scope of practice
| 2011-05-15 | P | P | P | Identify stakeholders with representatives of State Education Department; New York State Nurses Association and other interested stakeholders; identify areas in statutes, regulations and policies that would require change and formulate recommendations on scope of practice
PART B - ALLOW NURSE PRACTIONERS TO SIGN MEDICAL EVALUATIONS FOR ACF/AL
| 2011-06-01 | P | P | P | Draft regulatory changes to title 18 for internal review
| 2011-06-01 | P | P | P | Draft statuatory language for internal review
|  | 8 | 8 | 8 | Publish regulations in state register
|  | 8 | 8 | 8 | Respond to public comment
| 2011-07-20 | P | P | P | Governor signed Chapter 168 of Laws of 2011
| 2011-08-20 | P | P | P | Draft DAL for Executive Review
| 1/1/12 9/1/12 10/1/12 12/1/12 1/1/13 2/8/13 4/15/13 5/17/13 7/31/13 8/30/13 9/6/13 9/30/13 10/31/13 1/7/14 2/3/14 | P | P | P | Promulgate regulations
| 4/1/12 10/1/12 11/1/12 1/1/13 1/30/13 2/28/13 4/25/13 5/17/13 7/31/13 8/30/13 9/6/13 9/30/13 10/31/13 1/8/14 2/19/14 | P | P | P | Issue final DAL
PART C ELIMINATE RESTRICTIONS ON NURSING PRACTICES IN ACFS.
| 2011-04-28 | P | P | P | Discussed the concept of nursing in ACFs with the Division of Legal Affairs
| 2011-05-11 | P | P | P | Meeting scheduled with State Education Department representatives to discuss medications in ACFs
| 5/20/11 6/20/11 11/15/11 1/15/12 6/1/12 9/30/12 11/1/12 | P | P | P | DLA to draft concept paper proposal re: ACF limited LHCSAs
| 6/15/11 7/1/11 11/30/11 3/31/12 6/30/12 9/30/12 11/1/12 | P | P | P | Complete review of ACF Regulations and identify necessary amendments
PART D ALLOW LPNS TO COMPLETE ASSESSMENTS IN LTC SETTINGS
| 2011-04-15 | P | P | P | Convene internal meetings to determine next steps for revising scope of practice
| 2011-05-15 | P | P | P | Identify stakeholders with representatives of State Education Department; New York State Nurses Association and other interested stakeholders; identify areas in statutes, regulations and policies that would require change and formulate recommendations on scope of practice
PART E EXTEND THE USE OF MEDICATION AIDES INTO NURSING HOMES
| 5/15/11 7/15/11 11/1/11 | 8 | 8 | 8 | Identify areas in statutes, regulations and policies that would require change
| 5/15/11 7/15/11 | 8 | 8 | 8 | Develop agenda and timeline for meetings with SED and industry on proposed changes
| 9/1/11 10/1/11 11/15/11 12/15/11 | 8 | 8 | 8 | Draft changes to SED statute after workgroup discussions and consensus is reached
PART F EXPAND THE SCOPE OF PRACTICE OF HOME HEALTH AIDES TO INCLUDE THE ADMINISTRATION OF PRE-POURED MEDICATIONS TO BOTH SELF-DIRECTING AND NON-SELF DIRECTING INDIVIDUALS
| 2011-04-15 | P | P | P | Convene internal meetings to determine next steps for revising scope of practice
| 2011-05-15 | P | P | P | Identify stakeholders with representatives of State Education Department; New York State Nurses Association and other interested stakeholders; identify areas in statutes, regulations and policies that would require change and formulate recommendations on scope of practice
| 2011-12-31 | P | P | P | MRT Workforce Flexibility/Change of Scope of Practice recommendations approved by MRT and included in final report. Recommendations will be implemented in Phase 2 MRT process.
217 |  |  |  |  | Project Name: Create an Office for Development of Patient-Centered Primary Care Initiatives Division Lead: Team Lead: Description: |  | Completed
243 |  |  |  |  | Project Name: Accountable Care Organizations (ACOs) Division Lead: OHSM Team Lead: Joe Dimura Lisa Ullman Additional Staff: Karen Lipson, Jeffrey Rothman, Susan Bentley, Lisa McMurdo, Laura Lefebvre, Nina Daratsos, Phil Mossman, Lauren Tobias, Connie Donohue, Donna Haskin and Mark Tremblay. Description: PHL Article 29-E promotes the formation of ACOs to promote primary care, coordinated and improved care, while generating cost containment. This legislation requires DOH to establish a certification process for Medicare-only ACOs and to develop a regulatory framework to certify ACOs that will serve patients with other forms of health insurance. | 0 | Completed
DOH CERTIFICATION OF MEDICARE-ONLY ACOS
| 2012-09-27 | P | P | P | Convene DOH ACO work group to implement MRT # 243.
| 2012-11-02 | P | P | P | Review and summarize the Medicare-only ACOs Final Federal Rule.
| 11/2/12 | P | P | P | Review CMS ACO agreement forms, application forms and regulations which will be the bases for NYS regulations and certification process.
| 11/2/12 | P | P | P | Develop process for certifying Medicare-only ACOs in accord with CMS regs and NYS law.
| 12/7/12 | P | P | P | Next scheduled WG meeting.
| 11/26/12 12/14/12 | P | P | P | Work group drafted a letter which is going to be sent to each CMS approved Medicare-only ACO (15 Statewide). The letter provides policy and guidance on how to receive a NYS Certificate of Authority to operate as a Medicare-only ACO. The letter is under review by DLA and executive staff.
| 12/28/12 | P | P | P | Draft regulations developed and distributed to work group for review begining at next scheduled meeting on 1/3/13.
| 1/3/13 | P | P | P | next schedule work group meeting.
| 1/3/13 | P | P | P | Update to Medicare - Only letter: DOH's DLA office thought it was appropriate to ask Ms. Lisa Ulhman and Ms. Donna Frescator to review. DLA is currently checking with their office on status.
| 1/7/13 | P | P | P | Medicare - Only ACO certification letter approved by all parties and will be sent out by 1/11/13.
| 1/8/13 | P | P | P | Met with Assemblyman Gottfried to provide a update on current status of progress.
| 1/14/13 | P | P | P | Convened small sub group to work on draft regs to present to larger work group.
| 1/16/13 | P | P | P | Met with work group to continue our drafting of State ACO regs.
| 1/22/13 | P | P | P | Q&As for the commissioner's budget hearing have been completed and submitted providing status and outlook on the workgroups efforts.
| 1/31/13 5/31/13 8/30/13 10/31/13 6/21/14 10/19/14 12/17/14 | P | P | P | Develop DOH website containing information about ACOs that is useful to providers and patients; the information will be similar to the metrics published regarding MA managed care and health plans.
| 2/1/13 | P | P | P | Medicare-only ACOs will send their CMS documentation to OHSM and they will review and confirm their certification status. No new certificates can be issued after 12/31/16.
| 2/1/13 | P | P | P | Ensure that legal protections contained in PHL Art 29-E are granted to Medicare-only ACOs. This is an ongoing process that begins once DOH receives and approves Medicare-Only ACO application as outlined above. DOH has begun receiving applications.
| 2/1/13 and ongoing | P | P | P | Ensure that Medicare-only ACOs are operating in accordance with PHL Art. 29-E; if not DOH may limit, suspend or terminate a Certificate of Authority. This is an ongoing process that begins once DOH receives and approves Medicare-Only ACO application as outlined above. DOH has begun receiving applications.
| 3/1/13 | P | P | P | Begin to receive and review Medicare-Only certification applications
CERTIFY NON-MEDICARE ACOS WHO ACCEPT PATIENTS WITH OTHER FORMS OF HEALTH INSURANCE.
| 12/3/12 | P | P | P | State Regulations for State Certified ACOs (non-Medicare) currently under development.
| 1/28/13 | P | P | P | Consult with DFS, health care providers, third party payers (i.e., managed care plans/behavioral health organizations), advocates representing patients and other appropriate parties to draft non-Medicare ACO regulations. New amendament issued 1/9/13 allows for the regs to be developed in draft from prior to review by stakeholders.
| 5/16/13 | P | P | P | Sub group consisting of DFS staff including legal and DOH to work on issues relating to Third Party Payor/Shared saving and other payment section issues.
| 5/29/13 | P | P | P | Language specifically forbidding ACO's to sell insurance products will be included in the reg..
| 5/29/13 | P | P | P | ACO's must comply with all requirements of the 3rd party payor rules.
| 5/29/13 | P | P | P | IPA's must apply and will be regulated as a distinct ACO.
| 5/29/13 | P | P | P | Reg 164 will only apply to an ACO applicant if that entity is looking to contract to share risk through a capitation arrangement with entities certified under Article 44 of the Public Health Law, insurance companies authorized to do accident and health insurance. Reg 164 will be amended by DFS to include language specific to ACO's.
| 5/29/13 | P | P | P | any issues arising from ACO contracts with out of state insurers will be subject to the rules and regs of the state where the Insurance provider is regulated by.
| 6/3/13 | P | P | P | sub group of OHIP & OHSM to meet to discuss Dual eligible issues
| 6/3/13 | P | P | P | received confirmation from DFS staff that ammendment to Reg 164 will be completed with one month's time that will add ACO to the definition of "Intermediary Entity" which will require ACO's to comply with reg 164 which sets forth standards for financial risk transfers b/t insurers and health care providers.
| 6/11/13 | P | P | P | OHSM sub-group met to outline specific questions we have resulting from Dual Eligible and Medicaid inclusion in ACO reg
| 6/12/13 | P | P | P | Completed and submitted to OHIP staff questions and guidance for language to include in draft reg for Dual eligible and Medicaid inclusion in reg
| 6/12/13 | P | P | P | Met with OHIP staff to discuss recommended responses and language based on sub group questions
| 5/31/13 6/30/13 | P | P | P | DFS/DOH Sub group to complete Payment and shared savings section language
| 8/31/13 | P | P | P | Language specific to allowing ACO's to contract with DOH for Medicaid recipients under a full risk/capitation agreement w/o requirement of an Insurance License under art. 44 - reg 164 needs to be developed by DFS and reviewed and approved by DFS ES and DOH ES prior to inclusion in draft Reg. DFS Superintendent has approved Payment language that DOES NOT allow ACO to conrtract for full capitation with DOH w/o an Insurance license.
| 9/5/13 | P | P | P | Draft reg submitted to Dr. Shah, Sue Kelly, Karen W and Jason H for their review.
| 9/15/13 | P | P | P | AG's office to review Restraint of Trade language included in draft(currently under review 8/23/13).
| 2/1/13 4/15/13 5/31/13 6/31/13 7/30/13 9/15/13 10/8/13 10/16/13 11/2/13 2/5/14 4/30/14 8/13/14 10/15/14 | P | P | P | Develop and present concept paper to the Regulatory Affairs Unit, to include Regulatory impact statement(draft completed 8/21/13)
| 5/15/13 8/25/13 9/20/13 1/15/14 6/14/14 | P | P | P | Review/address public comments from stakeholder meeting
| 3/1/13 4/1/13 6/30/13 8/30/13 9/12/13 TBD 1/16/14 2/6/14 3/6/14 | P | P | P | Stakeholder review and feedback, meeting scheduled to include CHHANYS- Ed McGill GNYHA- Katherine Shure CHCANYS- Elizabeth Swain and Beverly Grossman Health Plan Association- Rose Duhan PHSPS- Anthony Fiori Hinman/Straub- Stephanie Piel and Monitfiore hospital
| 3/1/13 4/1/13 6/30/13 8/30/13 9/12/13 TBD 1/16/14 2/6/14 4/2/14 5/21/14 | P | P | P | 2nd Stakeholder review and feedback, meeting scheduled to include CHHANYS- Ed McGill GNYHA- Katherine Shure CHCANYS- Elizabeth Swain and Beverly Grossman Health Plan Association- Rose Duhan PHSPS- Anthony Fiori Hinman/Straub- Stephanie Piel and Monitfiore hospital
| 11/4/13 | P | P | P | Receive responses from other states on policy reqarding State Insurance licensure requirements
| 4/1/13 6/30/13 8/30/13 10/31/13 2/20/14 4/30/14 8/20/14 10/15/14 | P | P | P | Publish regulations in the State Register/ 45-day public comment period begins (send to DOS 9/30/14).
| 5/27/13 9/30/13 4/30/14 6/14/14 12/24/14 12/31/14 | P | P | P | Notice of adoption effective and published in the State Register (send to DOS 12/16/14)
| 6/7/13 8/30/13 | P | P | P | Develop requirements and process to certify non-Medicare ACOs.
| 6/7/13 7/4/14 12/17/14 2/15/15 | 8 | 8 | 8 | Develop DOH website containing information about non Medicare-only ACOs that is useful to providers and patients; the information will be similar to the metrics published regarding MA managed care and health homes. | Under development
| 6/24/13 10/19/13 | P | P | P | Non Medicare-only ACOs will send their documentation to OHSM and they will review and confirm their certification status. No new certificates can be issued after 12/31/16.
990 |  |  |  |  | Project Name: Explore the Establishment of Reimbursement Rates to Support Efforts to Address Health Disparities Division Lead: Division of Financial Planning and Policy (DFPP); Greg Allen, Director Team Lead: Hope Plavin Add'l staff: Donna Haskin, Ron Bass Description: Explore enhanced reimbursement rates for culturally competent care | 0 | Completed
ESTABLISHMENT OF REIMBURSEMENT RATES
| 5/15/11 5/1/11 | P | P | P | Discuss initiative with the Office of Public Health to determine activities necessary to support culturally competent care that address health disparities
| 5/15/11 5/1/11 | P | P | P | Identify availability of information on cultural competency and training opportunities for health care providers
| 5/29/11 5/15/11 6/15/11 | P | P | P | Meet with stakeholders
| 5/15/11 6/15/11 | P | P | P | Identify costs associated with incorporating cultural competency in health care settings
| 2011-06-15 | P | P | P | Identify certification requirements for medical language interpretation services.
| 2011-06-15 | P | P | P | Identify barriers to medical language interpreter certification.
| 7/15/11 9/1/11 | P | P | P | Review CHIPRA regulations and explore the possibility of 75% FMAP
| 6/1/11 6/29/11 7/29/11 9/1/11 11/1/11 6/1/12 | 8 | 8 | 8 | Determine whether enhanced reimbursement for Medical Language Interpreting Services is appropriate and, if so, the amount of enhancing reimbursement for Medical Language Interpreting Services.
| 6/30/11 7/29/11 9/1/11 11/15/11 6/15/12 | 8 | 8 | 8 | Pending a coverage decision on Medical Language Interpreting Services, determine policy and monitoring protocols related to enhanced reimbursement for these services to support culturally competent care.
| 7/5/11 8/15/11 9/1/11 11/15/11 6/15/12 | 8 | 8 | 8 | If enhancing reimbursement, determine payment methodology
| 9/15/11 9/1/11 11/30/11 6/30/12 | 8 | 8 | 8 | Notify providers of available enhancement and billing guidance.
| 2011-09-15 | 8 | 8 | 8 | Complete system changes.
| 10/15/11 10/1/11 12/15/11 7/1/12 | 8 | 8 | 8 | Implement enhancement.
| 2011-12-31 | P | P | P | Recommendations of MRT Health Disparities Work Group included in MRT Final Report. Recommendations will be implemented as part of MRT Phase 2 process in 2012.
MRT HEALTH DISPARITIES WORK GROUP
| 2011-08-01 | P | P | P | Announce work group membership
| 2011-08-09 | P | P | P | Initial work group meeting - Albany
| 2011-09-16 | P | P | P | Second work group meeting - NYC
| 2011-10-03 | P | P | P | Third work group meeting - Albany/NYC
| 2011-10-12 | P | P | P | Fourth work group meeting - location TBD
| 2011-11-01 | P | P | P | Final recommendations submitted to the full MRT
889 |  |  |  |  | Project Name: Redesign NYS Bed Hold Policy for Nursing Homes Division Lead: OLTC Team Lead: Robert Loftus Additional Staff: Jackie Pappalardi, Ken Evans, Joe Naglieri Description: Redesign the nursing home bed hold policy for all Medicaid recipients over 21 to recalibrate Medicaid benefits and reimbursement rates, and to meet the Medicaid savings target as proposed. | 0 | Completed
| 2011-03-10 | P | P | P | Meet with Internal Stakeholders to review options to implement proposal.
| 2011-03-11 | P | P | P | Submit Federal Public Notice for MRT 889
| 2011-05-13 | P | P | P | Draft and submit SPA.
| 2011-08-02 | P | P | P | Confer with CMS on draft SPA submitted for MRT#889
| 8/18/11 3/15/12 | P | P | P | Submit implementation options to Department Executives.
| 2012-03-27 | 8 | 8 | 8 | Implement evolution project with new edits
| 2012-04-15 | P | P | P | Reconvene internal group to review changes to bed hold law
| 4/15/12 4/20/12 | P | P | P | Calculate savings achieved with edits in place
| 2012-05-15 | P | P | P | Develop draft alternative options for new policy
| 2012-05-15 | P | P | P | Submit options to the Dept. Executive Staff for review
| 2012-07-10 | P | P | P | Week of 7/9/12: Meet with NH associations to discuss options
| 2012-07-24 | P | P | P | Meet with NH associations to discuss options
| 2012-08-27 | P | P | P | Meet with DOH principals to discuss options
| 5/15/12 7/23/12 9/30/12 | P | P | P | Confer with CMS on options drafted
| 8/15/11 8-30-11 4/15/12 6/1/12 8/1/12 9/30/12 | P | P | P | Draft and submit new SPA.
| 6/15/12 8/15/12 9/30/12 | P | P | P | Submit evolution project for program edits (if necessary)
| 7/15/11 8/30/11 5/15/12 7/15/12 9/15/12 9/30/12 | P | P | P | Identify regulatory and systems requirements necessary to implement the recommendations of the proposal. Staff work on regulation is complete.
| 10/1/11 11/15/11 4/1/12 5/15/12 7/15/12 9/15/12 9/30/12 11/30/12 12/31/12 | P | P | P | Upon CMS approval, communicate policy requirements to Stakeholders through a Dear Administrator Letter and Dear CEO letter. Post Questions and Answers and provider communication to the public website.
| 2013-01-01 | P | P | P | Per diem adjustment to capture balance of savings achieved by bedhold implemented.
| 2/1/13 2/18/13 | P | P | P | Implement, retroactive to 7/1/12, reduction in bed hold payment for hospital leaves of absence.
1058 |  |  |  |  | Project Name: Maximize Peer Services Division Lead: DFPP Team Lead: Jacqueline Allaman Description: Explore Medicaid Reimbursement for peer services such as care and recovery coaches | 0 | Completed
| 2011-03-31 | P | P | P | Submit FPN
| 2011-04-20 | P | P | P | Begin research regarding use of peers in health programs including mental health and substance abuse programs, programs for people with developmental disabilities, and long term care programs.
| 2011-05-03 | P | P | P | Meet with OMH, OPWDD, OASAS, OLTC regarding use of peers
| 2011-05-20 | P | P | P | Meet with stakeholders to discuss ideas, suggestions, etc.
| 2011-07-08 | P | P | P | Meet with stakeholders to share research findings and discuss recommendations
| 2011-08-01 | P | P | P | Develop draft report and place in internal clearance
| 8/8/11 8/15/11 8/25/11 | P | P | P | Complete internal clearance and send to stakeholders for comments
| 8/22/11 9/1/11 | P | P | P | Receive comments from stakeholders on draft report and revise report
| 8/26/11 9/6/11 | P | P | P | Meet with stakeholders to discuss final edits
| 9/9/11 9/8/11 | P | P | P | Complete report and place in final internal clearance for approval
| 9/16/11 9/9/11 | P | P | P | Submit report to BHO Subcommittee
| 2011-09-16 | 8 | 8 | 8 | Determine next steps based on report findings
| 2011-10-03 | 8 | 8 | 8 | Announce report regarding the use of peers within Medicaid reimbursable programs
1032 |  |  |  |  | Project Name: Establish a Housing Disregard as Incentive to Join Managed Long Term care (MLTC) Division Lead: Coverage and Enrollment Team Lead: Wendy Butz Description: Provide nursing home residents who are discharged back to the community with a housing disregard if they join a MLTC plan. | 0 | Completed
POLICY AND PROCEDURE
| 7/30/11 8/15/11 8-30-11 9/30/11 10/21/11 11/21/11 12/15/11 1/27/12 | P | P | P | Complete review of policy issues
| 12/1/11 12/27/11 2/1/12 2/24/12 3/2/12 5/1/12 | P | P | P | Submit draft ADM for clearance
| 3/1/12 3/16/12 5/21/12 7/1/12 9/1/12 9/15/12 10/1/12 | P | P | P | Issue ADM - effective 04/02/2012 07/01/12 09/01/12 9/15/12 10/15/12
1115 WAIVER
| 7/30/11 9/23/11 10/21/11 11/21/11 12/1/11 12/27/11 1/27/12 | P | P | P | Submit draft Waiver to CMS for informal review
| 7/30/11 9/23/11 10/21/11 11/21/11 12/1/11 12/27/11 1/27/12 | P | P | P | Submit draft Waiver for DOH clearance
| 10/31/11 11/30/11 1/15/12 | P | P | P | Finalize and submit Waiver to HCRA
| 2012-03-01 | P | P | P | Submission of Waiver to CMS
SYSTEMS UPDATES
| 2011-04-01 | P | P | P | Submit System Change Request
| 8/5/11 9/23/11 10/14/11 12/1/11 11/15/11 | P | P | P | Finalize system change requirements
| 8/30/11 10/31/11 12/15/11 | P | P | P | Finalize System Action Request
CNS
| 4/27/12 3/2/12 3/9/12 4/15/12 | P | P | P | Development/coding changes
| 6/8/12 4/14/12 5/14/12 6/6/12 | P | P | P | Unit testing
| 2012-06-15 | P | P | P | User Acceptance
MBL
| 4/27/12 3/2/12 3/9/12 4/15/12 | P | P | P | Development/coding changes
| 6/8/12 4/14/12 5/14/12 6/6/12 | P | P | P | Unit testing
| 2012-06-15 | P | P | P | User Acceptance
WMS
| 4/27/12 3/2/12 3/9/12 4/15/12 | P | P | P | Development/coding changes
| 6/8/12 4/14/12 5/14/12 | P | P | P | Unit testing
| 2012-06-15 | P | P | P | User Acceptance
| 06/12 (12.2 Migration) | P | P | P | Migrate system changes
| 6/20/12 6/18/12 10/15/12 | P | P | P | Implementation
1434 |  |  |  |  | Project Name: Convert a portion of Family Planning grants to Medicaid rate reimbursement Division Lead: DFFP Team Lead: Alan Maughan Description: Convert a portion of Family Planning grants to 90% federally funded Medicaid rates. | -7 | Completed
| 2011-03-14 | P | P | P | Begin drafting required SPA, Regulation changes, and Federal Public Notice
| 2011-03-15 | P | P | P | Submit Public Notice
| 2011-04-13 | P | P | P | Notify providers via Medicaid Update and eMedNY Provider Communications
| 2011-03-25 | P | P | P | Submit SPA - SPA no longer required
| 2011-05-01 | P | P | P | Submit regulation changes - Regulation no longer required
| 5/23/11 5/30/11 | P | P | P | Notify providers of the updated implementation methodology
| 5/25/11 5/30/11 6/22/11 | P | P | P | Receive schedule for contract updates from the Division of Family Health
| 2011-06-22 | P | P | P | Emails sent to FP contractors informing them of their 2011 contract reductions (Bureau of Maternal Child Health)
| 2011-07-01 | P | P | P | Implement Prospectively
| 2011-10-15 | 8 | 8 | 8 | FP contract amendments complete (Bureau of Maternal Child Health)
| 2011-07-01 | 8 | 8 | 8 | Implement retroactive to 4/1/11 (pending SPA approval)
| 2011-08-15 | 8 | 8 | 8 | Reprocess affected claims back to 4/1/11 - July-August 2011
1172 |  |  |  |  | Project Name: Nursing Home Sprinkler Loan Pool Division Lead: DHCF Team Lead: Lana I. Earle Description: Assist NHs with Developing Financing Mechanism to Satisfy Federal Sprinkler Mandate, Effective August 13, 2013 | 0 | Completed
| 2011-04-21 | P | P | P | Follow up meeting on conference calls and discussions held in Mid March with DASNY, NYAHSA and DOH to determine the potential financing vehicles/structures available to NHs to meet Federal Mandate
| 2011-05-15 | P | P | P | Exchange information with Industry Associations identifying sprinkler needs and costs by facility and sponsor, continue to determine if there are lenders willing to finance NH sprinklers, and/or if there are sprinkler vendors interested in large pooled financings
| 5/25/11 6/2/11 | P | P | P | Internal meeting to discuss next steps.
| 6/14/11 6/24/11 | P | P | P | Follow up meeting with DOH, DASNY and Associations
| 8/1/11 8/19/11 | P | P | P | Work with DASNY and associations to develop informational materials (reimbursement methodology, financial condition of NHs) for vendors and lenders, meet with potential banks
| 2011-08-23 | P | P | P | Provide association list of NHs that have submitted CON to determine if they have secured financing
| 9/2/11 9/7/11 | P | P | P | Provide association list of NHs that have not submitted CON and are not sprinkler compliant to determine if they have secured financing
| 9/8/11 9/19/11 | P | P | P | Meet with associations to discuss lists and potential options for financially struggling nursing homes that cannot secure financing
| 2011-09-29 | P | P | P | Industry associations will use the lists to survey homes to determine which homes have secured resources/financing, for homes financing who are the lenders and what are the terms of the financings, who are the anticipated vendors/installers of sprinkler equipment - reach out to National Association and other states
| 2011-10-12 | P | P | P | Industry Association survey completed
| 10/21/11 10/31/11 | P | P | P | Between 10/14 and 10/31 conduct follow up to survey responses (if necessary)
| 2011-11-01 | P | P | P | Summarize and evaluate survey data and formulate options
| 2011-11-29 | P | P | P | Follow-up meeting on options for homes that cannot independently secure financing
| 2011-12-13 | P | P | P | Conference Call to distribute information on homes with HUD insured mortgages - continue to compile list of homes that need assistance
| 2011-12-29 | P | P | P | Review list of homes that need assistance - Identify those with HUD insured morgages
| 2012-01-10 | P | P | P | Conf call with associations to finalize list of NHs that possibly need assistance with sprinklers
| 2012-01-19 | P | P | P | Follow up meeting on status of lists
| 1/6/12 1/25/12 | P | P | P | Contact HUD to discuss options
| 1/20/12 1/25/12 | P | P | P | Conf call with HUD on Financing Options, Match list to the HUD list
| 2012-01-30 | P | P | P | Weekly follow up call w/ assocs on status of sprinkler compliance list
| 1/30/12 2/6/12 2/13/12 | P | P | P | Record webinar for week of 2/13/12
| 2/1/12 3/1/12 | P | P | P | Weekly follow up call w/ assocs on status of sprinkler compliance list (Financially Disadv Calc on Hold pending filing of final cost reports by certain facilities)
| 2012-03-08 | P | P | P | Weekly follow up call w/ assocs on status of sprinkler compliance list, list Finalized, Options for financing for facilities that are financially challenged and cannot access credit markets - accelerate capital reimbursement - potential lenders include Pension Fund, other banks
| 2012-03-15 | P | P | P | Joint letter from DOH and Associations to HUD requesting HUD verify which NHs are FHA insured,allow subordinate debt, and be flexible with respect to pledged accounts receivable and the use of escrow funds.
| 2012-04-06 | P | P | P | Finalize draft regulation for submission to Public Health and Health Planning Council (PHHPC)
| 2012-04-13 | P | P | P | Finalize PPT for PHHPC
| 5/1/12 6/1/12 | P | P | P | Submit SPA to CMS
| 2012-05-24 | P | P | P | PHHPC Committee Meeting - Emergency Reg
| 2012-06-07 | P | P | P | PHHPC Council Meeting (NYC) - Emergency Reg
| 8/1/12 7/14/12 | P | P | P | Distribute DAL to FD Facilities
| 4/27/12 6/1/12 7/16/12 | P | P | P | Finalize Draft DAL to FD Facilities describing application process for the acceleration of capital reimbursement
| 7/26/12 8/9/12 | P | P | P | PHHPC Committee Meeting - Second Emergency Adoption
| 2012-08-21 | P | P | P | Governor's Office approval of permnament reg filed with DOS. 45 Day Public Comment begins
| 6/30/12 8/1/12 9/30/12 | P | P | P | CMS approval of SPA
| 7/1/12 8/1/12 9/30/12 3/30/13 | P | P | P | Process applications and rate adjustments (ongoing)
| 8/1/12 - 10/1/12 | P | P | P | Ongoing submission and review of requests from FD facilities to accelerate rate - amend capital rates as required (followng PHHPC approval / Reg Filing) - Work with Associations to brief lenders on the accelerated capital regulations
| 8/9/12 12/6/12 | P | P | P | PHHPC Council Meeting (NYC) - Regular Reg Adoption
1451 |  |  |  |  | Project Name: Establish Various MRT Workgroups Division Lead: OHIP Team Lead: Jason Helgerson Description: Establish various workgroups to focus discussion on major reform issues. Workgroups will include: Payment Reform, Basic Benefit Review, Program Streamlining and State/Local Responsibility, Supportive Housing, Managed Long Term Care Implemenation and Waiver Redesign, Behavioral Health Reform, Workforce Flexibility and Change of Scope Practice, Medical Malpractice and Health Disparities | 0 | Completed
| 2011-03-21 | P | P | P | Solicit participation of MRT members through email
| 2011-04-08 | P | P | P | Determine State lead for each of the nine subcommittees
| 2011-04-18 | P | P | P | Distribute draft subcommittee charges to DOH leads
| 2011-04-22 | P | P | P | Meet with State subcommittee leads to determine process for engaging outside stakeholders & calendar of meetings
| 2011-05-05 | P | P | P | Deadline for MRT members to identify subcommittees they would like to participate in
| 2011-05-25 | P | P | P | Kickoff meeting with internal staff on initial three workgroups: Behavioral health reform, MLTC, Program Streamlining and State/Local
| 2011-06-15 | P | P | P | DOH subcommittee leads to present Jason Helgerson with list of outside stakeholders to participate in subcommittee, determined in consultation with subcommittee chairs
| 2011-06-15 | P | P | P | Biweekly meetings with Jason Helgerson and State subcommittee leads to commence.
| 2011-06-15 | P | P | P | Invitations to initial three workgroup members to be sent
| 2011-06-20 | P | P | P | Work group membership and meeting dates to be posted to web
| 2011-06-25 | P | P | P | First workgroup meeting. Workgroups will meet a minimum of 2-3 times between June and October.
| 2011-07-15 | P | P | P | Decision made on second round of workgroups to begin; dates set for invitations and meetings.
| 2011-07-21 | P | P | P | Health Systems Redesign: Brooklyn work group begins; hearings scheduled for 8/28 and 9/21
| 8/1/11 8/25/11 | P | P | P | Decision made on third round of workgroups to begin; dates set for invitations and meetings.
| 2011-11-01 | P | P | P | Recommendations from phase 1 workgroups presented to MRT
| 2011-12-13 | P | P | P | Recommendations from phase 2 & 3 workgroups presented to MRT
| 2011-12-31 | P | P | P | MRT to report to Governor Cuomo and forward approved work group recommendations
1458 (Partially Complete) |  |  |  |  | Project Name: Care Management Population & Benefit Expansion, Access to Services, and Consumer Rights Division Lead: DMC Team Lead: Jennifer Dean Additional Staff: Nina Daratsos Description: Omnibus Medicaid Managed Care initiatives, eliminates many exempt/excluded populations, expands the benefit package, promotes access to services, and ensures consumer rights | -14.15 | Completed
| Att. 1 (Year 1) | P | P | P | Attachment 1 - Expand Managed care Enrollment for non-dual eligibles and modify mainstream benefit package
| Att. 1 (Year 2) | 8 | 8 | 8 | Attachment 1 - Expand Managed care Enrollment for non-dual eligibles and modify mainstream benefit package
| Att. 2 | P | P | P | Attachment 2 - Access to Benefits and Consumer Protections
| Att. 3 | P | P | P | Attachment 3 - Streamline Managed care Eligibility Process
| Att. 1 |  |  |  | ATTACHMENT 1 - EXPAND MANAGED CARE ENROLLMENT FOR NON-DUAL ELIGIBLES AND MODIFY MAINSTREAM BENEFIT PACKAGE
RATES
| See MRT #6 |  |  |  | Rate Implementation
DMC IMPLEMENTATION
| 2011-03-11 | P | P | P | Draft accompanying legislation for review
| 2011-03-14 | P | P | P | Assess systems impact internally and discussed with EB/EC systems staff
| 2011-03-20 | P | P | P | Draft accompanying waiver changes for proposal to CMS
| 2011-03-21 | P | P | P | Internal meeting regarding personal care benefit change / MCO contracting issues
| 2011-03-24 | P | P | P | Meet with Health Plan Associations to discuss proposal impact
| 2011-04-11 | P | P | P | Meet with enrollment broker to discuss proposal impact
| 2011-04-13 | P | P | P | Conference Call with LDSS to discuss changes
| 2011-04-20 | P | P | P | CMS waiver changes sent to CMS
| 2011-04-20 | P | P | P | Tribal notice sent
| 2011-04-21 | P | P | P | Begin weekly meetings with systems staff
| 2011-04-25 | P | P | P | Finalize recipient restriction policy for enforcing restrictions on carved out services
| 2011-04-27 | P | P | P | MMC Contract to CMS for approval
| 2011-04-27 | P | P | P | Public Notice Issued for waiver amendment
| 2011-04-30 | P | P | P | Notify MCO's of personal care contracting requirements
| 2011-04-30 | P | P | P | Deliver systems change SA /EP to WMS/eMedNY for implementation
| 2011-04-30 | P | P | P | Meet with Enrollment Broker Contractor to review changes made and training needs for call center and outreach staff
| 2011-05-04 | P | P | P | Meet with managed care plans regarding personal care benefit transition and restricting recipients within MMC
| 2011-05-11 | P | P | P | MMCARP meeting review of changes
| 2011-06-15 | P | P | P | Identify excluded/exempt populations in FFS (for Rates)
| 5/30/11 6/6/11 6/20/11 | P | P | P | Review and approve MCO subcontracts for personal care benefit
| 5/10/11 5/30/11 6/6/11 7/1/11 | P | P | P | Draft MMC statewide contract amendment including new benefit package language effective 7-1-2011 8-1-2011
| 5/25/11 6/15/11 7/1/11 | P | P | P | Notify current managed care recipients of personal care of benefit change
| 7/20/11 7/27/11 | P | P | P | Train enrollment broker on population expansions
| 8/1/11 9/1/11 | P | P | P | Train local social services districts and EB/EC staff on populations being added
| 2011-09-01 | P | P | P | Medicaid Update article released
| 2011-09-01 | P | P | P | Outreach completed for providers, plans, advocacy groups, etc.
| 2011-09-07 | P | P | P | Training completed for Fair Hearings staff
| 9/1/11 9/20/11 9/25/11 | P | P | P | Waiver negotiations complete
| 9/1/11 9/10/11 9/25/11 10/1/11 | P | P | P | Distribute new materials to LDSS/other stakeholders
| 2011-10-01 | P | P | P | Implementation
| 6/20/11 9/1/11 10/1/11 10/14/11 10/31/11 11/30/11 12/8/11 12/16/11 | P | P | P | CMS approval of MMC/NYC contract terminations and MMC amendments
RATES
| See MRT #6 |  |  |  | Rate Implementation
| Att. 2 |  |  |  | ATTACHMENT 2 - ACCESS TO BENEFITS AND CONSUMER PROTECTIONS
| 2011-03-24 | P | P | P | Meet with Health Plan Associations to discuss proposal impact
| 2011-04-15 | P | P | P | Review MCO benefits denial model notices for changes
| 2011-04-30 | P | P | P | Review model managed care handbooks for information regarding benefits coverage
| 2011-05-11 | P | P | P | MMCARP meeting review of changes
| 4/30/11 5/25/11 6/1/11 6/20/11 | P | P | P | Distribute new model language to plans for benefits denial notices
| 5/20/11 6/9/11 | P | P | P | Distribute to plans amended handbook language for eratta sheets
| 2011-07-01 | P | P | P | Implementation of updated notices
| 5/30/11 7/1/11 7/30/11 9/1/11 | P | P | P | Implementation of updated notices
| 2011-09-01 | P | P | P | Outreach completed for providers, plans, advocacy groups, etc.
| Att. 3 |  |  |  | ATTACHMENT 3 - STREAMLINE MANAGED CARE ELIGIBILITY PROCESS
| 2011-03-11 | P | P | P | Draft accompanying legislation for review
| 2011-03-14 | P | P | P | Assess systems impact internally and discussed with EB/EC systems staff
| 2011-03-20 | P | P | P | Draft accompanying waiver changes for proposal to CMS
| 2011-03-21 | P | P | P | Internal meeting with OHIP eligibility and FE oversight staff regarding choice period
| 2011-03-24 | P | P | P | Meet with Health Plan Associations to discuss proposal impact
| 2011-04-04 | P | P | P | Develop managed care contract change
| 2011-04-08 | P | P | P | Meet with systems staff to ensure timing of changes.
| 2011-04-20 | P | P | P | Review available informational materials for necessary changes
| 2011-04-27 | P | P | P | Public Notice Issued for waiver amendment
| 2011-04-30 | P | P | P | Meet with Enrollment Broker Contractor to review changes made and training needs for call center and outreach staff
| 2011-05-05 | P | P | P | Draft/approve changes to program materials for printing (brochures, enrollment forms,etc)
| 2011-05-06 | P | P | P | Finalize system change requirements
| 2011-05-11 | P | P | P | MMCARP meeting review of changes
| 2011-05-13 | P | P | P | Deliver systems change EP to eMedNY for implementation
| 2011-05-13 | P | P | P | System specifications submitted to WMS (SA)
| 2011-07-15 | P | P | P | WMS Systems changes testing begins
| 7/20/11 7/27/11 | P | P | P | Train enrollment broker on choice period changes
| 8/1/11 9/1/11 | P | P | P | Train local social services districts and EB/EC staff on choice period changes
| 2011-09-01 | P | P | P | Medicaid Update article released
| 2011-09-07 | P | P | P | Training completed for Fair Hearings staff
| 2011-09-15 | P | P | P | Outreach completed for providers, plans, advocacy groups, etc.
| 9/1/11 9/10/11 9/25/11 | P | P | P | Distribute new materials to LDSS/other stakeholders
| 2011-10-01 | P | P | P | Implementation
| Year 1 Implementation | P | P | P | ATTACHMENT 1 - EXPAND MANAGED CARE ENROLLMENT FOR NON-DUAL ELIGIBLES AND MODIFY MAINSTREAM BENEFIT PACKAGE
RATES
| See MRT #6 |  |  |  | Rate Implementation
POPULATION EXPANSION 4/1/12
| 2011-11-10 | P | P | P | Submit 4/1/12 waiver changes to CMS
| 2011-11-15 | P | P | P | Upstate stakeholder meeting to identify homeless issues
| 2011-11-17 | P | P | P | Downstate stakeholder meeting to identify homeless issues
| 2011-11-28 | P | P | P | Managed Care Policy and Planning Meeting with MCOs
| 2011-12-08 | P | P | P | Present 4/1/12 changes to MMCARP
| 2011-12-20 | P | P | P | Upstate homeless issues follow-up conference call
| 2011-12-21 | P | P | P | Downstate homeless issues follow-up conference call
| 2012-01-04 | P | P | P | Homeless population phase-in meeting
| 2012-01-09 | P | P | P | Managed Care Policy and Planning Meeting with MCOs
| 2012-01-10 | P | P | P | Medicaid managed care homeless operational issues follow-up conference call
| 2012-01-21 | P | P | P | Assess systems impact internally and discussed with EB/EC and WMS/eMedNY systems staff
| 2012-01-27 | P | P | P | Formation of subgroups for homeless issues
| 2012-01-27 | P | P | P | Discussion of homeless assessment regulatory requirements
| 2012-01-30 | P | P | P | Deliver systems change SA /EP to WMS/eMedNY for implementation
| 2012-01-31 | P | P | P | Discussion with Maximus
| 2012-02-01 | P | P | P | Begin training of LDSS / stakeholders
| 2012-02-06 | P | P | P | Discussion with Maximus
| 2012-02-07 | P | P | P | Meet (call) with Medicaid Matters
| 2012-02-10 | P | P | P | Homeless provider/FQHC Information sent to plans
| 2012-02-15 | P | P | P | Train enrollment broker on population expansions
| 2012-02-15 | P | P | P | Train local social services districts and EB/EC staff on populations being added
| 2012-02-16 | P | P | P | Managed Care Policy and Planning Meeting with MCOs
| 2012-02-22 | P | P | P | Completion of Initial Assessment Workgroup
| 2012-02-24 | P | P | P | Completion of Case Management Workgroup
| 2012-03-01 | P | P | P | ESRD provider information sent to plans
| 2012-03-01 | P | P | P | Completion of Return Mail Workgroup
| 2012-03-01 | P | P | P | Medicaid Update articles released for ESRD, homeless, LBW babies, etc
| 2012-03-07 | P | P | P | Statewide webinar w/ stakeholders
| 2012-03-15 | P | P | P | Managed Care Policy and Planning Meeting with MCOs
| 2012-03-21 | P | P | P | Review final changes with LDSS staff
| 2012-03-21 | P | P | P | Exemption form reviewed and approved
| 2012-03-22 | P | P | P | Updated mandatory brochure
| 2012-03-22 | P | P | P | Training for Schuyler and Steuben mandatory program
| 2012-03-25 | P | P | P | Outreach completed for providers, plans, advocacy groups, etc.
| 2012-03-25 | P | P | P | Training completed for Fair Hearings staff
| 2012-03-25 | P | P | P | Waiver negotiations complete (all approved but look-alike population)
| 2012-03-28 | P | P | P | Distribute new materials to LDSS/other stakeholders
| 2012-04-01 | P | P | P | Implementation
| 2012-04-03 | P | P | P | MMCARP meeting review of changes
| 2012-04-09 | P | P | P | Meet (call) with Medicaid Matters
| 2012-04-17 | P | P | P | Managed Care Policy and Planning Meeting with MCOs
| 2012-04-21 | P | P | P | Statewide webinar Q&A document posted to the web
| 2012-05-14 | P | P | P | HRA/DHS/SDOH/EB meeting with plans regarding homeless implementation
| 2012-05-16 | P | P | P | HRA/SDOH/EB meeting with plans regarding homeless systems implementation
| 2012-07-30 | P | P | P | Waiver negotiations complete (look-alike population)
| 2012-08-14 | P | P | P | Meeting to discuss/identify homeless implementation issues
COUNTY MANDATORY ENROLLMENT EXPANSIONS 2012
| 2011-10-17 | P | P | P | Letter to Schuyler and Steuben County Commissioners on mandatory implementation
| 2012-04-02 | P | P | P | Heads up letters to Schuyler and Steuben County recipients
| 2012-05-01 | P | P | P | Mandatory Stakeholder Meeting for Schuyler County
| 2012-05-02 | P | P | P | Mandatory Stakeholder Meeting for Steuben County
| 2012-05-02 | P | P | P | Medicaid Update article for Schuler and Steuben mandatory implementation
| 2012-04-24 | P | P | P | Maximus site visit for Schuyler County
| 2012-04-25 | P | P | P | Maximus site visit for Steuben County
| 2012-05-15 | P | P | P | Staff training for Schuyler County
| 2012-05-16 | P | P | P | Staff training for Steuben County
| 2012-05-09 | P | P | P | Max EB and Exemption training for Schuyler County managed care staff
| 2012-05-10 | P | P | P | Max EB and Exemption training for Steuben County managed care staff
| 2012-03-16 | P | P | P | Letter to Tioga County Commissioner on mandatory implementation
| 2012-04-19 | P | P | P | Meet with Tioga County Commissioner and staff regarding implementation
| 2012-06-13 | P | P | P | Maximus site visit for Tioga County
| 2012-05-15 | P | P | P | Heads up letters to Tioga recipients
| 2012-06-07 | P | P | P | Mandatory Stakeholder Meeting for Tioga County
| 2012-05-30 | P | P | P | Medicaid Update article for Tioga County mandatory implementation
| 2012-06-26 | P | P | P | Max EB and Exemption training for Tioga County managed care staff
| 2012-07-19 | P | P | P | Staff Training for Tioga County
| 2012-03-16 | P | P | P | Letter to Wyoming County Commissioner on mandatory implementation
| 2012-05-10 | P | P | P | Meet with Wyoming County Commissioner and staff regarding implementation
| 2012-06-05 | P | P | P | Heads up letters to Wyoming recipients
| 2012-07-20 | P | P | P | Mandatory Stakeholder Meeting for Wyoming County
| 2012-06-30 | P | P | P | Medicaid Update article for Wyoming County
| 2012-05-18 | P | P | P | Letter to Jefferson County Commissioner on mandatory implementation
| 2012-06-19 | P | P | P | Meet with Jefferson County Commissioner and staff regarding implementation
| 2012-08-08 | P | P | P | Maximus site visit for Jefferson County
| 2012-09-04 | P | P | P | Heads up letters to Jefferson recipients
| 9/15/12 9/19/12 | P | P | P | Mandatory Stakeholder Meeting for Jefferson County
| 9/15/12 9/19/12 | P | P | P | Max EB and Exemption training for Jefferson County managed care staff
| 2012-08-17 | P | P | P | Medicaid Update article for Jefferson County
| 2012-05-18 | P | P | P | Letter to Chemung County Commissioner on mandatory implementation
| 2012-06-19 | P | P | P | Meet with Chemung County Commissioner and staff regarding implementation
| 8/30/12 9/20/12 10/1/12 10/16/12 | P | P | P | Maximus site visit for Chemung County
| 9/15/12 10/1/12 10/17/12 | P | P | P | Heads up letters to Chemung recipients
| 10/1/12 10/15/12 11/9/12 | P | P | P | Mandatory Stakeholder Meeting for Chemung County
| 9/30/12 11/10/12 | P | P | P | Medicaid Update article for Chemung County
| 2012-05-18 | P | P | P | Letter to St. Lawrence County Commissioner on mandatory implementation
| 2012-06-19 | P | P | P | Meet with St. Lawrence County Commissioner and staff regarding implementation
| 2012-08-09 | P | P | P | Maximus site visit for St. Lawrence County
| 2012-09-04 | P | P | P | Heads up letters to St. Lawrence recipients
| 2012-10-01 | P | P | P | Mandatory Stakeholder Meeting for St. Lawrence County
| 2012-09-30 | P | P | P | Max EB and Exemption training for St. Lawrence County managed care staff
| 2011-02-15 | P | P | P | Staff Training for St. Lawrence County
| 2012-08-17 | P | P | P | Medicaid Update article for St. Lawrence County
| 2012-05-18 | P | P | P | Letter to Lewis County Commissioners on mandatory implementation
| 2012-06-19 | P | P | P | Meet with Lewis County Commissioner and staff regarding implementation
| 2012-08-09 | P | P | P | Maximus site visit for Lewis County
| 2012-09-04 | P | P | P | Heads up letters to Lewis County recipients
| 2012-09-18 | P | P | P | Mandatory Stakeholder Meeting for Lewis County
| 2012-09-19 | P | P | P | Max EB and Exemption training for Lewis County managed care staff
| 2012-08-17 | P | P | P | Medicaid Update article for Lewis County
| 2012-05-18 | P | P | P | Letter to Warren County Commissioners on mandatory implementation
| 2012-06-19 | P | P | P | Meet with Warren County Commissioners and staff regarding implementation
| 2012-08-29 | P | P | P | Maximus site visit for Warren County
| 2012-09-04 | P | P | P | Heads up letters to Warren County recipients
| 2012-09-28 | P | P | P | Mandatory Stakeholder Meeting for Warren County
| 2012-08-17 | P | P | P | Medicaid Update article for Warren County
| 2012-11-19 | P | P | P | Statewide Mandatory Implementation Complete
BENEFIT CHANGE IMPLEMENTATION 7/1/12 - DENTAL
| 2011-11-28 | P | P | P | Managed Care Policy and Planning Meeting
| 2012-01-01 | P | P | P | Internal meeting to discuss provider network for dental and nursing home benefit
| 2012-01-09 | P | P | P | Managed Care Policy and Planning Meeting
| 2012-01-21 | P | P | P | Assess systems impact internally and discussed with EB/EC and WMS/eMedNY systems staff
| 2012-01-26 | P | P | P | Meet with LDSS to discuss changes
| 2012-02-08 | P | P | P | Draft Medicaid Update article
| 2012-02-10 | P | P | P | Internal meeting regarding dental MCO contracting issues
| 2012-02-16 | P | P | P | Managed Care Policy and Planning Meeting with MCOs
| 2012-02-24 | P | P | P | Meet with Health Plans to discuss proposal impact
| 2012-03-07 | P | P | P | Statewide webinar w/ stakeholders
| 2012-03-15 | P | P | P | Managed Care Policy and Planning Meeting with MCOs
| 2012-03-19 | P | P | P | Quarterly CMS advocate (access and capacity) meeting
| 2012-03-21 | P | P | P | Review final changes with LDSS staff
| 2012-04-03 | P | P | P | MMCARP meeting review of changes
| 2012-04-11 | P | P | P | Meet with enrollment broker to discuss proposal impact on educational materials
| 2012-04-15 | P | P | P | Notify MCO's of final contracting requirements and provide lists of non-contracted providers for dental benefit
| 2012-04-21 | P | P | P | Statewide webinar Q&A document posted to the web
| 2012-05-01 | P | P | P | Begin compilation and drafting of MMC Contract
| 2012-05-05 | P | P | P | Meet with Enrollment Broker Contractor to review materials changes made and training needs for call center and outreach staff
| 2012-05-10 | P | P | P | Meet with dental and orthodontia providers in NYC regarding transition
| 2012-05-10 | P | P | P | Submit request to eMedNY for SOB benefits change
| 2012-05-15 | P | P | P | Review and approve MCO subcontracts for dental benefit
| 2012-06-01 | P | P | P | Medicaid Update article released for dental benefit
| 2012-06-01 | P | P | P | Notify affected managed care recipients of dental benefit change
| 2012-06-12 | P | P | P | Webinar regarding dental/orthodontia implementation
| 2012-06-03 | P | P | P | Continue quarterly MMCARP meetings
| 2012-07-01 | P | P | P | Implementation
BENEFIT EXPANSION 11/1/12 - CDPAP
| 2012-01-30 | P | P | P | CDPAP Workgroup Meeting
| 2012-02-10 | P | P | P | CDPAP Orientation Meeting
| 2012-03-12 | P | P | P | CDPAP Workgroup Meeting
| 2012-05-01 | P | P | P | Begin compilation and drafting of MMC Contract
| 2012-05-02 | P | P | P | CDPAP Workgroup Meeting
| 2012-05-17 | P | P | P | Managed Care Policy and Planning Meeting with MCOs
| 2012-06-04 | P | P | P | Internal meeting to discuss programmatic issues
| 2012-06-14 | P | P | P | Managed Care Policy and Planning Meeting with MCOs
| 2012-06-30 | P | P | P | Provide contracting requirements to managed care plans for contracting
| 2012-07-01 | P | P | P | Submit request to eMedNY for SOB benefits change
| 2012-07-10 | P | P | P | Information released to CDPAP financial intermediaries
| 2012-07-15 | P | P | P | Information released to LDSS
| 2012-10-10 | P | P | P | Conference call with MCO's and FI's
| 2012-10-12 | P | P | P | Updated client information to LDSS/plans
| 2012-10-24 | P | P | P | Client specific information sent to LDSS/fiscal intermediaries
| 2012-07-17 | P | P | P | Meeting with trade associations
| 7/20/12 10/1/12 | P | P | P | Notice to beneficiaries affected regarding change
| 2012-08-16 | P | P | P | Managed Care Policy and Planning Meeting with MCOs
| 2012-09-11 | P | P | P | Managed Care Policy and Planning Meeting with MCOs
BENEFIT EXPANSION 10/1/12 - ORTHODONTIA
| 2012-02-21 | P | P | P | Meeting to discuss orthodontia transition
| 2012-03-12 | P | P | P | Conference call re: Medicaid orthodontia w/ SDOH and NYC prior approval staff
| 2012-03-27 | P | P | P | Orthodontia in MMC discussion
| 2012-04-15 | P | P | P | Submit 10/1/12 waiver changes to CMS
| 2012-04-20 | P | P | P | Meet with Health Plans to discuss proposal impact
| 2012-04-30 | P | P | P | Continue internal meetings regarding Orthodontia
| 2012-05-01 | P | P | P | Begin compilation and drafting of MMC Contract
| 2012-05-04 | P | P | P | Meet with SDOH dental and NYC- DOHMH to confirm meeting with providers
| 2012-05-08 | P | P | P | Meet with SDOH dental and NYC- DOHMH to confirm meeting with providers
| 2012-05-31 | P | P | P | Meet with dental and orthodontia providers in NYC regarding transition
| 2012-05-10 | P | P | P | Assess systems impact internally and discuss eMedNY systems staff
| 2012-05-17 | P | P | P | Managed Care Policy and Planning Meeting with MCOs
| 2012-05-20 | P | P | P | Deliver systems request for SOB benefits change to eMedNY for implementation
| 2012-06-12 | P | P | P | Webinar regarding dental/orthodontia implementation
| 2012-06-13 | P | P | P | Present 10/1/12 changes to MMCARP
| 2012-06-14 | P | P | P | Managed Care Policy and Planning Meeting with MCOs
| 2012-06-30 | P | P | P | Webinar Questions and Answers posted to web
| 2012-07-23 | P | P | P | Meeting to discuss orthodontia transition
| 2012-08-01 | P | P | P | Train local social services districts at NYPWA Conference
| 2012-08-16 | P | P | P | Managed Care Policy and Planning Meeting with MCOs
| 2012-08-23 | P | P | P | Webinar for clinical information
| 2012-08-30 | P | P | P | Webinar for plan/dental vendor contracting upstate
| 2012-09-01 | P | P | P | Distribute new materials to LDSS/other stakeholders
| 2012-09-01 | P | P | P | Medicaid Update article released for Orthodontia benefit
| 2012-09-11 | P | P | P | Managed Care Policy and Planning Meeting with MCOs
| 2012-09-15 | P | P | P | Outreach completed for providers and plans
| 9/17/12 11/1/12 | P | P | P | Meeting to discuss orthodontia transition
| 9/20/12 10/22/12 | P | P | P | Outreach completed for Fair Hearings staff
| 2012-10-01 | P | P | P | Implementation
1462 |  |  |  |  | Project Name: Long Term Care Insurance Proposals Division Lead: OLTC Team Lead: Mary Ann Anglin Add'l Staff: Dave Hoffman Description: Various strategies to promote use of private LTC insurance | 0 | Completed
PART A- CREATE ADDITIONAL PLAN OPTION FOR THE PARTNERSHIP FOR LTC
| 2011-04-25 | P | P | P | Confirm passage of budget language/ Draft 2-4-100 Proposal
| 2011-05-10 | P | P | P | Solicit comment and seek approval of the PLTC E -Board
| 6/1/11 7/1/11 | P | P | P | Draft State Plan Amendment
| 7/1/11 8/1/11 8/5/11 | P | P | P | Submit State Plan Amendment
| 2011-09-01 | P | P | P | Collaborate with SID for implementation
| 12/1/11 2/1/12 4/15/12 5/16/12 | P | P | P | Inform insurers and the public of new option
PART B STRATEGIES TO INCENT PURCHASE OF LTC INSURANCE
| 2011-07-01 | P | P | P | Review Federal Tax Law to assess implication for use of IRA/401k and other tools without penalty
| 8/1/11 9/1/11 10/1/11 12/1/11 1/1/11 | P | P | P | Develop Program Bill for 500 person demo of pre-tax LTC savings accounts
| 11/1/11 12/1/11 | P | P | P | Review legal implication of Use of Accelerated death benefit
| 2011-12-01 | P | P | P | Investigate possible use of reverse mortgage to pay for LTC insurance
| 2012-07-01 | P | P | P | Staff will incorporate information for the public regarding currently available strategies for financing long term care in any communication developed to announce changes to the PLTC from #1462 Part A when DFS regulations are approved.
PART C CREATION OF LTC INSURANCE MARKETING FUND AND CAMPAIGN
| 2011-05-15 | P | P | P | Review Marketing Fund Proposal with E-Board
| 2011-06-01 | 8 | 8 | 8 | Draft Marketing Fund Proposal
| 2011-08-01 | 8 | 8 | 8 | Present Proposal to E-Board for feedback
| 8/1/11 9/1/11 9/10/11 10/7/11 11/10/11 | P | P | P | Convene E-Board Marketing Sub-Committee
| 9/1/11 10/1/11 10/7/11 11/10/11 | P | P | P | Solicit commitment from insurers
| 10/1/11 11/1/11 11/10/11 | P | P | P | Convene LTC Insurance Marketing Partners
| 12/1/11 1/1/12 7/1/12 | P | P | P | Contract for campaign development | Ongoing
4155 |  |  |  |  | Project Name: Eliminate Long Term Care Assessment Center Funding Division Lead: Team Lead: Add'l Staff: Description: Eliminate Long Term Care Assessment Center funding. | -6 | Completed
| 2011-04-01 | P | P | P | LTC Assessment Center Funding Removed from the Budget
4153 |  |  |  |  | Project Name: Expanded Pharmacy Reimbursement Controls Division Lead: DOIT Team Lead: Mark Malone Add'l Staff: Steve Helmin, Mary Carroll, Kim Leonard Description: Implement contract to enhance controls on drug utilization. | -2.3 | Completed
ADMINISTRATIVE
| 2011-07-01 | P | P | P | Obtain approval for contract modification
| 2011-06-01 | P | P | P | CSC agreement to work at risk
| 2011-07-01 | P | P | P | HID agreement to work at risk
| 2011-07-01 | P | P | P | OSC approved contract amendment
SYSTEMS
| 2011-05-05 | P | P | P | Reinstate EP 0719/HID project
| 2011-05-05 | P | P | P | Identify interfaces with all contractors
| 6/1/11 6/30/11 7/18/11 | P | P | P | Requirements Definition: Functional Requirements Document
| 9/1/11 9/30/11 10/21/11 | P | P | P | System Detailed Design: Program Design Document
| 9/30/11 11/22/11 12/2/11 | P | P | P | Coding and Unit Test: Develop source code and systems documentation.
| 11/15/11 12/15/11 | P | P | P | Systems Integration Test: Proposed test cases to be exercised during SIT
| 11/16/11 12/16/11 | P | P | P | State approval of SIT
| 2011-12-23 | P | P | P | Regression, Performance and User Acceptance Testing
| 2011-12-29 | P | P | P | Implement EP0719 with enhanced clinical upfront editing function.
PROGRAM/CLINICAL
| 2011-05-01 | P | P | P | Identify clinical program requirements and timelines
| 2011-12-29 | P | P | P | Implement DURB frequency/quantity/duration recommendations
| 2011-12-29 | P | P | P | Implement MRT 15H: PA for Previously Exempt Classes
| 2011-12-29 | P | P | P | Implement PA length of 12 months
| 2011-12-29 | P | P | P | Implement MRT 15K: Limit Opioids to 4 scripts every 30 days
| 12/29/11 2/23/12 | P | P | P | Implement PDL drugs and clinical criteria
| 12/29/11 2/23/12 | P | P | P | Implement step-therapy
| 12/29/11 2/23/12 | P | P | P | Implement CDRP clinical criteria
4156 |  |  |  |  | Project Name: Mitigate Negative Provider Impacts from Implementing Nursing Home Rebasing Division Lead: DHCF Team Lead: Lana Earle Add'l Staff: Description: Initiate a series of actions designed to minimize the negative provider impacts associated with the implementation of rebasing methodology and implement new Statewide Pricing Methodology | -6.4 | Completed
REBASING AND REMEDIATION PLAN
| 2011-05-26 | P | P | P | Conduct Joint DOH Industry Association Webinar to Review Rebasing Mitigation Plan and Schedules for Rebasing Rates, and Implementation of NH Pricing Methodology
| 2011-06-29 | P | P | P | Conduct Joint DOH Industry Association Webinar on Technical Aspects of Rebasing Rates
| 2011-06-21 | P | P | P | Amend SPA 11-03 Eliminate Case Mix Adjustments for January 2011 and July 2011 (SPA approved 6/21/11)
| 2011-06-09 | P | P | P | Submit SPA 11-60 Uniform Rate Reduction
| 2011-06-17 | P | P | P | Submit SPA to eliminate 2011 Trend Factor effective April 1, 2011 (SPA 11-65)
| 2011-06-30 | P | P | P | Submit SPA 11-52 to Eliminate 2010 and 2011 FD Payments
| On or before 6/27/11 | P | P | P | Receive approval of $210 million nursing home cap SPA #09-50 (May 6, 2011) Submit SPA #11-41 and receive approval (June 15, 2011) to implement mitigation payments, develop recoupment percentages with industry associations
| On or before 6/27/11 | P | P | P | Upon approval of SPA #09-50 and #11-41 process April 1, 2009, May 1, 2009, July 1, 2009, January 1, 2010, April 1, 2010 and January 1, 2011 rates, process May 1, 2011 and June 1, 2011 mitigation payments, process 2008 cash receipts assessment reconciliation, See May 26, 2011 Webinar, issue Dear Admin Letter
| 2011-10-21 | P | P | P | Prepare following rates for DOB approval: July 1, 2010 (case mix adjustments) January 1, 2011 (2011 capital rates, trend factor increase for Jan Feb Mar 2011), April 1, 2011 eliminate Trend Factor (requires CMS approval), May 1, 2011, June 1, 2011 and July 7, 2011 (prescription drug carve out) See May 26, 2011 Webinar, Issue Dear Admin Letter
| 2011-10-21 | P | P | P | Prepare following rates for DOB approval: April 1, 2011, May 1, 2011 June 1, 2011 and July 1, 2011 to implement uniform rate reduction (requires CMS approval) See May 26, 2011 Webinar, Issue Dear Admin Letter
| 10/15/11 11/15/11 | P | P | P | Upon DOB approval, process following rates for eMedNY: July 1, 2010 (case mix adjustments) January 1, 2011 (2011 capital rates, trend factor increase for Jan Feb Mar 2011), April 1, 2011 eliminate Trend Factor (requires CMS approval), May 1, 2011, June 1, 2011 and July 7, 2011 (prescription drug carve out) See May 26, 2011 Webinar, Issue Dear Admin Letter
| 10/30/11 11/15/11 | P | P | P | Upon DOB approval, process following rates for eMedNY: April 1, 2011, May 1, 2011 June 1, 2011 and July 1, 2011 to implement uniform rate reduction (requires CMS approval) See May 26, 2011 Webinar, Issue Dear Admin Letter
| 8/28/11 9/1/11 | T | T | T | Industry Associations develop NH pricing quality rate setting methodology and review with Department, develop regulations, circulate initial rates. On 9/1/11, Associations indicated, that despite their hard work and concerted efforts, they were unable to reach consensus on all the elements of a new pricing methodology. | Pricing Methodology
| 2011-09-27 | P | P | P | DOH meet with Associations to discuss their efforts - continue to collaborate on development of new pricing methodology.
| 10/19/11 11/1/11 | P | P | P | Department model, review, and discuss pricing methodology options
| 2011-12-20 | P | P | P | On or before noon on 12/20 send Federal Public Notice to DOS for publishing by year end
| 2011-12-20 | P | P | P | Update CMS
| 2011-12-20 | P | P | P | Hold NH Industry webinar on pricing
| 12/31/11 1/20/12 1/27/12 | P | P | P | Submit draft SPA to CMS
| 2012-01-27 | P | P | P | Quality Measures Work Group Meeting
| 2012-02-07 | P | P | P | Meeting with CMS to review SPA docs
| 1/6/12 1/27/12 2/24/12 3/2/12 | P | P | P | Submit draft regulations to Associations for Review
| 2012-03-28 | P | P | P | Submit final SPA to CMS
| 2012-04-04 | P | P | P | Post Informational Pricing Rate Sheets to HCS
| 2012-04-04 | P | P | P | Webinar - Informational Pricing Rate Sheets Enacted Budget Update
| 3/12/12 4/12/12 5/2/12 | P | P | P | Follow up Quality Measures Work Group Meeting
| 2012-04-13 | P | P | P | Finalize NH regulations with Department of State
| 4/1/12 5/1/12 6/1/12 6/21/12 | P | P | P | CMS Approval
| 2012-06-29 | P | P | P | Secure DOB Approval and process and post rates
4648 |  |  |  |  | TRANSITION FPBP FROM 1115 WAIVER TO STATE PLAN |  | Completed
PART 1
POLICY AND PROCEDURE
| 2011-06-01 | P | P | P | Complete preliminary review of policy issues
| 2012-10-23 | P | P | P | Draft GIS with instructions for LDSS prior to ADM release
| 2012-10-23 | P | P | P | Submit draft GIS for clearance
| 3/1/12 4/1/12 8/1/12 9/15/12 9/28/12 11/1/12 11/12/12 | P | P | P | Submit draft Administrative Directive (ADM) for clearance
| 4/1/12 8/1/12 10/1/12 11/30/12 12/31/12 3/1/13 5/1/13 7/1/13 9/2/13 12/31/13 | P | P | P | Take necessary steps to discontinue FPBP in 1115 Waiver - contingent on SPA 12-12 approval.
| 6/1/12 10/1/12 11/30/12 12/31/12 2/11/13 2/25/13 | P | P | P | Issue ADM - issued in draft to LDSS
STATE PLAN
| 2011-05-05 | P | P | P | Submit draft SPA 11-40 for DOH clearance
| 2011-05-13 | P | P | P | Finalize and submit SPA 11-40 to HCRA Operations and Financial Analysis
| 2012-11-01 | P | P | P | Implement changes
PART 2
PRESUMPTIVE ELIGIBILITY FOR FPBP
POLICY AND PROCEDURE
| 2011-06-01 | P | P | P | Complete preliminary review of policy issues
| 5/1/12 6/1/12 | P | P | P | Determine necessary modifications of materials (MOU, regs, etc) to reflect centralization of FPBP applicaton processing.
| 7/1/11 12/1/11 1/1/12 3/1/12 5/1/12 6/1/12 | P | P | P | Develop and submit Regulations
| 1/1/12 2/1/12 7/1/12 10/1/12 10/31/12 | P | P | P | Develop paper-based training for FPBP providers
| 1/1/12 2/1/12 3/15/12 | P | P | P | Modify Memorandum of Understanding with FPBP providers and for clearance
| 2/1/12 2/21/12 3/15/12 | P | P | P | Submit draft letter to FPBP providers for clearance
| 2012-04-01 | P | P | P | Develop PE screening form for providers
| 4/1/12 8/1/12 9/15/12 9/28/12 11/1/12 11/12/12 12/31/12 | P | P | P | Submit draft Administrative Directive (ADM) for clearance
| 4/1/12 8/1/12 9/15/12 9/28/12 10/26/12 | P | P | P | Mail letters and MOU to FPBP providers
| TBD | 8 | 8 | 8 | Update online training - pending training contract
| 6/1/12 10/1/12 11/30/12 12/31/12 2/11/13 2/25/13 | P | P | P | Issue ADM - issued in draft to LDSS
STATE PLAN
| 2011-05-05 | P | P | P | Submit draft SPA 11-40 for DOH clearance
| 2011-05-13 | P | P | P | Finalize and submit SPA 11-40 to HCRA Operations and Financial Analysis
WEBSITE
| 6/1/12 10/1/12 11/30/12 1/8/13 3/1/13 5/1/13 6/21/13 | P | P | P | Post information about presumptive eligiblitiy for Family Planning services
| 11/1/12 12/10/12 12/14/12 | P | P | P | Implement changes
PART 3
AUTOMATE ENROLLMENT OF POST-PARTUM WOMEN INTO FAMILY PLANNING BENEFIT PROGRAM OR FAMILY PLANNING EXTENSION PROGRAM
POLICY AND PROCEDURE
| 2011-06-01 | P | P | P | Complete preliminary review of policy issues
| 4/1/12 8/1/12 9/15/12 9/28/12 11/1/12 11/12/12 | P | P | P | Submit draft ADM for clearance
| 6/1/12 10/1/12 11/30/12 12/31/12 2/11/13 2/25/13 | P | P | P | Issue ADM - issued in draft to LDSS
| 4/1/12 8/1/12 9/15/12 9/28/12 | P | P | P | Coordinate with Bureau of Maternal and Child Health to draft and clear Medicaid Update article for Family Planning Providers
| 2012-04-01 | 8 | 8 | 8 | Coordinate with Bureau of Maternal and Child Health to draft letter to Family Planning providers
| 6/1/2012 10/1/12 11/9/12 | P | P | P | Issue Medicaid Update article for Family Planning Providers
| 2012-06-01 | 8 | 8 | 8 | Mail letter to FPBP providers
| 2012-11-01 | P | P | P | Implement changes upstate
| 3/1/13 7/1/13 | P | P | P | Implement changes in NYC
SYSTEM UPDATES - DOWNSTATE
| 2012-08-23 | P | P | P | eMedNY release of EP 1618
WMS PRESUMPTIVE FPBP
| 2012-01-31 | P | P | P | Submit System Change Request Form
| 6/1/11 7/1/11 9/1/11 2/14/12 3/1/12 | P | P | P | Finalize system change requirements
| 6/15/11 7/15/11 10/1/11 2/7/12 3/2/12 | P | P | P | Finalize System Action Request
| 7/1/12 9/5/12 | P | P | P | Development/coding changes
| 4/23/12 8/20/12 9/14/12 | P | P | P | Unit testing Begins
| 6/18/12 8/20/12 10/15/12 | P | P | P | User Acceptance
| 6/18/12 10/20/12 | P | P | P | Migrate system change
SYSTEM UPDATES
CHANGES TO INCLUDE RETROACTIVE COVERAGE IN FPBP
| 2011-04-01 | P | P | P | Submit system change request
| 7/1/12 9/5/12 | P | P | P | Development/coding changes
| 4/23/12 8/20/12 9/14/12 | P | P | P | Unit testing Begins
| 6/18/12 8/20/12 10/15/12 10/10/12 | P | P | P | User Acceptance
| 6/18/12 10/20/12 | P | P | P | Migrate system change
SYSTEM UPDATES
CHANGES TO PROVIDE 24 MONTH FAMILY PLANNING EXPANSION
| 2011-04-01 | P | P | P | Submit system change request
| 7/1/12 9/5/12 | P | P | P | Development/coding changes
| 4/23/12 8/20/12 9/14/12 | P | P | P | Unit testing Begins
| 6/18/12 8/20/12 2/15/13 6/15/13 | P | P | P | User Acceptance
| 6/18/12 2/17/13 6/17/13 | P | P | P | Migrate change (Migration is dependent on eMedNY's ability to accept a new coverage code)
SYSTEM UPDATES - UPSTATE
WMS PRESUMPTIVE FPBP
| 2011-04-11 | P | P | P | Submit System Change Request Form
| 6/1/11 7/1/11 9/1/11 2/14/12 3/1/12 | P | P | P | Finalize system change requirements
| 6/15/11 7/15/11 10/1/11 2/7/12 3/1/12 | P | P | P | Finalize System Action Request
| 7/1/12 9/5/12 | P | P | P | Development/coding changes
| 4/23/12 8/20/12 9/14/12 | P | P | P | Unit testing Begins
| 6/18/12 8/20/12 10/15/12 | P | P | P | User Acceptance
| 6/18/12 10/20/12 | P | P | P | Migrate system change
SYSTEM UPDATES
CHANGES TO INCLUDE RETROACTIVE COVERAGE IN FPBP
| 2011-04-01 | P | P | P | Submit system change request
| 7/1/12 9/5/12 | P | P | P | Development/coding changes
| 4/23/12 8/20/12 9/14/12 | P | P | P | Unit testing Begins
| 6/18/12 8/20/12 10/15/12 | P | P | P | User Acceptance
| 6/18/12 10/20/12 | P | P | P | Migrate system change
SYSTEM UPDATES
CHANGES TO PROVIDE 24 MONTH FAMILY PLANNING EXPANSION
| 2011-04-01 | P | P | P | Submit system change request
| 7/1/12 9/5/12 | P | P | P | Development/coding changes
|  | P | P | P
| 4/23/12 8/20/12 9/14/12 | P | P | P | Unit testing Begins
| 6/18/12 8/20/12 10/15/12 | P | P | P | User Acceptance
| 6/18/12 10/20/12 | P | P | P | Migrate change (Migration is dependent on eMedNY's ability to accept a new coverage code)
4655 |  |  |  |  | Project Name: Expand Downstate FQHC Region Division Lead: DOH / DHCF Team Lead: Janet Baggetta Add'l Staff: Phyllis Casale, Rick Nair Description: Expand the downstate region to increase reimbursment to certain Federally Qualified Health Centers (FQHC) that serve residents of this region. | 2.4 | Completed
| 2011-04-27 | P | P | P | Submit FPN.
| 2011-04-15 | P | P | P | Determine if regulations are needed.
| 2011-04-18 | P | P | P | Work with BHOFA staff to prepare necessary State Plan Amendment materials.
| 2011-04-20 | P | P | P | Submit State Plan Amendment 11-59.
| 2011-04-29 | P | P | P | Calculate revised FQHC Rate Sheets
| 2011-05-05 | P | P | P | Receive Medicaid Managed Care impact for Budget Package for wrap payment
| 5/5/11 5/20/11 | P | P | P | Finalize Budget Package with revised FQHC/wrap Rates. Submit for Executive approval.
| 5/5/11 5/20/11 | P | P | P | Submit Draft Budget package/rates to DoB for initial review
| 5/26/11 7/1/11 7/20/11 | P | P | P | Receive Budget Package Executive approval
| 7/20/11 8/25/11 | P | P | P | Receive CMS Approval
| 7/21/11 8/26/11 | P | P | P | Submit Final Budget package/rates to DOB for approval
| 7/28/11 9/6/11 | P | P | P | Receive DOB Approval
| 7/29/11 9/8/11 | P | P | P | Transmit revised FQHC rates and other required data to eMedNY.
4651-A |  |  |  |  | Project Name: Global Spending Cap Division Lead: John Ulberg DFRS Team Lead: Mark Shutts Add'l Staff: Ann Foster Description: Periodically monitors Medicaid spending and implements Savings Allocation Plans (if needed), which are designed to bring projected spending in line with a cap (aka Global Spending Cap) of approximately 4% growth per year. | 0 | Completed
| 2011-03-30 | P | P | P | Issue a Federal Public Notice
| 2011-03-30 | P | P | P | Consulted within the Department and with the Division of Budget (DOB) to develop a model that will track Medicaid expenditures by industry sector (i.e., inpatient outpatient, freestanding clinic, nursing homes, etc) that make up and coincide with the approximately $15 billion State spending cap.
| 2011-04-01 | P | P | P | Map data warehouse extraction using MARS detcat codes to the same sectors agreed upon with DOB to gain confidence that monthly extractions are appropriately being input into the model.
| 2011-04-01 | P | P | P | Model monthly cash flow for online (claims) expenditures using historical experience (2009-10) adjusted for known anomalies (ie. Retroactive rate packages) within each sector.
| 2011-04-05 | P | P | P | Test receipt of data from data warehouse and the input/output of the established model.
| 2011-04-11 | P | P | P | Model monthly cash flow for offline expenditures in consultation with DOB's internal cash flow attributed to each sector.
| 2011-04-15 | P | P | P | Model monthly cash flow for each MRT proposal by industry sector.
| 2011-04-15 | P | P | P | Combine monthly cash flows for online, offline and MRT proposals into one model.
| 2011-04-19 | P | P | P | Brief DOH Executive Staff on cap reporting documents.
| 2011-04-22 | P | P | P | Review and get agreement upon a format for reporting monthly. Discussion will include the format of the cash flow and any accompanying charts.
| 2011-04-22 | P | P | P | Discuss and get agreement on any additional/supplemental reports to be posted.
| 2011-05-05 | P | P | P | Brief the Hospital Associations regarding data sources and calculations used in the development of the Medicaid global spending cap cash flow.
| 2011-05-16 | P | P | P | Receive April's data feed (online and offline) and and input into the model.
| 2011-05-23 | P | P | P | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 5/16/11 5/26/11 6/2/11 | P | P | P | Brief Legislative staff on cap reporting documents.
| 5/27/11 5/31/11 6/3/11 | P | P | P | Post reports to the website.
| 2011-06-16 | P | P | P | Receive May's data feed (online and offline) and and input into the model.
| 2011-06-24 | P | P | P | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 6/30/11 7/8/11 | P | P | P | Post reports to the website.
| 2011-07-15 | P | P | P | Receive June's data feed (online and offline) and and input into the model.
| 2011-07-22 | P | P | P | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 7/29/11 8/5/11 | P | P | P | Post reports to the website.
| 2011-08-15 | P | P | P | Receive July's data feed (online and offline) and and input into the model.
| 2011-08-22 | P | P | P | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 2011-09-12 | P | P | P | Post reports to the website.
| 2011-09-16 | P | P | P | Receive August's data feed (online and offline) and and input into the model.
| 2011-09-23 | P | P | P | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 9/30/11 10/5/11 | P | P | P | Post reports to the website.
| 2011-10-15 | P | P | P | Receive September's data feed (online and offline) and and input into the model.
| 2011-10-22 | P | P | P | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 10/31/11 11/14/11 | P | P | P | Post reports to the website.
| 2011-11-16 | P | P | P | Receive October's data feed (online and offline) and and input into the model.
| 2011-11-23 | P | P | P | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 11/30/11 12/2/11 12/14/11 | P | P | P | Post reports to the website.
| 2011-12-16 | P | P | P | Receive November's data feed (online and offline) and and input into the model.
| 2011-12-23 | P | P | P | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 2011-12-30 | 8 | 8 | 8 | Post reports to the website.
| 2012-01-16 | 8 | 8 | 8 | Receive December's data feed (online and offline) and and input into the model.
| 2012-01-23 | 8 | 8 | 8 | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 2012-01-31 | 8 | 8 | 8 | Post reports to the website.
| 2012-02-15 | 8 | 8 | 8 | Receive January's data feed (online and offline) and and input into the model.
| 2012-02-22 | 8 | 8 | 8 | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 2012-02-29 | 8 | 8 | 8 | Post reports to the website.
| 2012-03-16 | 8 | 8 | 8 | Receive February's data feed (online and offline) and and input into the model.
| 2012-03-23 | 8 | 8 | 8 | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 2012-03-30 | 8 | 8 | 8 | Post reports to the website.
| 2012-04-16 | 8 | 8 | 8 | Receive March's data feed (online and offline) and and input into the model.
| 2012-04-23 | 8 | 8 | 8 | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 2012-04-30 | 8 | 8 | 8 | Post reports to the website.
|  | 8 | 8 | 8 | SFY 12-13 Monthly reporting will fall on the same monthly schedule as 2011-12.
4651-B |  |  |  |  | Project Name: 2% Across the Board Reductions Division Lead: John Ulberg DFRS Team Lead: Shaneeva Norbi Add'l Staff: Stephanie Fargnoli, Phil Mossman, Ann Heilmann Description: This proposal implements a 2% Across the Board Reduction to most Medicaid payments | -345 | Completed
GENERAL PROCESS FOR IMPLEMENTATION
| 2011-03-30 | P | P | P | Publish the Federal Public Notice based on the Executive Budget language.
| 2011-04-27 | P | P | P | Publish a clarifying Federal Public Notice based on the Enacted Budget and negotiated alternatives by sector.
| 2011-05-31 | P | P | P | Finalize list of included/excluded services for purposes of the State Plan Amendment
| 2011-04-21 | P | P | P | Submit a draft of the Hospital Inpatient State Plan Amendment to CMS for the across the board actions
| 2011-08-18 | P | P | P | Receive CMS Approval of Hospital Inpatient State Plan Amendment
| 6/3/11 6/13/11 | P | P | P | Submit a draft of the Outpatient services State Plan Amendment to CMS and if needed any plans for alternatives identified by the sectors (several sectors are included in this state plan amendment, please see list below where asterisked *).
| 9/19/11 09/30/11 10/28/11 11/14/11 12/9/11 12/16/11 | P | P | P | Receive CMS Approval of Outpatient Services State Plan Amendment. Date may need to be modified dependent on CMS. (several sectors are included in this state plan amendment please see list below where asterisked*).
PROVIDER NOTIFICATION STRATEGY
| 6/8/11 6/15/11 9/1/11 09/19/11 09/28/11 10/20/11 | P | P | P | Develop language for provider notification (i.e Medicaid update, email blast, website informational documents etc.)
| 2011-10-24 | P | P | P | Initiate development and design of DOH 2% website
| 2011-10-28 | P | P | P | Finalize language for provider notification
| 6/13/11 6/21/11 09/15/11 11/3/11 | P | P | P | Notify provider communities through email blasts, Medicaid Update, eMedNY website etc...
| 2011-11-03 | P | P | P | 2% Website goes live, post all necessary materials
2% ATB EVOLUTION PROJECT
| 6/20/11 6/27/11 | P | P | P | Submit draft Evolution Project Request for changes that will be made to the system to effectuate the inclusions/exclusions to the across the board reduction.
| 10/1/11 11/1/11 11/3/11 | P | P | P | Implementation of Evolution Project Request for changes that will be made to the system to effectuate the inclusions/exclusions to the across the board reduction moving forward
| 2011-10-19 | P | P | P | Begin retroactive adjustment calculation back to the effective date according to law for the across the board reduction- (effective for dates of service on and after April 1, 2011)
| 2011-11-03 | P | P | P | Prospective implementation of 2% reduction begins
| 2011-11-14 | P | P | P | Discuss and finalize set up of retroactive adjustment recoupment strategy
| 2011-11-21 | P | P | P | Release provider notification update on retroactive adjustment recoupment (i.e Medicaid update, website update etc.)
PATH OF PARTICIPATION BY SECTOR (ALTERNATIVE PROPOSAL ACCEPTED OR REJECTED)
INPATIENT
|  | P | P | P | Industry did not propose an alternative to the across the board, therefore 2% reduction applies.
| 2011-04-21 | P | P | P | Submit SPA as a draft to CMS ( Hospital Inpatient)
| 9/19/11 09/30/11 10/28/11 11/14/11 12/9/11 12/16/11 | P | P | P | CMS Approval
| 09/20/11 09/30/11 11/1/11 11/3/11 | P | P | P | Implemented savings being realized prospectively as of November 3
HOSPITAL BASED OUTPATIENT
|  | P | P | P | Industry did not propose an alternative to the across the board, therefore 2% reduction applies.
| 6/3/11 6/13/11 | P | P | P | Submit SPA as a draft to CMS (Outpatient Services)
| 9/19/11 09/30/11 10/28/11 11/14/11 12/9/11 12/16/11 | P | P | P | CMS Approval
| 09/20/11 09/30/11 11/1/11 11/3/11 | P | P | P | Implemented savings being realized prospectively
FREESTANDING CLINIC
|  | P | P | P | Alternative proposal accepted to generate commensurate savings through a reduction to the APG base rates, which will occur only after the unpaid APG investment is approved by CMS
| 6/3/11 6/13/11 | P | P | P | Submit SPA as a draft to CMS (Outpatient Services)
| 9/19/11 09/30/11 10/28/11 11/14/11 12/9/11 12/16/11 | P | P | P | CMS Approval
| 09/20/11 09/30/11 11/1/11 11/3/11 | P | P | P | IMPLEMENTED savings being realized prospectively
IN-STATE NURSING HOME
| 2011-03-31 | P | P | P | Alternative proposal accepted to generate commensurate savings through an increase of the cash assessment accepted.
| 2011-03-31 | P | P | P | Complete provider impact
| 2011-03-31 | P | P | P | DOB approval
| 2011-04-15 | P | P | P | Discuss and finalize set up of system change with the Office of Pool Administrator (OPA)
| 2011-04-18 | P | P | P | OPA system updated to accept new reports with increased cash assessment
| 2011-04-28 | P | P | P | Notify provider communities through dear administrator letter
| 2011-05-16 | P | P | P | First receipt of increase
| 2011-05-17 | P | P | P | Implemented savings being realized
OUT OF STATE NURSING HOME
2% reduction applies.
| 2011-08-05 | P | P | P | Submit SPA 11-49 as a draft to CMS
| 9/19/11 09/30/11 10/28/11 11/14/11 | P | P | P | CMS Approval (received approval 9/23/2011)
| 9/20/11 9/30/11 11/3/11 | P | P | P | Implemented savings being realized (waiting for the NI SPA approval for implementation to commence)
PERSONAL CARE
|  | P | P | P | Industry did not propose an alternative to the across the board, therefore 2% reduction applies.
| 6/3/11 6/13/11 | P | P | P | Submit SPA as a draft to CMS (Outpatient Services)
| 9/19/11 9/30/11 10/28/11 11/14/11 12/9/11 12/16/11 | P | P | P | CMS Approval
| 9/20/11 9/30/11 11/1/11 11/3/11 | P | P | P | Implemented savings being realized prospectively
HOME HEALTH
|  | P | P | P | CHHA- Industry proposal rejected, therefore 2% reduction applies
| 6/3/11 6/13/11 | P | P | P | Submit SPA as a draft to CMS (Outpatient Services)
| 9/19/11 9/30/11 10/28/11 11/14/11 12/9/11 12/16/11 | P | P | P | CMS Approval
| 9/20/11 9/30/11 11/1/11 11/3/11 | P | P | P | Implemented savings being realized prospectively
|  | P | P | P | LTHHCP- Alternative proposal accepted to generate commensurate savings through an increase of the cash assessment accepted.
| 2011-03-31 | P | P | P | Complete provider impact
| 2011-03-31 | P | P | P | DOB approval
| 2011-04-15 | P | P | P | Discuss and finalize set up of system change with the Office of Pool Administrator (OPA)
| 2011-04-18 | P | P | P | OPA system updated to accept new reports with increased cash assessment
| 2011-06-01 | P | P | P | Notify provider communities through dear administrator letter
| 2011-06-20 | P | P | P | First receipt of increase
|  | P | P | P | Implemented savings being realized
HOME NURSING
|  | P | P | P | Industry did not propose an alternative to the across the board, therefore 2% reduction applies.
| 6/3/11 6/13/11 | P | P | P | Submit SPA as a draft to CMS (Outpatient Services)
| 9/19/11 9/30/11 10/28/11 11/14/11 12/9/11 12/16/11 |  |  |  | CMS Approval
| 09/20/11 09/30/11 11/1/11 11/3/11 | P | P | P | Implemented savings being realized prospectively
ASSISTED LIVING PROGRAMS
|  | P | P | P | Alternative proposal accepted to generate commensurate savings through a reduction of the state only funding of 'EQUAL'.
|  | P | P | P | Official letter from industry
| 2011-06-28 | P | P | P | Complete impact by provider
|  | P | P | P | Discuss and finalize set up of system change
| 2011-07-22 | P | P | P | Finalize Pay List Revision
| 2011-08-22 | P | P | P | Implement reduction of EQUAL checks
|  | P | P | P | Implemented savings being realized
MANAGED LONG TERM CARE
|  | P | P | P | Alternative proposal accepted to generate commensurate savings through reducing premium levels
| 10/28/11 11/30/11 12/14/11 | P | P | P | Calculate revised premium rates
| 11/4/11 12/2/11 12/16/11 | P | P | P | Submit rates to DOB for approval
| 11/18/11 12/10/11 12/24/11 | P | P | P | DOB approval
| 12/2/11 12/10/11 12/24/11 | P | P | P | Mercer rate certification letter
| 12/9/11 12/15/11 12/29/11 | 8 | 8 | 8 | Send rates to CMS for approval
| 12/16/11 1/5/12 1/19/12 | 8 | 8 | 8 | Mail/post rates after CMS approval
|  | 8 | 8 | 8 | Implemented savings being realized
MANAGED CARE / FHP
|  | P | P | P | Alternative proposal accepted to generate commensurate savings through reducing premium levels
For further information on the implementation of the Managed Care alternative to generate savings through reducing premium levels please see MRT project plan # 6
| 2011-09-01 |  |  |  | Calculate revised premium rates
| 8/1/11 8/15/11 8/25/11 9/1/11 |  |  |  | Implement all changes to rates effective 4/1/11 (marketing, trend reduction, surplus reduction, inpatient changes, etc) and add pharmacy to 10/1/11 rates
| 8/15/11 8/25/11 9/1/11 |  |  |  | Submit rates to DOB for approval
| 2011-09-12 |  |  |  | DOB approval
| 2011-09-26 |  |  |  | Mercer rate certification letter
| 2011-10-24 |  |  |  | Mail/post rates after CMS approval and all needed changes have been made to model contract and 115 waiver (see MRT #1458)
|  | P | P | P | Implemented savings being realized
PHARMACY
|  | P | P | P | Interactions amongst existing proposals and other pharmacy programs will generate commensurate savings, resulting in 1% or less in ATB cuts.
| 6/3/11 6/13/11 | P | P | P | Submit SPA as a draft to CMS (Outpatient Services)
| 9/19/11 09/30/11 10/28/11 11/14/11 12/9/11 | P | P | P | CMS Approval
| 7/1/11 8/1/11 9/1/11 9/30/11 11/1/11 11/3/11 | P | P | P | Program and Data Analysis staff will identify the retroactive adjustment for period April 1, 2011 through ATB reduction implementation date.
| 7/1/11 8/1/11 9/1/11 9/30/11 11/1/11 11/3/11 | P | P | P | Retroactive amounts will be prorated and added to prospective adjustments over the remainder of the SFY.
|  | P | P | P | Adjustments will be applied by CSC and will appear as a separate line item on invoices for the remainder of the SFY.
| 9/20/11 9/30/11 11/1/11 11/3/11 | P | P | P | Implemented savings being realized prospectively as of November 3
PHYSICIANS
|  | P | P | P | Office place of service - Alternative proposal accepted to generate commensurate savings for office based physicians through an reduction in radiology fees.
| 2011-07-01 | P | P | P | Fee reduction processed
|  | P | P | P | Implemented savings being realized
|  | P | P | P | All other places of service*- Industry did not propose an alternative to the across the board, therefore 2% reduction applies.
| 6/3/11 6/13/11 | P | P | P | Submit SPA as a draft to CMS (Outpatient Services)
| 9/19/11 9/30/11 10/28/11 11/14/11 12/9/11 12/16/11 | P | P | P | CMS Approval
| 9/20/11 9/30/11 11/1/11 11/3/11 | P | P | P | Implemented savings being realized prospectively
OTHER SERVICES (Dental, Eye/X-ray, etc.)
|  | P | P | P | Office place of service - Alternative proposal accepted to generate commensurate savings for office based physicians through an reduction in radiology fees.
| 2011-07-01 | P | P | P | Fee reduction processed
|  | P | P | P | Implemented savings being realized
|  | P | P | P | All other places of service*-Industry did not propose an alternative to the across the board, therefore 2% reduction applies.
| 6/3/11 6/13/11 | P | P | P | Submit SPA as a draft to CMS (Outpatient Services)
| 9/19/11 9/30/11 10/28/11 11/14/11 12/9/11 12/16/11 | P | P | P | CMS Approval
| 9/20/11 9/30/11 11/1/11 11/3/11 | P | P | P | Implemented savings being realized prospectively
METHADONE MAINTENANCE TREATMENT PROGRAMS
|  | P | P | P | 2% reduction applies.
| 6/3/11 6/13/11 | P | P | P | Submit SPA as a draft to CMS (Outpatient Services)
| 9/19/11 9/30/11 10/28/11 11/14/11 12/9/11 12/16/11 | P | P | P | CMS Approval
| 09/20/11 09/30/11 11/1/11 11/3/11 | P | P | P | Implemented savings being realized prospectively
4652 |  |  |  |  | Project Name: Reform Personal Care Services Program in NYC Division Lead: OLTC/DHCBS Team Lead: Margaret Willard Add'l Staff: Linda Gowdy Description: | -57 | Completed
STATE PLAN AMENDMENT & REGULATORY PROCESS
| 2011-03-17 | P | P | P | Review SPA, Statute and regulations related to the PCSP
| 2011-04-01 | P | P | P | Make appropriate changes as needed to SPA, Statute and/or Regulations with DLA direction. Follow existing process for changes.
| 2011-04-19 | P | P | P | Change in regulation 18 NYCRR 505.14 and 505.28 initiated
| 2011-05-02 | P | P | P | Preliminary review of draft regulations by DLA
| 5/20/11 6/17/11 8/5/11 | P | P | P | Necessary changes made to draft regulations based on DLA recommendations
| 5/13/11 5/23/11 6/22/11 8/10/11 | P | P | P | Internal administrative review initiated after DLA preliminary review completed
| 5/25/11 7/6/11 8/12/11 | P | P | P | Internal review completed, package advanced to Executive Chamber
| 6/8/11 7/20/11 8/26/11 10/19/11 | P | P | P | Publication in State Register
GIS / FAIR HEARINGS
| 2011-04-28 | P | P | P | Draft of GIS limiting Level 1 services
| 2011-04-28 | P | P | P | GIS enters Internal Clearance Process
| 2011-04-13 | P | P | P | Conference between DOH and OTDA re: Fair Hearing rights
| 2011-04-28 | P | P | P | Draft of FH reduction notice to be prepared
| 2011-05-02 | P | P | P | Create FH notice as ana attachment to GIS
| 5/20/11 6/4/11 | P | P | P | GIS completed internal clearance process
| 5/13/11 5/24/11 6/4/11 | P | P | P | Distribution of GIS to Local Districts
| 2011-05-06 | P | P | P | Conference call with HRA staff to discuss CCO model
| 2011-05-09 | P | P | P | Formulate questions to be used by HRA in discussions with HHC
| 2011-05-12 | P | P | P | Initiate internal clearance of OLTC questions for HRAs use
| 5/19/11 6/10/11 | P | P | P | Share questions and concerns with HRA for consideration and response
| 2011-06-15 | P | P | P | Collaborate with HRA and HHC in establishing criteria for a care coordination model for high needs PCS recipients.
| 4/1/11 6/6/11 6/15/11 | P | P | P | Collaborate with HRA in developing and approving the process for moving low need CHHA cases to the PCSP
| 9/1/11 11/15/11 12/31/11 2/15/12 3/8/12 4/1/12 | P | P | P | Develop and issue policy directives/standards for local districts
| 9/1/11 12/15/11 2/15/12 3/8/12 4/1/12 | P | P | P | Provide ongoing training and monitoring of the PCSP as required
4655 |  |  |  |  | Project Name: Expand Downstate FQHC Region Division Lead: DOH / DHCF Team Lead: Janet Baggetta Add'l Staff: Phyllis Casale, Rick Nair Description: Expand the downstate region to increase reimbursment to certain Federally Qualified Health Centers (FQHC) that serve residents of this region. | 2.4 | Completed
| 2011-04-27 | P | P | P | Submit FPN.
| 2011-04-15 | P | P | P | Determine if regulations are needed.
| 2011-04-18 | P | P | P | Work with BHOFA staff to prepare necessary State Plan Amendment materials.
| 2011-04-20 | P | P | P | Submit State Plan Amendment 11-59.
| 2011-04-29 | P | P | P | Calculate revised FQHC Rate Sheets
| 2011-05-05 | P | P | P | Receive Medicaid Managed Care impact for Budget Package for wrap payment
| 5/5/11 5/20/11 | P | P | P | Finalize Budget Package with revised FQHC/wrap Rates. Submit for Executive approval.
| 5/5/2011 5/20/11 | P | P | P | Submit Draft Budget package/rates to DoB for initial review
| 5/26/11 7/1/11 7/20/11 | P | P | P | Receive Budget Package Executive approval
| 7/20/11 8/25/11 | P | P | P | Receive CMS Approval
| 7/21/11 8/26/11 | P | P | P | Submit Final Budget package/rates to DOB for approval
| 7/28/11 9/6/11 | P | P | P | Receive DOB Approval
| 7/29/11 9/8/11 | P | P | P | Transmit revised FQHC rates and other required data to eMedNY.

## Cancelled
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
CANCELLED PROPOSALS (DUE TO NOT BEING INCLUDED IN ENACTED BUDGET):
15C |  |  |  |  | Project Name: Reduce Pharmacy Reimbursement & Dispensing Fees Division Lead: DFPP Team Lead: Mary Carroll Janet Elkind Description: Reduction in pharmacy ingredient cost and dispensing fee reimbursement amounts to align with levels achieved in other State Medicaid Programs and commercial payers. | -30.2 | Cancelled
| 2011-04-01 | P | P | P | Obtain enabling legislation to reduce reimbursement & fees. | Executive language accepted.
| 2011-04-01 | P | P | P | Obtain legislation to eliminate HIV Specialty Pharmacy designation and associated higher drug reimbursement. | Executive language accepted.
| 2011-04-15 | P | P | P | Draft State Plan Amendment (SPA) (Program impact statement & State Plan Review Summary) | Complete.
| 2011-04-15 | P | P | P | Meet with staff from ADAP re: HIV Specialty Pharmacy.
| 2011-04-25 | P | P | P | Workgroup to determine strategy and timing for rate reduction | Staff from DFPP/DOB/DOIT
| 2011-05-01 | P | P | P | Determine staffing needs. | No additional staffing requirements.
| 2011-05-01 | P | P | P | Meet with regulated parties (PSSNY, chains) | Discussion with PSSNY & NACDS 4/12- f/u to be scheduled week of 5/2
| 2011-05-01 | P | P | P | Submit final SPA package | With State Plan Coordinator
| 2011-05-15 | P | P | P | Establish Average Acquisition Cost (AAC) workgroup
| 2011-07-01 | P | P | P | Establish potential process for retroactive pricing adjustment to achieve savings estimate, if decision is made to retroactively apply reductions | SPA submission prior to 6/30/11 will be retro to first day of submission quarter (4/1).
| 7/1/11 8/1/11 8/15/11 | P | P | P | Revise reimbursement methodology in claims system | To be done internally by DFPP staff. Waiting for SPA approval
| 7/1/11 8/1/11 8/15/11 | P | P | P | Revise dispensing fees in claims system | To be done internally by DFPP staff. Waiting for SPA approval
| 6/1/11 6-15-11 7/1/11 8/1/11 8/15/11 | P | P | P | Notify stakeholders through Medicaid Update article and Provider letters | Waiting for SPA approval
| 6/1/11 6-15-11 7/1/11 8/1/11 8/15/11 | P | P | P | Update DOH website "Pricing Methodology" | Waiting for SPA approval
| 7/1/11 8/1/11 8/15/11 | P | P | P | Obtain SPA approval | Second set of questions received for 11-61. Third set of questions received and responded to
| 7/1/11 8/1/11 8/15/11 | P | P | P | Implement | Savings are based on 4/1/11 implementation. Staff have developed a plan that will achieve the savings based on a 4/1 date.
| 2011-09-01 | P | P | P | Determine final payment for HIV pharmacy and notify FMG to make payment. | collect data from current HIV pharmacy and compute payment.
| 10/1/11 3/1/12 7/1/12 11/1/13 2/1/14 4/1/14 | 8 | 8 | 8 | Implement AAC reimbursement methodology | Inclusion of AAC in the "lower of" reimbursement methodology has been removed from SPA 11-61. Determination has been made to complete pricing survey, develop reimbursement and resubmit to CMS once AAC pricing and dispensing fee has been developed.
15-J |  |  |  |  | Project Name: Reimbursement Changes for Clotting Factor Products Division Lead: DFPP Team Lead: Mary Carroll Description: Change the reimbursement methodology for clotting factor products to pay at the lesser of acquisition cost or the Medicaid established state maximum allowable cost (SMAC). | Merged with #15-C
| 2011-05-15 | P | P | P | Establish Average Acquisition Cost (AAC) workgroup
| 2011-05-01 | P | P | P | Identify staffing needs | No additional staff.
| 2011-08-05 | P | P | P | Add clotting factor reimbursement changes to AAC project | Stakeholders notified
| 2011-08-10 | P | P | P | Complete emergency regulation package authorizing the Department to require submission of acquisition cost
| 8/15/11 10/1/11 11/1/11 12/15/11 | P | P | P | Submit system project to revise reimbursement methodology | EP1626A
| 8/30/11 10/1/11 10/20/11 | P | P | P | Develop reporting method/tool for acquisition cost | Will use Health Commerce System secure FTP.
| 2011-12-01 | P | P | P | Identify CPA firm that will work with team | Ernst & Young
| 2011-12-30 | P | P | P | Establish governance structure and project plan
| 2012-01-09 | P | P | P | Develop focus group qualities, identify participants and schedule
| 2012-01-13 | P | P | P | Create initial AAC and COD methodology
| 1/13/12 2/24/12 3/12/12 | P | P | P | Outline data capture process
| 1/17/12 2/24/12 3/12/12 | P | P | P | Outline data requirements
| 2/3/12 2/24/12 3/15/12 | P | P | P | Develop online survey tool
| 2/3/12 2/24/12 3/8/12 | P | P | P | Complete focus group process
| 2/3/12 2/24/12 3/15/12 | P | P | P | Deploy pilot AAC/COD survey tool
| 2/3/12 2/24/12 3/15/12 | P | P | P | Approve methodology and data capture process
| 2012-02-24 | P | P | P | Deploy contact/resource center
| 3/10/12 3/20/12 4/16/12 6/1/12 6/28/12 | P | P | P | Issue pilot COD survey and collect data
| 3/10/12 3/20/12 4/16/12 6/1/12 6/28/12 | P | P | P | Issue pilot AAC survey and collect data
| 3/23/12 3/28/12 4/30/12 6/18/12 7/18/12 9/15/12 | P | P | P | Review data and address submission errors
| 4/2/12 5/4/12 6/25/12 7/25/12 9/25/12 | P | P | P | De-identify data, consolidate and review
| 2012-09-27 | P | P | P | Issue full COD survey
| 4/2/12 5/4/12 6/25/12 7/25/12 9/27/12 11/27/12 | P | P | P | Begin developing Emergency Reg package
| 4/6/12 7/2/12 8/2/12 9/28/12 | P | P | P | Identify AAC pilot outliers
| 4/10/12 7/9/12 8/9/12 10/16/12 | P | P | P | Verify statistical representative sample of data
| 4/14/12 6/5/12 7/16/12 8/16/12 10/30/12 | P | P | P | Create final AAC report based on pilot survey and verification
| 4/16/12 7/20/12 8/20/12 11/1/12 12/4/12 | P | P | P | Approve final AAC survey methodology | Being pushed out due to impact of Hurricane Sandy
| 4/23/12 6/15/12 8/1/12 8/28/12 11/1/12 12/4/12 | P | P | P | Implement AAC data collection | Being pushed out due to impact of Hurricane Sandy
| 4/23/12 6/15/12 8/1/12 8/28/12 11/1/12 12/15/12 1/15/13 2/23/13 3/22/13 5/29/13 6/19/13 7/5/13 8/1/13 8/23/13 9/11/13 10/15/13 10/25/13 12/3/13 | P | P | P | Identify dispensing fee(s)
| 4/23/12 6/15/12 8/30/12 2/4/13 2/28/13 3/29/13 8/2/13 9/12/13 10/16/13 11/16/13 1/21/14 5/1/14 | 8 | 8 | 8 | Notify Legislature of pricing change
| 4/23/12 6/15/12 8/30/12 11/15/12 2/25/13 3/29/13 7/15/13 8/15/13 9/17/13 10/21/13 12/23/13 1/24/14 3/31/14 | 8 | 8 | 8 | Submit SPA
| 4/23/12 6/15/12 8/30/12 11/15/12 2/25/13 3/29/13 5/29/13 6/19/13 7/15/13 8/26/13 9/17/13 10/21/13 12/23/13 5/1/14 | 8 | 8 | 8 | Submit Regulatory Package
| 5/22/12 7/16/12 9/16/12 2/4/13 | P | P | P | Review data and address submission errors
| 5/31/12 7/20/12 9/19/12 12/15/12 2/6/13 | P | P | P | De-identify data, consolidate and review
| 6/4/12 7/23/12 9/20/12 12/27/12 3/15/13 | P | P | P | Identify AAC outliers
| 6/11/12 7/30/12 10/30/12 3/27/13 | P | P | P | Verify statistical representative sample of AAC data
| 5/24/13 6/26/13 7/26/13 8/15/13 8/23/13 9/25/13 11/4/13 12/3/13 | P | P | P | webex with focus group to discuss final analysis
| 6/18/12 8/31/12 12/1/12 2/15/13 4/13/13 5/22/13 6/28/13 7/2/13 8/6/13 8/23/13 9/19/13 10/26/13 12/27/13 1/21/14 4/18/14 | 8 | 8 | 8 | Create final report based on data survey and verification
| 6/28/12 9/15/12 1/1/13 5/1/13 8/1/13 10/1/13 11/1/13 2/1/14 4/1/14 | 8 | 8 | 8 | Deploy AAC as basis of payment
|  | 8 | 8 | 8 | Project on hold; pending until 15-16 budget discussions
15-D |  |  |  |  | Project Name: Increase the Number of Immunizations that a Pharmacist May Administer Division Lead: DFPP Team Lead: Mary Carroll Description: This proposal will allow pharmacists to administer all vaccines recommended by the CDC for patients ages 11 and above. | -30.2 | Cancelled
18 |  |  |  |  | Project Name: Eliminate Spousal Refusal Division Lead: DCE Team Lead: Wendy Butz Description: Eliminate the loophole that allows legally responsible relatives to refuse to financially support their applying spouse, or child to obtain Medicaid. | -28.3 | Cancelled
41 |  |  |  |  | Project Name: New York State Public Health Service Corps Division Lead: Primary Care Team Lead: Karen Westervelt Additional Staff: Caleb Wistar/Barry Gray Description: Implement the New York State Public Health Service Corps | 1 | Cancelled
104 |  |  |  |  | Project Name: Medicaid Co-payment Changes Division Lead: DFPP Team Lead: Akbar Khan (MA) Add'l staff: Ron Bass (MA), Ralph Bielefeldt (CHP), Sue Barth (FHP) Description: Ensure Consumer Protection and Promote Personal Responsibility | -7.5 | Cancelled
121 |  |  |  |  | Project Name: Public Nursing Homes Corporation Division Lead: Team Lead: Valerie Deetz Add'l Staff: Mark Kissinger, Laura Sprague, Jackie Pappalardi Description: This proposal would establish a State authority/public benefit corporation that counties with nursing homes would have the option to join. | 0 | Cancelled
147 |  |  |  |  | Certain initiatives from MRT # 145 were rejected: Reinstate Industrial Development Agency (IDA) Financing Temporary suspension of NCQPA by Article 28 facilities Death and Felony Crime Reporting |  | Cancelled
264 |  |  |  |  | Project Name: Apply a surcharge to Physician Office Based Surgery and Radiology Services Division Lead: DHCF Team Lead: Anthony Naglieri Add'l Staff: Phyllis Stanton, Michelle Levesque Description: Implement a broad based and uniform surcharge on surgery and radiology services provided by phyisicians in office-based settings, including non-licensed urgent care centers, utilizing CPT codes. | ($8 M) | Cancelled
CANCELLED PROPOSALS
15F |  |  |  |  | Project Name: Implement a Voluntary Mail Order Program Division Lead: DFPP Team Lead: Mary Carroll Description: Create a mail order pharmacy benefit for maintenance drugs, to take advantage of higher discounts. | 0 | Cancelled
15L |  |  |  |  | Project Name: Proper disposal of unused meds and waste reduction through short cycle dispensing and re-dispensing Division Lead: DFPP Team Lead: Mary Carroll Description: Ensure the appropriate disposal and/or return of unused medications and require long term care (LTC) pharmacies to dispense in quantities less than 30 days | 0 | Cancelled
154-1 |  |  |  |  | Project Name: PECOS - Require Medicare Enrollment for All Ordering Physicians of Home Health Service Project Lead: Tom Meyer (Alicia Whitlingup - OMIG) Description: Require that physicians who order services for individuals that are enrolled in both Medicare and Medicaid (dual eligible’s) be enrolled in Medicare consistent with Medicare Provider Enrollment, Chain and Ownership system (PECOS) requirements. PECOS requirements authorize the denial of Medicare claims for physicians who order services (home care, pharmacy, durable medical equipment and radiology) for dual eligible’s who are not enrolled as a Medicare provider. In these cases, Medicaid would be required to pay the entire claim as the payor of last resort. Accordingly, this proposal is necessary to ensure appropriate Medicare billing, thereby avoiding future increased Medicaid costs. |  | Cancelled
154-6 |  |  |  |  | Project Name: Expand RRP - Expand the Restricted Recipient Program Project Lead: Sam Spitzberg Project Description: Define triggers that create mandatory restriction for recipients without existing full clinical reviews; automatically authorize recipient restriction for recipients who possess multiple (two or more) Medicaid identification cards and use or attempt to use such cards as well as present a forged or altered prescription; authorize recipient restriction for managed care enrollees for pharmacy/dental/other restriction categories; and extend the initial restriction period from 24 to 36 months, and extend the second, third and any additional restriction periods. | -2.2 | Cancelled
154-7 |  |  |  |  | Project Name: Card Swipe Pharmacy- Mandate Participation in the Cardswipe Program for Pharmacies Billing in Excess of $1M in 2010 Who Have Not Submitted A Compliance Certification Project Lead: Sheila Emminger Project Description: Require all pharmacies billing Medicaid in excess of $1M who have not filed a Compliance Certificate with the Bureau of Compliance to participate in the OMIG Cardswipe Program (landline) with a Vx570 terminal supplied by the department. With the impending transition of pharmacy coverage to the managed care arena, the card swipe expansion is redirected to the deployment of mobile card swipe terminals to transportation providers and private duty nurses. It is anticipated that between 1000 and 1250 mobile terminals will be deployed during SFY 11-12, yielding the anticipated cost avoidance. | -3.99 | Cancelled
1116 |  |  |  |  | Project Name: Apply 60 Month Look Back Period to Non-Institutional Long Term Care Division Lead: Coverage and Enrollment Team Lead: Wendy Butz Description: Apply 60 month look back period for transfer of assets to non-institutional long term care applicants with spousal impovershment protections. | 0 | Cancelled

## Merged
MRT Project # | Project/Task Description | State Savings ($millions) | Status/Team Lead Information
15-J | Project Name: Reimbursement Changes for Clotting Factor Products Division Lead: DFPP Team Lead: Mary Carroll Description: Change the reimbursement methodology for clotting factor products to pay at the lesser of acquisition cost or the Medicaid established state maximum allowable cost (SMAC). | 0 | Merged with #15-C
Merged with #15-C, Reduce Pharmacy Reimbursement & Dispensing Fees. Approved by Jason Hegerson 8/4/11
101 | Project Name: Develop Initiatives to Integrate and Manage Care for Dual Eligibles Division Lead: DMC Team Lead: Linda Gowdy Description: Develop approaches for serving dual eligibles | 0 | Merged with #90
Merged with #90, Mandatory Enrollment in MLTC/ Plans / Health Home Conversion, approved by Jason Helgerson 2/9/12
131 (partial) | Project Name: Improved Medicaid Lien Recovery Division Lead: Team Lead: Add'l Staff: Description: Incentive lien recovery with counties |  | Merged with #15-L
Merged with #15-L, Proper disposal of unused meds and waste reduction through short cycle dispensing and re-dispensing, approved by Jason Helgerson 6/15/11
154-4 | Pharmacy Restock- Require Pharmacies to Restock and Re-Dispense Returned Medications Project Lead: OMIG/Alicia Whitlingum | 0 | Merged with #102
Merged with #102, Centralize Estate Recovery for Medicaid Lien Process, approved by Jason Helgerson 6/15/11
1021 | Project Name: Facilitating Co-Located physical health, behavioral health and developmental disability services Division Lead: DFPP Team Lead: Denise Spor Description: To streamline process & eliminate barriers and to determine a single set of rules for facilities seeking to co-locate services | 0 | Merged with #89
Merged with #89 Health Homes; approved by Jason Helgerson 4/6/11.
1029 | Project Name: Administrative Renewal for Aged, Blind, and Disabled and Medicare Savings Program (MSP) Participants Division Lead: DCE Team Lead: Wendy Butz Description: Allow aged, blind and disabled with fixed incomes to be automatically renewed based on cost of living increases. | -0.1 | Merged with #133
Merged with #133; approved by Jason Helgerson 4/6/11.
1427 | Project Name: CDPAP and Managed Care Division Lead: OLTC/DHCBS Team Lead: Linda Gowdy Description: Include of Consumer Directed Services in Managed Long Term Care Benefit (A) & Promulgate CDPAP regulations (B) | 0 | Merged with #90
Merged with #90, Mandatory Enrollment in MLTC/ Plans / Health Home Conversion, approved by Jason Helgerson 2/9/12
1458 | Project Name: Care Management Population & Benefit Expansion, Access to Services, and Consumer Rights Division Lead: DMC Team Lead: Joanne Martinez Patricia Sheppard Additional Staff: Nina Daratsos, Eric Planck Denise Urbano, Alisa Costa, and Joanne Martinez Description: Omnibus Medicaid Managed Care initiatives, eliminates many exempt/excluded populations, expands the benefit package, promotes access to services, and ensures consumer rights |  | Merged with #8401
Merged with #8401, Care Management Population & Benefit Expansion, Access to Services, and Consumer Rights; approved by Jason Helgerson 1/27/16
4647 | Project Name: Expand MATS Division Lead: DFPP Team Lead: Rob Kent (OASAS) Add'l Staff: Deirdre Astin (DOH) Description: Explore expanding and transitioning MATS into health home. | 0 | Merged with #89
Merged with #89 Health Homes; approved by Jason Helgerson 6/15/11

## #1458 Merged
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2011-2012 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
As of: | 1/27/16
1458 |  |  |  |  | Project Name: Care Management Population & Benefit Expansion, Access to Services, and Consumer Rights Division Lead: DMC Team Lead: Joanne Martinez Patricia Sheppard Additional Staff: Nina Daratsos, Eric Planck Denise Urbano, Alisa Costa, and Joanne Martinez Description: Omnibus Medicaid Managed Care initiatives, eliminates many exempt/excluded populations, expands the benefit package, promotes access to services, and ensures consumer rights |  | Merged - #8401
| Att. 1 (Year 1) | P | P | P | Attachment 1 - Expand Managed care Enrollment for non-dual eligibles and modify mainstream benefit package
| Att. 1 (Year 2) | 8 | 8 | 8 | Attachment 1 - Expand Managed care Enrollment for non-dual eligibles and modify mainstream benefit package
| Att. 2 | P | P | P | Attachment 2 - Access to Benefits and Consumer Protections
| Att. 3 | P | P | P | Attachment 3 - Streamline Managed care Eligibility Process
| Year 1 Implementation | P | P | P | Attachment 1 - Expand Managed care Enrollment for non-dual eligibles and modify mainstream benefit package
| Year 3+ Implementation |  |  |  | Attachment 1 - Expand Managed care Enrollment for non-dual eligibles and modify mainstream benefit package
| 2013-03-28 | P | P | P | Legislation approved for the balance of population/benefit roll-out schedule
Population Expansion 4/1/13
|  | P | P | P | Individuals enrolled in LTHHCP
| 2012-05-02 | P | P | P | Begin internal meetings re: enrollment policies and procedures
| 9/1/12 9/15/12 10/5/12 10/22/12 | P | P | P | Assess systems impact internally and discussed with EB/EC and WMS/eMedNY systems staff
| 9/31/12 10/25/12 | P | P | P | Deliver systems change SA /EP to WMS/eMedNY for implementation
| 2012-09-19 | P | P | P | Present update and proposed changes to MMCARP
| 2012-10-17 | P | P | P | Managed Care Policy and Planning Meeting with MCOs
| 2012-11-08 | P | P | P | Managed Care Policy and Planning Meeting with MCOs
| 11/10/12 12/10/12 2/28/13 5/1/13 5/15/13 | P | P | P | Medicaid Update article released regarding new population being enrolled
| 12/1/12 1/29/13 | P | P | P | Train local social services districts and EB/EC staff on benefits being added
| 12/1/12 3/1/13 | P | P | P | Outreach completed for providers and plans
| 12/1/12 3/1/13 4/1/13 | P | P | P | Outreach completed for Fair Hearings staff
| 12/12/12 12/19/12 | P | P | P | Present update and proposed changes to MMCARP
| 2012-12-12 | P | P | P | Managed Care Policy and Planning Meeting with MCOs
| 2012-12-20 | P | P | P | Meeting to discuss LTHHCP Implementation
| 2012-12-27 | P | P | P | Meeting to discuss LTHHCP Implementation
| 2013-01-07 | P | P | P | Meeting to discuss LTHHCP Implementation
| 1/21/13 1/24/13 | P | P | P | Meeting to discuss LTHHCP Implementation
| 2013-02-04 | P | P | P | Meeting to discuss LTHHCP Implementation
| 2/1/13 2/20/13 4/15/13 3/18/13 | P | P | P | Stakeholder Engagement Meeting - Webinar
| 3/22/13 5/10/13 | P | P | P | Instructional letter regarding LTHHCP transition sent to LDSS
| 2013-04-02 | P | P | P | Received CMS approval
| 2013-04-03 | P | P | P | Conference call held with LDSS and HRA
| 2013-05-15 | P | P | P | List of members receiving enrollment packets sent to LDSS
|  | P | P | P | MA Buy-In for the working disabled
| 2013-01-10 | P | P | P | Work with enrollment broker to identify population and MMC enrollment
| 2013-01-31 | P | P | P | NYPWA presentation to LDSS staff
|  | P | P | P | LDSS placed (non agency) foster care children living in the community (upstate only)
| 2012-12-04 | P | P | P | Meeting to discuss foster care
| 2012-12-10 | P | P | P | Meeting to discuss BHO/foster care
| 2012-12-19 | P | P | P | Meeting to discuss foster care
| 2013-01-18 | P | P | P | Assess current managed care enrollment policies at selected Upstate LDSS as part of readiness review
| 2013-01-18 | P | P | P | Draft electronic survey to assess current policies and procedures at Upstate LDSS for enrollment of children in foster care into managed care |  | Salient Analyst: Joe Naglieri Lana Earle
| 2013-01-25 | P | P | P | Forward 2008 foster care plans to selected LDSS to be updated for 2012-13
| 2013-01-25 | P | P | P | Conference call with LDSS to discuss current foster care enrollment and issues
| 2013-02-25 | P | P | P | Draft Policy Paper under Review
| 2013-03-04 | P | P | P | Intra-agency meeting on foster care with OCFS
| 2013-02-07 | P | P | P | Data match to identify affected populations
| 2013-02-28 | P | P | P | Data match to identify specialty providers of health, BH and MH services to children in foster care
| 2013-02-28 | P | P | P | Data match - providers seeing children in foster care matched to MCO provider networks
| 3/6/13 3/25/13 | P | P | P | Data match - providers not affiliated with MCO sent to LDSS to identify those used for mandated assessments and referrals
| 2013-03-25 | P | P | P | Review sample referral form in use by LDSS currently enrolling foster care into managed care.
| 2013-03-18 | P | P | P | Stakeholder Engagement Meeting/Webinar
| 2013-04-02 | P | P | P | Received CMS approval
| 2013-04-03 | P | P | P | List of enrolled children entering FC sent to plans
| 2013-04-05 | P | P | P | Update Medicaid Managed Care model contract to reflect changes to foster care children
| 2013-05-02 | P | P | P | Internal meeting to discuss FC roll-out progress
| 2013-05-07 | P | P | P | Began monthly implementation follow-up meetings with LDSS
Benefit Expansion 4/1/13 (CMS approval 4/3/13)
| up to 4/1/13 | P | P | P | Ongoing discussions of implementation issues with CMS
| 2013-01-16 | P | P | P | List of providers sent to mainstream MCOs for contracting purposes
| 2013-04-01 | P | P | P | Medical Social Services benefit added
| 2013-04-01 | P | P | P | Home Delivered Meals benefit added
Benefit Expansion 7/1/13 8/1/2013
Adult Day/AIDS Adult Day Health Care/Directly Observed Therapy for TB/Inpatient TB Ordered by Local Health Commissioner
| 2013-03-01 | P | P | P | Meeting to discuss implementation
| 2013-03-11 | P | P | P | Plan, provider and recipient data retrieved
| 2013-04-03 | P | P | P | Notification letter to CMS in approval process
| 2013-05-07 | P | P | P | Internal meeting to discuss transition of benefits into MMC
| 2013-05-15 | P | P | P | Lists of affected providers/clients to plans for contracting
| 2013-05-23 | P | P | P | Drafting policy papers for 7/1/13 benefits - ADHC/AADHC, and TB DOT
| 2013-05-30 | P | P | P | eMedNY updated for scope of benefit changes
| 2013-05-30 | P | P | P | Meeting with all MCOs regarding 7/1/13 benefit changes
| 2013-05-31 | P | P | P | Draft policy papers for 7/1/13 benefit changes under review
| 2013-06-06 | P | P | P | Internal meeting to discuss transition of benefits into MMC
| 2013-06-10 | P | P | P | Webinar with Plans and Providers regarding 7/1/13 benefit changes
| 2013-06-11 | P | P | P | Internal meeting to discuss transition of benefits into MMC
| 2013-06-13 | P | P | P | MMCARP conference call discussing new benefits and plan responsibilities
| 2013-06-25 | P | P | P | Webinar materials and guidance for new benefits posted to MRT website
| 2013-07-26 | P | P | P | CMS Approval received for ADHC, AIDS ADHC and TB DOT benefit transition
| 5/15/13 6/15/13 7/1/13 7/30/13 | P | P | P | Medicaid Update article released for all 8/1/13 benefits
| 2013-08-12 | P | P | P | Conference Call with AIDS Adult Day Health Care providers to discuss issues with claims submissions
| 2013-08-01 | P | P | P | Benefit expansion extended to 8/1/2013
Benefit Expansion 10/1/13
| 2013-07-23 | P | P | P | Roll-out schedule presented at NYPWA conference
| 2013-08-20 | P | P | P | Meeting with Director of Hospice Association
| 2013-08-26 | P | P | P | Network, rates, enrollee and provider data sent to plans
| 2013-09-01 | P | P | P | Policy paper and plan provider networks submitted to CMS for approval
| 2013-09-11 | P | P | P | Webinar with Plans and Providers regarding 10/01/13 benefit
| 2013-09-17 | P | P | P | Hospice recipient data retrieved
| 2013-09-18 | P | P | P | Meeting with Director of Hospice Association
| 2013-10-01 | P | P | P | Policy Paper created and distributed to stakeholders
| 2013-10-03 | P | P | P | Policy Paper posted to MRT 1458 Supplemental Info page
| 2013-10-01 | P | P | P | Benefit: Hospice
Population and Benefit Expansion 1/01/14 3/01/14 04/01/14 6/01/14 8/01/14 01/01/15 (Revised work plan 11/2014)
Population: Residents of Health Care Facilities Benefit: Nursing Home Benefit
| 2013-03-01 | P | P | P | Ongoing meetings within OHIP divisions
| 2013-05-01 | P | P | P | Monthly NH Association Call
| 2013-05-06 | P | P | P | Internal meeting to discuss transition of non-duals into MMC
| 2013-05-10 | P | P | P | NH transition conference call with MCOs and health plan associations
| 2013-06-17 | P | P | P | NH transition conference call with MCOs and health plan associations
| 6/30/13 8/1/13 9/15/13 | P | P | P | Systems changes submitted to eMedNY/WMS
| 6/30/13 7/15/13 | P | P | P | Review of proposed policy changes with Maximus
| 6/30/13 7/15/13 7/23/13 | P | P | P | Stakeholder Engagement Meeting (meeting with Nursing Homes, LDSS, and plans)
| 2013-07-23 | P | P | P | Roll-out schedule presented at NYPWA conference
| 2013-07-23 | P | P | P | NH transition workgroups created (finance/rates, network/contracting, eligibility/enrollment, access)
| 2013-09-13 | P | P | P | Stakeholder Engagement Meeting (meeting with Nursing Homes and plans)
| 2013-10-02 | P | P | P | Stakeholder Engagement Meeting (meeting with Nursing Homes and plans)
| 2013-10-30 | P | P | P | Stakeholder Engagement Meeting (meeting with Nursing Homes and plans) Initial policy document shared
| 2013-11-25 | P | P | P | Stakeholder/Workgroup Meeting
| 10/28/13 11/30/13 | P | P | P | Workgroup recommendations finalized for Finance
| 10/28/13 11/30/13 | P | P | P | Workgroup recommendations finalized for Access and Quality
| 10/28/13 11/30/13 | P | P | P | Workgroup recommendations finalized for Network and Contracting
| 10/28/13 11/30/13 | P | P | P | Workgroup recommendations finalized for Eligibility and Enrollment
| 2013-12-10 | P | P | P | Share policy document with workgroups for review
| 2013-12-18 | P | P | P | Nursing Home Transition Webinar (plans, nursing homes, stakeholders)
| 2013-12-19 | P | P | P | Present update and proposed changes to MMCARP
| 2013-12-30 | P | P | P | Respond to comments and finalize policy decisions
| 2013-12-31 | P | P | P | Revised policy paper shared with workgroups
| 2014-01-30 | P | P | P | Revised policy paper shared with staff and CMS
| 2014-02-05 | P | P | P | Submitted responses to CMS questions on reimbursement section of policy document
| 1/24/14 1/27/14 | P | P | P | Stakeholder/Workgroup Meeting
| 12/20/13 1/31/14 2/28/14 | P | P | P | Policy guidance document sent to stakeholders
| 2015-01-01 | P | P | P | Financial - January 2014 March 2014 4/01/14 Rates (Updated November 2014)
| 1/28/14 2/28/14 | P | P | P | Share Data Source table with Mercer (Updated for methodology change)
| 5/16/14 7/31/14 | P | P | P | Develop Draft Projected Member Months (Updated for change in implementation date)
| 2014-03-06 | P | P | P | Review Draft Rate Methodology with plans
| 2/2/14 2/10/14 3/14/14 3/27/14 | P | P | P | Develop NH Rate Trends
| 2/2/14 2/10/14 3/14/14 3/27/14 | P | P | P | Develop Program changes
| 2/2/14 2/10/14 3/14/14 3/27/14 | P | P | P | Develop Managed Care Adjustment
| 2/2/14 2/10/14 3/14/14 3/27/14 | P | P | P | Receive draft rate development from Mercer
|  | P | P | P | Share draft rates with plans
| 2/22/14 9/5/14 | P | P | P | Release Notice: Nursing Home FFS Benchmark rates (Updated for January 2014 rates with case mix adjustment)
|  | P | P | P | CMS approval of separate rate cell approach
| 2014-03-27 | P | P | P | EP 1836 - new rate codes completed (Pending rates to test)
| 2014-11-06 | P | P | P | Develop Final Projected Member Months
| 2014-11-13 | P | P | P | Receive final rate development from Mercer
| 2014-11-13 | P | P | P | Develop Rate Ranges
| 2014-11-13 | P | P | P | Actuarial Certification Letter
| 2014-11-27 | P | P | P | Prepare DOB Rate Package
| 2014-11-27 | P | P | P | Prepare CMS Approval Request
| 2014-12-04 | P | P | P | Create plan rate sheets packages in pdf form to be mailed to plans
| 2014-12-19 | P | P | P | Prepare Rate Package to Load Rates
| 2/1/14 2/7/14 | P | P | P | Develop premiums within MMC and MLTC
| 2013-12-31 | 8 | 8 | 8 | Provide Final Rates to Mercer
| 2013-12-31 | 8 | 8 | 8 | Develop Expansion Rates
| 2013-12-31 | 8 | 8 | 8 | Provide Expansion Rates to DLTC
| 12/31/13 2/28/14 6/1/14 7/1/14 8/1/14 1/1/15 | P | P | P | Obtain DOB and CMS Approval
| 2014-02-10 | P | P | P | Public Webinar on NAMI development
| 12/20/13 2/1/14 2/28/14 | P | P | P | Post policy guidance and webinar materials to MRT website
| 12/20/13 2/1/14 | P | P | P | Medicaid Update summary article released for December February January issue
| 2014-02-20 | P | P | P | Full Medicaid Update article submitted for February issue
| 2/1/14 2/28/14 | P | P | P | Review Maximus scripts, notices, and exemption forms for any necessary revisions
| 2/15/14 2/21/14 | P | P | P | Publish Premiums
| 2014-02-24 | P | P | P | Stakeholder Engagement Meeting
| 12/1/13 2/1/14 | P | P | P | Provider Network Submissions Due
| 2014-03-10 | P | P | P | Meeting w/HRA and NYC and Phase 1 Nursing Homes
| 2014-03-13 | P | P | P | Conference Call with Phase 1 Counties (NYC, Nassau, Suffolk, Westchester)
| 2014-03-18 | P | P | P | Statewide MTAG Presentation
| 2014-03-20 | P | P | P | Webinar Presentation (Nursing Homes and Advocates)
| 2014-03-28 | P | P | P | Citiwide Meeting Presentation (HRA & NYC Nursing Homes)
| 2014-06-20 | P | P | P | Inclusion of veteran's' Nursing Homes in plan networks approved and transmitted to stakeholders
| 2014-08-01 | P | P | P | Outreach to nursing homes and Plans to clarify policy and billing procedures
| 2015-01-22 | P | P | P | Webinar Presentation with stakeholders: Nursing Homes, Plans, Advocacy Groups, Enrollment Broker
| 2/1/15 5/1/15 5/19/15 | P | P | P | Presentation to HRA and providers in NYC
| 8/1/14 1/1/15 2/1/15 | P | P | P | Final policy document posted to MRT website
| 8/1/14 10/1/14 1/1/15 | P | P | P | Final policy document completed and circulated to stakeholders
| 8/1/14 10/1/14 1/1/15 3/1/15 | P | P | P | Final response to questions from advocacy groups completed and posted to MRT website
| 4/1/14 6/1/14 7/1/14 8/1/14 10/1/14 1/1/15 4/1/15 5/1/15 | P | P | P | Release ADM
| 1/1/14 3/1/14 4/1/14 6/1/14 7/01/14 8/01/14 10/1/14 1/1/15 2/1/15 | P | P | P | Phase 1 Phase 1 Benefit transition to managed care benefit package New York City - Bronx, Kings, New York, Queens, Richmond, Nassau, Suffolk, Westchester Counties
| 3/1/15 3/26/15 | P | P | P | Presentation to Nassau, Suffolk, Westchester LDSS
| 2015-04-01 | P | P | P | Phase 2 benefit transition to managed care benefit package Nassau, Suffolk, and Westchester
| 2015-07-01 | 8 | 8 | 8 | Phase 1 & 2 Counties - voluntary enrollment in MC becomes available to individuals residing in nursing homes who are FFS Medicaid
| 10/1/14 11/1/14 | 8 | 8 | 8 | Phase 3 - Allegany, Cattaraugus, Jefferson, Lewis, St. Lawrence, Steuben
| 11/1/14 12/1/14 | 8 | 8 | 8 | Phase 4 - Chemung, Cortland, Schuyler, Seneca, Tioga, Yates
| 6/1/15 6/18/15 | P | P | P | M-TAG Presentation to Upstate Region Enrollment Broker Counties
| 6/1/15 6/18/15 | P | P | P | M-TAG Presentation to Upstate Region non-Enrollment Broker Counties
| 7/1/15 7/29/15 | P | P | P | Follow-up Presentation to Plans and Providers in Upstate Phase 3 Counties
| 9/1/14 10/1/14 12/1/14 1/1/15 7/1/15 | P | P | P | Phase 3 benefit transition to managed care benefit package - Albany, Allegany, Broome, Cattaraugus, Cayuga, Chemung, Chenango, Clinton, Columbia, Cortland, Delaware, Dutchess, Erie, Essex, Franklin, Fulton, Genesee, Greene, Hamilton, Herkimer, Jefferson, Lewis, Livingston, Madison, Monroe, Montgomery, Niagara, Oneida. Onondaga, Ontario, Orange, Orleans, Oswego, Otsego, Putnam, Rensselaer, Rockland, St. Lawrence, Saratoga, Schenectady, Schoharie, Schuyler, Seneca, Steuben, Sullivan, Tioga, Tompkins, Ulster, Warren, Washington, Wayne, Wyoming, Yates All remaining counties
| 1/1/16 10/1/15 | P | P | P | All remaining counties - voluntary enrollment in Medicaid managed care becomes available to individuals residing in nursing homes who are in FFS Medicaid.
| 10/1/14 11/1/14 | 8 | 8 | 8 | Phase 3 - Allegany, Cattaraugus, Jefferson, Lewis, St. Lawrence, Steuben
| 11/1/14 12/1/14 | 8 | 8 | 8 | Phase 4 - Chemung, Cortland, Schuyler, Seneca, Tioga, Yates
| 2014-10-03 | P | P | P | Initiate Billing/Cash Flow Work Group Meetings (10/04,11/3)
| 5/20/15 ongoing | P | P | P | Weekly technical calls with HRA regarding transition issues and questions
| 1/1/15 2/1/15 | P | P | P | NAMI Finance workgroup meetings
| 1/1/15 2/1/15 | P | P | P | Nursing Home Transition Webinar (plans, nursing homes, stakeholders)
| 8/18/15 9/22/15 | P | P | P | Ongoing monthly meetings with LDSS
| 1/1/15 2/1/15 | P | P | P | Monthly Meetings with MCO reps, nursing homes, stakeholders
Population Expansion 9/1/15
[5 empty] | HCBS Waiver - NH Transition and Diversion |  | Merged with Phase 5, #8401
HCBS Waiver - TBI
HCBS OPWDD Care At Home Waivers 3, 4, and 6