## Ph. 8 Catch All
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2018-2019 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
| 2018-10-24 |  |  |  | P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
11001 |  |  |  |  | Project Name: Asset Verification System (AVS) Division Lead: Division of Health Care Reform and Health Insurance Exchange Integration Team Lead: Ralph Bielefeldt Judy Arnold Additional Staff: Wendy Butz Description: The State should invest in an Asset Verification System (AVS) to permit the electronic verification of assets (including assets in the 5 year look back period) for determining eligibility for aged, blind, and disabled Medicaid applicants and recipients. AVS should be deployed as soon as possible in existing systems and this functionality should also exist in any new eligibility system. |  | In Progress
| 6/1/12 | P | P | P | Analyze Requirements
| 11/1/12 12/1/12 2/15/13 5/1/13 6/15/13 6/21/13 7/12/13 8/9/13 10/1/13 10/15/13 | P | P | P | Select a contractor
| 11/15/12 12/15/12 2/15/13 5/15/13 6/15/13 6/21/13 7/12/13 8/9/13 10/1/13 | P | P | P | B1184 funding justification submitted to DOB for approval
| 12/1/12 1/1/13 3/15/13 6/1/13 7/1/13 7/15/13 8/15/13 8/23/13 10/15/13 11/1/13 12/2/13 1/15/14 3/12/14 | P | P | P | Start Negotiate negotiating contract and deliverables
| 1/1/13 2/1/13 4/1/13 7/1/13 7/31/13 8/31/13 11/15/13 11/30/13 12/31/13 2/1/14 4/16/14 7/1/14 9/1/14 10/1/14 12/1/14 | P | P | P | Contract approved (Executed, pending final processing)
| 1/1/13 2/1/13 4/1/13 8/1/13 12/15/13 1/24/14 3/1/14 7/1/14 9/1/14 10/1/14 10/31/14 12/31/14 3/1/15 4/30/15 6/15/15 7/1/15 7/31/15 9/15/15 11/16/15 1/18/16 2/8/16 | 8 | 8 | 8 | Develop programming specifications and deliverables. (System Change Request form submitted, pending approval)
| 1/1/13 2/1/13 4/1/13 8/1/13 12/15/13 1/24/14 3/1/14 7/1/14 9/1/14 10/1/14 10/31/14 12/31/14 3/1/15 4/30/15 6/15/15 7/1/15 7/31/15 9/15/15 11/16/15 1/8/16 2/8/16 3/31/16 | P | P | P | Develop LDSS training requirements
| 1/1/13 2/1/13 4/1/13 8/1/13 12/15/13 1/24/14 3/1/14 7/1/14 9/1/14 10/1/14 10/31/14 12/31/14 3/1/15 4/30/15 6/15/15 7/1/15 7/31/15 9/15/15 11/16/15 1/8/16 2/8/16 3/31/16 | P | P | P | Test programming
| 4/1/13 6/1/13 10/1/13 11/1/13 2/1/14 3/7/14 11/1/14 12/1/14 2/28/15 4/15/15 5/1/15 7/1/15 9/30/15 10/31/15 1/8/16 2/29/16 5/20/16 6/20/16 9/30/16 10/31/16 11/30/16 | P | P | P | ADM Issued for implementation statewide |  | Draft ADM was issued statewide on 11/14
| 8/1/13 10/1/13 11/1/13 12/1/13 3/1/14 4/1/14 12/1/14 1/1/15 4/1/15 6/1/15 7/1/15 8/15/15 9/30/15 12/15/15 1/29/16 2/29/16 | P | P | P | Train LDSS staff - pilot districts
| 8/1/13 10/1/13 11/1/13 12/1/13 3/1/14 4/1/14 12/1/14 1/1/15 4/1/15 6/1/15 8/15/15 9/14/15 10/19/15 1/11/16 2/1/16 3/7/16 | P | P | P | Implement AVS program - pilot districts
| 2017-03-28 | P | P | P | Train all districts - except NYC
| 2017-03-29 | P | P | P | Implement for applications - all districts except NYC
| 8/5/2017 10/17/17 11/10/17 | P | P | P | Implementation of renewals - all districts except NYC
| 2017-10-12 | P | P | P | Complete NYC Testing
| 8/1/2017 9/15/17 10/6/17 10/31/17 11/30/17 | P | P | P | Issue Final ADM
| 2017-10-23 | P | P | P | Implement NYC - Pilot phase - chronic care
| 10/30/17 10/31/17 | P | P | P | Train NYC staff
| 1/20/2018 2/28/2018 | P | P | P | NYC - Implement all non-spousal electronic nursing home applications
| 3/30/2018 07/31/18 09/28/18 12/31/18 | 8 | 8 | 8 | NYC - Implement all non-spousal electronic nursing home conversions
| 6/29/2018 03/26/2018 | P | P | P | NYC - Implement all spousal electronic nursing home applications
| 7/31/2018 09/28/18 12/31/18 | 8 | 8 | 8 | NYC - Implement all spousal electronic nursing home conversions
| 9/28/2018 12/31/2018 | 8 | 8 | 8 | NYC - Implement all manual nursing home applications and conversions
| 2018-11-30 | 8 | 8 | 8 | Implement all community SSI-related - NYC
| 2019-01-30 | 8 | 8 | 8 | Implement Renewals - NYC
11002 |  |  |  |  | Project Name: Enforce billing restriction to prevent Nurse Practitioners, Physician Assistants, and Nurse-Midwives from being paid separately for practitioner claims for services provided in (Article 28) hospitals. Division Lead: Division of Program Development and Management / Greg Allen Team Lead: Mark Tremblay/Ron Bass Mary Jane O'Brien Additional Staff: Bill Bruno, Ron Bass, Donna Haskin Description: Do not permit Nurse Practitioners, Physician Assistants, or Nurse-Midwives from submitting and being reimbursed for separate professional claims when they provide services in (Article 28) hospitals. | State Savings 2013-2014 ($millions) ($1.5) | Completed - June 2018
PROGRAM DEVELOPMENT
| 8/7/13 9/6/13 9/12/13 | P | P | P | Meet with OHIP staff (policy and operations) to discuss policy details and steps to implement.
| 9/20/13 | P | P | P | Met with OHIP Operations to discuss utilizing Edit 01142 to pend claims for providers with the most claims and/or dollars paid for non-physician practitioner services (e.g., Nurse Practitioners, Physician Assistants, and Licensed Midwives) outside of the all inclusive rates in violation of Medicaid policy.
| 10/4/13 10/23/13 | P | P | P | Analyze claims data to identify providers with the most claims and/or dollars paid for non-physician practitioner services in violation of current Medicaid policy and submit request to OHIP operations to pend claims utilizing the 01142 Edit.
| 8/21/13 9/6/13 9/13/13 | P | P | P | Meet with OHIP staff (rate setting/MMC) to discuss rate impacts and managed care implications.
| 10/1/13 11/1/13 4/1/14 5/1/15 3/15/16 5/15/16 8/1/16 9/1/16 11/1/16 2/1/17 4/1/17 6/1/17 8/1/17 2/1/18 8/1/18 | P | P | P | Program implementation
NOTIFICATIONS
| 8/28/13 9/6/13 9/13/13 | P | P | P | Meet with staff to outline details of policy guidance documents including Medicaid Update and eMedNY list serve notification.
| 11/1/13 1/14/14 | P | P | P | Submit Medicaid Update and eMedNY list serve notification that DOH will begin enforcing this policy beginning 1/1/2014 7/1/2014 (without billing system edits to deny payment).
| 11/15/13 | P | P | P | Meet with OHIP Operations to discuss revising practitioner fee schedules for NPs. PAs, and Nurse Midwives to eliminate "institutional" category.
| 12/31/13 1/1/14 4/1/14 | P | P | P | Change Provider fee schedules for NPs. PAs, and Nurse Midwives to eliminate/revise "institutional" category.
| 4/1/14 | P | P | P | Revise all billing guidance, manuals, and DOH online material to conform with Medicaid Update guidance regarding new incompatible rate code/COS/POS combinations policy.
EVOLUTION
| 8/21/13 10/4/13 11/1/13 12/18/13 1/1/14 | P | P | P | Finalize EP to deny claims for NPs, PAs, and Nurse Midwives if billed as rendering provider for services provided in an Article 28 clinic.
| 9/14/13 11/15/13 1/3/14 4/1/14 5/27/14 | P | P | P | Meet to reconsider EP priority rankings to advance the case for implementing this systems change due to: OSC Audit, Budget, and MRT implications.
| 12/1/13 1/1/14 5/7/14 | P | P | P | EP moves to Functional Review Document.
| 4/1/14 6/26/14 | P | P | P | EP is implemented to "pay and report" effective 4/1/14 through 4/15/16 current
| 2016-06-28 | P | P | P | Post implementation enhancement was instituted and after numerous data reviews the EP was determined to be ineffective.
| 2017-06-22 | P | P | P | In order to accomplish this objective a new EP was submitted to refine system editing
| 8/1/2017 10/1/17 2/1/18 8/1/18 | P | P | P | New EP moves to functional review
| 10/1/2017 12/1/17 4/1/18 10/1/18 | P | P | P | New EP is implemented to "pay and report" effective
| 7/1/14 6/26/14 5/1/16 8/1/16 9/1/16 11/1/16 2/1/17 4/1/17 6/1/17 8/1/17 12/1/17 2/1/18 6/1/18 12/1/18 | P | P | P | EP is implemented as "deny payment" effective 7/1/14 5/1/16
POST IMPLEMENTATION
| 9/1/14 9/1/15 3/15/16 5/15/16 8/1/16 9/1/16 11/1/16 2/1/17 4/1/17 6/1/17 8/1/17 2/1/18 4/1/18 10/1/18 | P | P | P | Collect claims data to track savings
| 11/1/14 11/1/15 3/15/16 5/15/16 8/1/16 9/1/16 11/1/16 2/1/17 4/1/17 6/1/17 8/1/17 2/1/18 4/1/18 6/1/18 10/1/18 4/1/19 | P | P | P | Monitor and resolve complaints. Address systemic issues (if necessary)
11003 |  |  |  |  | Project Name: HCBS Settings Statewide Transition Plan Division Lead: OPCHSM Project Lead: Mark Kissinger Team Lead: Karen Meier, Madeline Kennedy Description: Implement STP Across All Agencies/Offices |  | In Progress
| 6/15/15 9/1/15 10/1/15 11/1/15 2/1/16 | P | P | P | Develop RFP to Hire Consultant to Implement STP
| 12/31/15 7/31/16 1/1/17 2/1/2017 4/1/17 5/1/17 | P | P | P | Procure Consultant
| 12/31/15 3/31/16 7/1/16 10/1/16 12/1/16 1/15/2017 5/1/2017 6/1/17 11/1/17 | P | P | P | DOH Staff Develops Surveys for Residential and Non-residential settings
| 5/31/16 7/1/16 10/1/16 12/1/16 2/1/2017 3/31/17 6/1/17 12/1/17 | P | P | P | Consultant DOH Implements Residential and Non-residential surveys
| 1/31/16 7/31/16 12/31/16 3/31/17 6/28/17 8/23/17 | P | P | P | Consultant Develops Evaluation Tool to Validate Survey Results and Remediation Efforts; Engages Stakeholders in Process
| Before 1/31/18 Through 12/1/18 | 8 | 8 | 8 | Consultant Reports to DOH/DLTC on Compliance Based on Survey Results
| Before 7/31/18 1/31/18 9/30/18 | P | P | P | Consultant Develops Remediation Plan for Approval by DOH/DLTC in consultation with service agencies and offices (OPWDD, OMH, OCFS, OASAS)
| Before 1/31/18 1/31/21 | 8 | 8 | 8 | Consultant State implements Remediation Plans, including heightened scrutiny process for settings that are presumed institutional but that can be shown to have the characteristics and qualities of home and community based settings. Process will include gathering public input for evidence to be submitted to CMS to support the assertion that these are community based settings.
| Before 7/31/18 7/31/21 | 8 | 8 | 8 | Consultant reports to DOH/DLTC on State reports compliance with remediation plans and progress on CMS designating presumed institutional settings as appropriate HCBS settings.
| Before 3/17/19 3/17/22 | 8 | 8 | 8 | Transition any individuals or programs that remain in settings not considered appropriate for HCBS to compliant settings or designate the illegal settings as institutional and not eligible for HCBS Medicaid funding.
11004 |  |  |  |  | Project Name: MC Pilot to Improve Access to Clozapine Medicaid MCO Performance Opportunity Project Division Lead: OMH Team Lead: Dr. Thomas Smith Additional Staff: Pieter Barnett; OMH-Psyckes; OMH-SF: Rich Tinkler Description: Clozapine and Intensive Care Transition Interventions for High-Acute MH Service Users. Over a 2 year state fiscal savings plan. | (2.04) (6.62) | Effective: 10/1/18
| 2018-04-12 | P | P | P | Initial Briefing for Managed Care Plans
| 2018-07-01 | P | P | P | Standing agenda item for MMCO Medical Directors
| 2018-07-01 | P | P | P | Initial Data Analytics( Preliminary)
| 2018-07-01 | P | P | P | Medicaid Managed Care Organization Readiness Planning
| 2018-07-01 | P | P | P | Designed Managed Care Award Model for reallocation
| 7/28/18 7/23/18 | P | P | P | OMH Hosted Learning Collaborative First Engagement Meeting with Hospital Porviders 1
| 2018-07-27 | P | P | P | OMH Hosted Meeting with Hospital Providers 2
| 2018-07-28 | P | P | P | OMH Hosted Learning Collaborative First Engagement
| 2018-08-10 | P | P | P | Letters to Plans formalizing the our process and goals
| 8/1/2018 8/20/18 | P | P | P | OMH finalizing DOH premium pullback allocation October Rate adjustment
| 8/1/2018 9/1/18 | P | P | P | Share Data Analytics Preliminary Findings to Plans
| 2018-09-01 | P | P | P | Final Data Analytics Available
| 2018-09-15 | P | P | P | Psyches Flag for Providers/Plans Available
| 2018-09-01 | P | P | P | MCO Oversight Begins
| 2018-09-01 | P | P | P | OMH Learning Collaborative Second Engagement
| 10/1/2018 10/30/18 | 8 | 8 | 8 | Implement best practices on target population through providers/MCO
| 10/1/2018 10/30/18 | 8 | 8 | 8 | Reduce PMPM Premiums on MCO's
| 2019-12-31 | 8 | 8 | 8 | Plan Measurement Results
| 2020-02-01 | 8 | 8 | 8 | MCO PMPM Awards based on Plan Measurement Results
11005 |  |  |  |  | Project Name: Best Practices in ER Diversion & Inpatient Discharge Division Lead: OMH Team Lead: Additional Staff: Description: This proposal implements best practices statewide through OMH clinical protocols in partnership with managed care plans and hospitals. | (4.54) | Merged with MRT #11004 - August 2018 Effective: 10/1/18
11006 |  |  |  |  | Project Name: Maximus Contract - 3-year Extension Division Lead: DHPCO Team Lead: James Featherstone Additional Staff: Bryan Tusch Description: This proposal extends the Maximus contract to three years |  | Effective: 4/1/18
| 7/11/18 | P | P | P | Call with Maximus to go over the gameplan for processing the extension
| 7/16/18 | P | P | P | Reach out to other program areas to determine projected quantities needed for the extension period.
| 9/15/18 | P | P | P | Prepare a draft budget based on estimated quantities and discuss with program areas, then with Maximus
| 10/15/18 | P | P | P | Draft contract amendment documents and submit to DEPS for review
| 11/15/18 | 8 | 8 | 8 | Send Contract Extension to Maximus for signature
| 12/14/18 | 8 | 8 | 8 | Receive Signed Contract Extension from Maximus
| 12/21/18 | 8 | 8 | 8 | Submit Completed Contract Extension Package to DEPS for Processing
| 1/22/19 | 8 | 8 | 8 | SFS Transaction Entered into SFS
| 1/23/19 | 8 | 8 | 8 | Contract Extension in Place. Project Completed.
11007 |  |  |  |  | Project Name: Performance Based Contract Restructure NY State of Health Customer Service Center Contract Amendment Division Lead: DEMI Team Lead: Ann Volpel Additional Staff: Description: This proposal extends the existing contract by three years and modifies the payment structure | (13.25) | Effective: 7/1/18
| 6/15/18 7/23/18 9/15/18 11/15/18 | 8 | 8 | 8 | Negotiate Contract Amendment Terms
| 7/1/18 8/15/18 9/25/18 11/15/18 | 8 | 8 | 8 | Obtain CMS Approval for Contract Amendment
| 7/1/18 9/1/18 10/1/18 11/30/18 | 8 | 8 | 8 | Execute Contract Amendment
11008 |  |  |  |  | Project Name: Claims Editing Enhancements Division Lead: Team Lead: Amanda Pyskadlo Additional Staff: Kathryn McCool Description: This proposal improves cost avoidance measures and enhanced fraud, waste, and abuse deterrence by expanding cost avoidance functions and enhancing the review processes for delays in claims filings. | (17.00) | Cancelled July 2018 - Effective: 4/1/18
11009 |  |  |  |  | Project Name: OMIG Savings Initiatives Division Lead: Team Lead: Gabrielle Ares Additional Staff: Erin Ives (OMIG) Description: This proposal supports initiatives to recover overpayments to Medicaid managed care organizations (MCO), require MCOs to report potential fraud, waste, or abuse, and to allow for the recovery of overpayments from MCO subcontractors or providers. These initiatives, combined with OMIG’s ongoing audit and recovery activities, represent the total savings. | (25.00) | Completed (No workplan needed) - October 2018
11010 |  |  |  |  | Project Name: Additional Funding for VAPAP/VBP-QIP Division Lead: OPCHSM Team Lead: Dan Sheppard Additional Staff: Tracy Raleigh Description: This proposals provides additional funding for financially distressed safety net hospitals. | 45.40 | Completed (No workplan needed) - September 2018
11011 |  |  |  |  | Project Name: Expand Access to Assisted Living Program Services Division Lead: OPCHSM Team Lead: Additional Staff: Description: Targeted Increase in ALP slots to provide additional non nursing home residential care alternatives. This proposal takes a multi step approach to increasing ALP utilization by 1) increases the resources needed to review ALP applications 2) provides authorizations for additional slots in areas of the state with limited ALP slots 3) authorizes current ALP providers in good standing to increase ALP slots on an expedited basis 4) provides for a demonstration program for persons with dementia in assisted living not on Medicaid to avoid nursing home placements. | 4.4 | Effective Date: 4/1/18 Completed (No workplan needed) - September 2018
11012 |  |  |  |  | Project Name: Reduce FFS/MCO Rate for Providers Without VBP Contracts Division Lead: OHIP Exec Team Lead: Ryan Ashe Additional Staff: Roland Poirier, Jason Ganns Description: This proposal establishes a new FFS/MCO Benchmark rate for providers without sufficient level of VBP contracting the State at FFS less a percentage to achieve targeted savings. | (7.50) | 7/1/18
| 11/1/18 | 8 | 8 | 8 | Determine providers that are not adequately engaging in VBP
| 12/31/18 | 8 | 8 | 8 | Determine appropriate benchmark rate (NH or Hospital) based on trailing provider
| 3/31/19 | 8 | 8 | 8 | Apply benchmark rate (if applicable) to trailing providers via MCO rate payments
11013 |  |  |  |  | Project Name: Hepatitis C Elimination Initiatives Division Lead: Office of Public Health; AIDS Institute Team Lead: Colleen Flannigan Additional Staff: Jackie Treanor, Joseph Kerwin, Ann Maxwell Description:The overall goal of the hepatitis C elimination initiatives and programs is to decrease hepatitis C (HCV) incidence, morbidity and mortality. This funding will support services targeting two populations disproportionally impacted by hepatitis C: people who inject drugs (PWID); and incarcerated individuals. | 5.00 | Effective: 4/1/18
| 10/1/2018 11/1/18 | 8 | 8 | 8 | Awards to establish a patient navigation program within Drug User Health Hubs/Syringe Exchange Programs operating outside of NYC to link HCV-positive PWID to HCV care and treatment.
| 2018-11-01 | 8 | 8 | 8 | Awards to conduct HCV community planning. Funding will support community planning grants to local health districts (LHDs) in ROS to facilitate community planning to address the HCV epidemic.
| 2019-07-01 | 8 | 8 | 8 | Awards will be made to implement and evaluate innovative HCV care and treatment models targeting PWID. Funding will also be used to enhance HCV testing.
| 2018-10-01 | P | P | P | Awards will be made to expand the HIV Criminal Justice Initiative (CJI) to link HCV-positive inmates to HCV care, treatment and supportive services upon release from prison |  | Contract has been executed
Funds will support enhanced hepatitis C surveillance and research activities:
| 10/1/2018 1/1/19 | 8 | 8 | 8 | a) HCV surveillance infrastructure;
| 2018-10-01 | P | P | P | b) Lab testing and utilization of new testing technologies to identify and respond to clusters of HCV among IDU networks; |  | Funding has been transferred to Wadsworth and the new technologies have been implemented.
| 2019-08-01 | 8 | 8 | 8 | c) HCV research;
| 2018-11-01 | 8 | 8 | 8 | d) BRFSS survey questions related to HCV diagnosis and treatment.
| 2019-03-31 | 8 | 8 | 8 | Funds will support a media campaign targeting the general public and at-risk populations.

## Ph. 8 Finance & Rate Setting
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2018-2019 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
11101 |  |  |  |  | Project Name: Indigent Care Workgroup Division Lead: DFRS Team Lead: Kevin Wright Additional Staff: Description: The Department will establish a temporary workgroup on hospital indigent care methodology which will make recommendations regarding Disproportionate Share Hospital (DSH) and Indigent Care Pool (ICP) funding. The workgroup shall convene no later than June 1, 2018 and create a report on its findings no later than December 1, 2018.
| 2018-06-01 | P | P | P | Announce workgroup chairs
| 2018-06-25 | P | P | P | Announce additional workgroup members
| 2018-07-11 | P | P | P | Meeting #1 - Goals, guiding principles, and education - NYC
| 2018-09-12 | P | P | P | Meeting #2 - Data sharing discussion (Part 1) - Albany
| 2018-10-10 | P | P | P | Meeting #3 - Data sharing discussion (Part 2) - if needed - NYC
| 2018-11-05 | 8 | 8 | 8 | Meeting #4 - Final workgroup recommendations - Albany
| 2018-11-21 | 8 | 8 | 8 | Submit workgroup findings draft report for Executive review
| 2018-12-01 | 8 | 8 | 8 | Release workgroup findings final report
11102 |  |  |  |  | Project Name: Quarterly Meetings on Medicaid Managed Care Rates Division Lead: DFRS Team Lead: Mike Dembrosky Additional Staff: Mark Shutts Description: The Executive commits to providing quarterly updates to the Legislature regarding Medicaid Managed Care rates. In the spirit of transparency, the Department, in conjunction with the Division of the Budget (DOB), will hold quarterly meetings with the chairpersons of the Senate and Assembly Health Committees, the Senate Finance Committee and the Assembly Ways and Means Committee. Staff from the offices of the chairpersons are welcome to participate in these monthly meetings in lieu of the elected official. The Department will also provide the actuarial memorandum which, pursuant to statute, is provided to managed care organizations 30 days in advance of submission to CMS. This document contains information regarding components of the premium (e.g. base amounts, trend percentages, category of service splits, etc.), add-on adjustments, quality pool amounts and various other Medicaid Managed Care rate development information. Finally, the Department will continue to provide the Legislature with all presentation materials disseminated at monthly managed care plan meetings.
| 2018-05-17 | P | P | P | April 2018 Rate Briefing
| TBD | P | P | P | Future Rate Briefings
11103 |  |  |  |  | Project Name: Nursing Home 1% ATB (4 Year Payback) Division Lead: DFRS Team Lead: Jada Eberle Additional Staff: Conor Petter Description: This proposal stretches out the repayment schedule of the Nursing Home 1% ATB retroactive payment (covering State fiscal years 2014-15 through 2017-18). | 35.00 | 4/1/18
| 2018-05-08 | P | P | P | Work with NH Associations to develop rate methodology
| 2018-06-21 | P | P | P | Submit SPA to CMS
| 2018-08-21 | P | P | P | Receive CMS approval of SPA
| 2018-08-21 | P | P | P | Prepare Rate Package
| 2018-08-24 | P | P | P | Submit Rate Package to Bureau for review & approval
| 2018-08-26 | P | P | P | Submit Rate Package to Division for review & approval
| 9/1/2018 10/10/18 | P | P | P | Submit Rate Package to Budget for review & approval
| 9/18/18 10/17/18 | 8 | 8 | 8 | Receive Rate Package Approved by DOB (pending DOB Approval)
| 9/18/18 10/229/18 | 8 | 8 | 8 | Submit payment to eMedNY
11104 |  |  |  |  | Project Name: Convert VBP-QIP / Other Supplemental programs to Essential Plan Division Lead: DFRS Team Lead: Mike Dembrosky Additional Staff: Rachel Hajos Description: This proposal converts supplemental programs from Medicaid to the Essential Plan thereby freeing up Global Cap resources. | (281.50) | 4/1/18
Programmatic Specifications
| 9/26/18 | 8 | 8 | 8 | Develop EP QIP Guidance Document
| 9/26/18 | 8 | 8 | 8 | Revise DY 4 VBP QIP Guidance Document
| TBD | 8 | 8 | 8 | Create EP QIP Facility MCO participation agreement
| 9/21/18 | 8 | 8 | 8 | Develop EP QIP Funding and Reporting Document for MCOs
| TBD | 8 | 8 | 8 | Develop EP QIP Website/Update VBP QIP Website
| 9/28/18 | 8 | 8 | 8 | Obtain executive signoff on all EP QIP guidance documents and agreements
| 9/12/18 | 8 | 8 | 8 | Legislative Briefing
| 9/12/18 | 8 | 8 | 8 | EP QIP Webinar for Stakeholders
| TBD | 8 | 8 | 8 | Prepare Stakeholder communication documentation
Rate Development
| 8/15/18 | P | P | P | Update EP Rates
| TBD | 8 | 8 | 8 | Rate Briefing with Managed Care Plans
| 2018-09-28 | P | P | P | EP Rates to DOB for Approval
| 2018-10-19 | 8 | 8 | 8 | DOB Approval of EP Rates
| 2018-10-19 | 8 | 8 | 8 | Load EP Rates
| 2018-09-28 | 8 | 8 | 8 | Update Mainstream Rates
| TBD | 8 | 8 | 8 | Rate Briefing with Managed Care Plans
| 2018-09-28 | 8 | 8 | 8 | Mainstream Rates to DOB for Approval
| 2018-10-19 | 8 | 8 | 8 | DOB Approval of Mainstream Rates
| 2018-11-19 | 8 | 8 | 8 | Load Mainstream Rates
11105 |  |  |  |  | Project Name: Rebate Risk Assessment Division Lead: DFRS Team Lead: Shaneeva Norbi Additional Staff: Mike Colabufo, Monica Toohey, PCG Description: This proposal allows the Department to engage with a vendor to perform an independent risk assessment of the rebate billing/collections protocols. | (15) | Merged from: MRT #9113 Effective Date: 4/1/18
| 5/7/18 | P | P | P | Identify and contract auditor |  | Shaneeva Norbi
| 5/18/18 5/25/18 | P | P | P | Develop scope and deliverables |  | Contractor/Shaneeva
| 6/26/18 | P | P | P | Meet to finalize scope of work |  | Contractor/Shaneeva
| 3/31/19 | 8 | 8 | 8 | Collection deadline for SFY 19 |  | Shaneeva Norbi
Audit Review
| 7/2/18 | 8 | 8 | 8 | Receive Medicaid Director approval of vendor -- Approval ON HOLD |  | Jackie McGovern/Shaneeva
| 7/6/18 | 8 | 8 | 8 | PCG contract arrangement finalized |  | Shaneeva Norbi
| 7/9/18 | 8 | 8 | 8 | Law and regulatory assessment begins |  | PCG
| 8/8/18 | 8 | 8 | 8 | Law and regulatory assessment ends |  | PCG
| 8/9/18 | 8 | 8 | 8 | Compliance Review begins |  | PCG
| 10/8/18 | 8 | 8 | 8 | Compliance Review ends |  | PCG
| 10/29/18 | 8 | 8 | 8 | Interim report w/ findings and recommendations submitted to DOH |  | PCG
| 10/30/18 | 8 | 8 | 8 | Compare findings to Magellan's implementation plan
| 11/9/18 | 8 | 8 | 8 | Summary of comparison to be submitted for review/ determine fiscal impact of Magellan's mitigation to PCG findings |  | Magellan/Shaneeva
| 11/15/18 | 8 | 8 | 8 | Conduct fiscal analysis of findings and recommendations not mitigated by Magellan from the Interim report |  | Shaneeva Norbi/ Mike Colabufo
| 11/29/18 | 8 | 8 | 8 | Final report of findings and recommendations due to DOH |  | PCG
| 12/5/19 | 8 | 8 | 8 | Prioritize findings and recommendations |  | PCG/ DOH
| 12/31/18 | 8 | 8 | 8 | Draft corrective action plan. |  | PCG/ DOH
| 1/1/19 | 8 | 8 | 8 | Implementation of corrective action plan. |  | Shaneeva Norbi/PCG
| 3/1/19 | 8 | 8 | 8 | Audit findings fiscal review |  | Shaneeva Norbi/ Mike Colabufo
System Changes
| 2018-09-20 | P | P | P | 5024 – Duplicate Pharmacy and Medical crossover claim fix | Moving to a different section | Monica Toohey
| 11/15/2018 | 8 | 8 | 8 | Fiscal impact review : identify associated dollars to be invoiced by this update | Moving to a different section | Shaneeva Norbi/ Mike Colabufo
| 2018-09-20 | P | P | P | 5864 – Validate submitted l code associated NDC’s |  | Monica Toohey
| 11/15/2018 | 8 | 8 | 8 | Fiscal impact review : identify associated dollars to be invoiced by this update |  | Shaneeva Norbi/ Mike Colabufo
| 4/25/18 | P | P | P | 5477 – eMedNY to Send Additional NDCs to MDW for Drug Rebate |  | Monica Toohey
| 9/17/18 11/15/18 | 8 | 8 | 8 | Prospective Fiscal impact review : identify associated dollars to be invoiced by this update |  | Shaneeva Norbi/ Mike Colabufo/Melissa Kamal
| 3/01/19 | 8 | 8 | 8 | Retroactively add NDCs to MDW for Drug Rebate |  | Shaneeva Norbi/ Mike Colabufo/Melissa Kamal
| 2018-08-29 | P | P | P | Invoice interest – ongoing |  | Magellan/Shaneeva Norbi
| 2018-10-31 | 8 | 8 | 8 | Interest Fiscal impact review |  | Shaneeva Norbi/ Mike Colabufo
11106 |  |  |  |  | Project Name: Implement a Penalty on poor performing Nursing Homes Division Lead: DFRS Team Lead: Rob Yankowski Additional Staff: Conor Petter Description: This proposal would use NHQP scoring and impose an additional 2% penalty to consistent poor performers by comparing low scoring quintiles for 2 consecutive years, and penalizing those who have scored either a 4:5 or 5:5 respectively. | (7.67) | 4/1/18 Completed - October 2018
| 2018-04-01 | P | P | P | Receive final Enacted Budget
| 2018-05-10 | P | P | P | Presented a draft list to Nursing Home Associations of Nursing Homes that would be penalized.
| 2018-06-22 | P | P | P | Submit SPA to CMS
| 2018-06-29 | P | P | P | Work with Nursing Home Associations to define financially distressed.
| 2018-07-10 | P | P | P | Finalize list of Nursing Homes subject to 2% penalty.
| 2018-08-21 | P | P | P | Receive CMS approval of SPA
| 2018-08-21 | P | P | P | Prepare Rate Package
| 2018-08-24 | P | P | P | Submit Rate Package to Bureau for review & approval
| 2018-08-26 | P | P | P | Submit Rate Package to Division for review & approval
| 2018-09-01 | P | P | P | Submit Rate Package to Budget for review & approval
| 2018-09-18 | P | P | P | Receive Rate Package Approved by DOB
| 2018-09-18 | P | P | P | Submit payment to eMedNY
11107 |  |  |  |  | Project Name: Rationalize Nursing Home Case Mix Index Increases Division Lead: DFRS Team Lead: Michelle Santos Additional Staff: James Conor Petter Description: The proposal is to work with the Nursing Homes Industry to revisit the current MDS Census Collection Process in an effort to promote a higher degree of accuracy in the MDS data which should result in a reduction of audit findings. | (7.50) | 4/1/18
| 7/25/2018 9/20/2018 | P | P | P | Work with Deloitte to develop initial proposal
| 2018-10-26 | P | P | P | Collect and process two Census uploads
| 08/08/18 10/15/2018 11/21/18 | 8 | 8 | 8 | Work with NH Associations to develop rate methodology
| 09/01/18 11/1/2018 | 8 | 8 | 8 | Prepare Rate Package
| 09/03/18 11/3/2018 | 8 | 8 | 8 | Submit Rate Package to Bureau for review & approval
| 09/08/18 11/12/2018 | 8 | 8 | 8 | Submit Rate Package to Division for review & approval
| 09/15/18 11/16/2018 | 8 | 8 | 8 | Submit Rate Package to Budget for review & approval
| 10/01/18 11/30/2018 | 8 | 8 | 8 | Receive Rate Package Approved by DOB
| 2018-12-15 | 8 | 8 | 8 | Submit payment to eMedNY
11108 |  |  |  |  | Project Name: Rural County Provider funding Division Lead: DFRS Team Lead: Rich Kappes Additional Staff: Laura Rosenthal, Frank Czernicki Description: This proposal would conduct a demo study looking at cost versus rates for rural county providers. The results of the analysis will allow the Department to increase rates where appropriate. | 1.50 | 4/1/18
| 2018-10-01 | P | P | P | Determine the counties eligible for payment Frontier and Remote (FAR) or PPS Rural County Designations
| 2018-10-01 | P | P | P | Determin breakout of funding for Personal Care /NHTD Waver/TBI program (requires Kissinger/Cater)
| 2018-10-01 | P | P | P | Conduct a rural Health Study.Use Cost Report to determine visits/staffing/income/expenses
| 2018-10-15 | P | P | P | Discus the current rate methodology and how the rural add on fits in with the current goals
| 2018-10-15 | P | P | P | Identify reimbursement issues
| 2018-10-15 | P | P | P | Develop recommendations
| 2018-10-31 | 8 | 8 | 8 | Select recommendation
|  | 8 | 8 | 8 | Meet with Rural Health Council for input
|  | 8 | 8 | 8 | Discuss Mythology to pay rural counties
|  | 8 | 8 | 8 | Select recommendation
|  | 8 | 8 | 8 | Modify SPA and Draft regulations for the new methodology (505.14)
|  | 8 | 8 | 8 | Submit SPA and regulations for the new methodology (505.14)
|  | 8 | 8 | 8 | Review and approval by DOH executives. Revise SPA to include updates to reimbursement
|  | 8 | 8 | 8 | Finalize and determine Rate
|  | 8 | 8 | 8 | Submit rate package for Executive review
|  | 8 | 8 | 8 | Publish updated finalized rate package
11109 |  |  |  |  | Project Name: Increase Current Penalties for Managed Care Plans that Fail to Meet VBP targets Division Lead: DFRS Team Lead: Roland Poirier Additional Staff: Description: This proposal increases VBP Roadmap penalties for MCOs that fail to achieve required levels of VBP contracting. | (10.00) | 4/1/18
| 2018-08-01 | P | P | P | Confirm the accuracy of plan-submitted VBPTR Data to be used for Penalty Assessment with DHPCO and DLTC
| 2018-08-13 | P | P | P | Review newly submitted DLTC data and reconfirm data with DHPCO and DLTC
| 8/15/18 8/29/18 11/2/18 | 8 | 8 | 8 | Calculate Penalty Adjustment Amounts & Communicate to Deloitte
| 10/1/18 11/2/18 | 8 | 8 | 8 | Include as an adjustment in the October Managed Care Rate Updates
11110 |  |  |  |  | Project Name: Increased MRT/Safety Net IGT Division Lead: DFRS Team Lead: Kevin Wright Additional Staff: Description: This proposal provides an increased MRT/Safety net IGT contribution from the SUNY system. | (46.30) | 4/1/18
| 9/18/2018 1/18/18 | 8 | 8 | 8 | DOH to request $22.56M SUNY IGT
| 9/24/2018 1/24/18 | 8 | 8 | 8 | SUNY to remit $22.56M IGT to DOH
| 2019-02-26 | 8 | 8 | 8 | DOH to request $22.56M SUNY IGT
| 2019-03-15 | 8 | 8 | 8 | SUNY to remit $22.56M IGT to DOH
11111 |  |  |  |  | Project Name: Safety Net (50% Safety Net 50% CHA & SCH) Division Lead: DFRS Team Lead: Monique Grimm Additional Staff: Description: This proposal provides additional funding for safety net hospitals, critical access hospitals, and sole community hospitals. | 50.00 | 4/1/18
| 8/14/18 9/28/18 | P | P | P | Create draft model for determining qualifying hospitals
| 8/21/18 10/5/18 10/9/18 | P | P | P | Review draft model for qualifying hospitals with hospital associations
| 9/21/18 10/26/18 10/11/18 | P | P | P | Finalize model for determining qualifying hospitals
| 9/28/18 11/2/18 10/9/18 | P | P | P | Create draft model for allocating funds to qualifying hospitals
| 10/5/18 11/9/18 10/9/18 | P | P | P | Review draft model for allocating funds with hospital associations
| 11/5/18 11/30/18 | 8 | 8 | 8 | Finalize model for allocating funds to qualifying hospitals
| 12/3/18 12/21/18 | 8 | 8 | 8 | Division of the Budget approval of rate package
| 12/10/18 12/28/18 | 8 | 8 | 8 | Provider/Health Plan Communications (Letters) developed for review & approval
| 12/17/18 12/31/18 | 8 | 8 | 8 | Communication to Hospitals
| 12/17/18 12/31/18 | 8 | 8 | 8 | Communication to Health Plans/Payment Distribution
11112 |  |  |  |  | Project Name: Enrollment Reconciliation Division Lead: DOS Team Lead: Alison Pingelski Additional Staff: Amit Bhaumik Description: This proposal provides funding related to enrollment discrepancies for CY 2014 and 2015 resulting from system related eligibility issues in NYSoH, WMS, and eMedNY impacting Managed Care plan's ability to bill capitated premiums. | 10 | 4/1/2018 Completed -September 2018 (Work is being reflected in DOS project management process)

## Ph. 8 Long Term Care
MRT Project # | Date | Scheudle | Senate | Assembly | Project/Task Description | Fiscal ($millions) | Status
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
11201 |  |  |  |  | Project Name: Admin Rate Reduction/Regulation Relief on MLTC Plans Division Lead: DLTC Team Lead: Rod Lloyd Kirk Dobson Additional Staff: Description: Reduce administrative portion of capitated rate from the current $215 per member per month (PMPM) to $200. $15 reduction. | -18.9 | Completed July 2018 Effective Date: 4/1/18
COMMUNICATIONS
| 2018-04-30 | P | P | P | Program Notice to Plans
| 2018-05-15 | P | P | P | DFRS Rate Presentation
RATES
| 2018-06-01 | P | P | P | Inclusion of Rate Adjustment in Rate Package
| 2018-07-01 | P | P | P | Approval of Rate Package
11202 |  |  |  |  | Project Name: Nursing Home Three Month Carve Out Proposal Division Lead: DLTC Team Lead: Laura Lehman Additional Staff: Sarah Atkinson, Kathy Loerzel Description: Limits the permanent NH benefit to a period of 3 months (exclusive of the Medicare benefit) | 75 | Effective Date: 5/1/18 12/15/18
PROVIDER COMMUNICATIONS
| 2018-05-15 | P | P | P | Hold 1st Stakeholder Meeeting
| 2018-06-13 | P | P | P | Hold 2nd Stakeholder Meeting
| 7/30/2018 9/4/2018 | 8 | 8 | 8 | Hold 3rd Stakeholder Meeting
| 2018-08-30 | 8 | 8 | 8 | Hold 4th Stakeholder Meeing
| 2018-10-01 | 8 | 8 | 8 | Medicaid Update Article on Intention to Disenroll Members
| 2018-12-01 | 8 | 8 | 8 | Release Applicable Policies to DOH Website
| 2018-12-01 | 8 | 8 | 8 | Publish Instructions on Effectuating Policy on DOH Website
ENROLLEE COMMUNICAITONS
| 2018-12-01 | 8 | 8 | 8 | Release Revised Notice to all MLTC consumers on the cessation of auto-enorllment
| 2018-12-01 | 8 | 8 | 8 | Release Notice of Permanent Placement and Intent to Disenroll to Eligible Enorllees for Disenrollment
| 2019-01-01 | 8 | 8 | 8 | MLTC Plans to update all member materials and handbooks in accordance with DOH guidance
PLAN AND LDSS COMMUNICATIONS
| 2018-08-09 | 8 | 8 | 8 | Plan Update - All Plan Meeitng
| 2018-11-15 | 8 | 8 | 8 | Communication to Plan on Auto-Enrollment Cessation Notification to Consumers
| 2018-10-15 | 8 | 8 | 8 | Release Plan Guidance Document on Disenrollment Procedures
| 2018-10-15 | 8 | 8 | 8 | Releease GIS to LDSS
| 2018-11-15 | 8 | 8 | 8 | LDSS Webinar on Procedures and Processes
| 2018-12-05 | 8 | 8 | 8 | Release Systems FAQ document
1115 AMENDMENT
| 2018-07-03 | P | P | P | Publish Public Notice
| 2018-07-03 | P | P | P | Publish Tribal Notice
| 7/1/2018 8/1/18 | 8 | 8 | 8 | Budget Neutrality Document Completed
| 2018-07-01 | P | P | P | DRAFT 1115 Amendment Completed
| 8/3/2018 8/24/2018 | ▲ | ▲ | ▲ | Submit 1115 amendment to CMS
| 2018-12-01 | ▲ | ▲ | ▲ | Receive CMS Approval
SPA
| 2018-10-01 | ▲ | ▲ | ▲ | Draft SPA for applicable chagnes
| 2018-12-01 | ▲ | ▲ | ▲ | Send SPA to CMS for Approval
REGULATORY
| 2018-08-01 | 8 | 8 | 8 | Evaluate regulations for modification/updates to be in compliance with statutes
| 2018-08-15 | 8 | 8 | 8 | Evaluate audit needs with OMIG
SYSTEMS
| 2018-12-01 | 8 | 8 | 8 | Cease Auto-Enrollment / "Close the Front Door"
| 2018-12-01 | 8 | 8 | 8 | Re-assign N6/N7 codes for permanent placement tracking
| 2018-12-01 | 8 | 8 | 8 | Effectuate necessary systems changes with Enrollment Broker
| 2018-12-01 | 8 | 8 | 8 | Effectuate necessary E-MedNY edits
| 2018-12-01 | 8 | 8 | 8 | Make changes to Form 3559 / HRA 2159i
| 2018-12-15 | 8 | 8 | 8 | Begin Disenrollments / "Close the Back Door"
11203 |  |  |  |  | Project Name: Restrict LHCSA Contracts with MLTCPs Division Lead: DLTC Team Lead: Erin Kate Calicchia Additional Staff: Description: Reduce the number of LHCSAs | -13.71 | Effective Date: 10/1/18 Completed - October 2018
COMMUNICATIONS
| 7/10/18 8/3/18 | P | P | P | Finalize Guidance Document
| 7/13/18 8/10/18 8/25/18 | P | P | P | Distribute Guidance Document to plans and providers
| 8/9/2018 9/6/2018 | P | P | P | Update to Plans - All Plan Meeig
RATES
| 2018-10-01 | P | P | P | Inclusion of Rate Adjustment in Rate Package
REGULATORY
| 2018-08-01 | P | P | P | Evaluate regulations for modification/updates to be in compliance with statutes
| 8/15/2018 10/1/2018 | P | P | P | Evaluate audit needs with OMIG
SYSTEMS
| 2018-09-01 | P | P | P | Make changes to PNDS requirements and release guidance if necessary
SURVEILLANCE
| 2018-09-01 | P | P | P | Incorporate changes into DLTC audit protocols
| 2018-10-01 | P | P | P | New ratios apply to plan contracts
11204 |  |  |  |  | Project Name: Restrict Memebers from Transfering Plans for a Period of 12 Months / MLTC Lock-In Proposal Division Lead: DLTC Team Lead: Kirk Dobson Additional Staff: Karis Browder Description: Restrict MLTC members from transitioning from plan to plan | -5.23 | Effective Date: 10/1/18
COMMUNICATIONS
| 2018-10-01 | 8 | 8 | 8 | Medicaid Update Article
| 2018-10-15 | 8 | 8 | 8 | Notification to MLTC Plans on intention to begin policy
| 2018-11-01 | 8 | 8 | 8 | Notice to MLTC Consumers on new restrictions
1115 AMENDMENT
| 2018-07-03 | P | P | P | Publish Public Notice
| 2018-07-03 | P | P | P | Publish Tribal Notice
| 7/1/2018 8/1/18 | 8 | 8 | 8 | Budget Neutrality Document Completed
| 2018-07-01 | P | P | P | DRAFT 1115 Amendment Completed
| 8/3/2018 8/24/2018 | ▲ | ▲ | ▲ | Submit 1115 amendment to CMS
| 2018-12-01 | ▲ | ▲ | ▲ | Receive CMS Approval
REGULATORY
| 2018-08-01 | P | P | P | Evaluate regulations for modification/updates to be in compliance with statutes
| 8/15/2018 10/1/2018 | 8 | 8 | 8 | Evaluate audit needs with OMIG
SYSTEMS
| 2018-06-01 | P | P | P | Finalize Systems changes with Enorllment Broker
| 2018-12-09 | 8 | 8 | 8 | Effectuate 12 month policy with Enrollment Broker
| 2018-12-09 | 8 | 8 | 8 | Effectuate good cause exemptions policy with Enrollment Broker
| 2019-01-14 | 8 | 8 | 8 | Effectuate one transfer in 90 days policy with Enrollment Broker
RATES
| 2018-10-01 | 8 | 8 | 8 | Include efficiency adjustment in October Rates
11205 |  |  |  |  | Project Name: Require a Continuous 120 Days of CBLTC Division Lead: DLTC Team Lead: Kirk Dobson Additional Staff: Erin Kate Calicchia Description: Require a Continuous 120 Days of CBLT and to implement a UAS score of 9 for MLTC eligibility | 11.65 | Completed May 2018
11206 |  |  |  |  | Project Name: FI Marketing Restriction Division Lead: DLTC Team Lead: Karis Browder Additional Staff: Jennifer Alhart, Michela Paniccia Description: Monitor FI Marketing | -4.93 | Effective Date: 4/1/18 Completed October 2018
COMMUNICATIONS
| 7/1/2018 8/1/18 | P | P | P | Finalize Guidance Document
| 7/13/2018 8/13/18 8/24/2018 | P | P | P | Release Informational Notice to plans
| 8/1/2018 9/1/2018 | P | P | P | Medicaid Update Article
AUTHORIZATION
| 7/15/2018 8/20/18 | P | P | P | Integrate marketing requirements within FI authorization process
11207 |  |  |  |  | Project Name: Authorization vs. Utilization Adjustment for MLTC Division Lead: DLTC Team Lead: Kirk Dobson Additional Staff: Description: Identifying members who are authorized for services within Managed Long Term Care, but not actively utilizing the services | -1.24 | Effective Date: 10/1/18
COMMUNICAITONS
| 2018-03-09 | P | P | P | Medicaid Update
| 3/19/2018 9/1/18 | 8 | 8 | 8 | Plan Informational Notice Document
POLICY
| 2018-07-27 | ▲ | ▲ | ▲ | Finalize Involuntary Disenrollment Policy
| 2018-08-03 | ▲ | ▲ | ▲ | Release Involuntary Disenrollment Policy
| 2018-08-01 | ▲ | ▲ | ▲ | Release Guidance to Plans on Involuntary Disenrollment Policy
| 2018-10-01 | ▲ | ▲ | ▲ | Finalize Involuntary Disenrollment Policy and implement with Enrollment Broker
11208 |  |  |  |  | Project Name: Social Adult Day Benefit Efficiency Savings Division Lead: DLTC Team Lead: Kirk Dobson Additional Staff: Shipra Iyer, Karis Browder Description: To allow MLTC plans to target the social day care benefits more efficiently, and adjust member utilization as necessary based on guidance and education | -28.13 | Effective Date: 10/1/18
COMMUNICATIONS
| 7/20/2018 8/7/18 8/23/18 | 8 | 8 | 8 | First Tri-Agency Meeting with OMIG and SOFA
| 2018-08-20 | 8 | 8 | 8 | Final Tri-Agency Meeting with OMIG and SOFA
| 2018-09-07 | 8 | 8 | 8 | Finalize Guidance Document for Plans
| 2018-09-14 | 8 | 8 | 8 | Release Guidance to Plans
| 2018-11-01 | 8 | 8 | 8 | Medicaid Update
POLICY
| 2018-10-01 | 8 | 8 | 8 | Finalize Social Adult Day changes and release policy document if necessary
RATES
| 2018-10-01 | 8 | 8 | 8 | Include efficiency adjustment in October Rates
11209 |  |  |  |  | Project Name: LHCSA/FI Cost reports Division Lead: DFRS Team Lead: Jack Pitera Additional Staff: Kirk Dobson; Karis Browder, Anthony Guidi Description: Reporting of cost incurred by LHCSA/ FI / Health Homes |  | Effective Date: 4/1/18
COMMUNICATIONS
| 2018-08-01 | 8 | 8 | 8 | Medicaid Update
| 7/20/2018 8/31/18 | 8 | 8 | 8 | Finalize Guidance to Providers on Submitting Cost Reports
| 7/20/2018 9/7/18 | 8 | 8 | 8 | Release Guidance to Providers on Submitting Cost Reports
| 2018-08-03 | 8 | 8 | 8 | Release FAQs if necessary
SYSTEMS
| 2018-07-27 | 8 | 8 | 8 | Finalize Cost Report Survey with OPA
| 2018-08-03 | 8 | 8 | 8 | Release Cost Report to Providers
| 2018-11-01 | 8 | 8 | 8 | Cost Reports due back to DOH
REGULATORY
| 2018-08-01 | 8 | 8 | 8 | Evaluate regulations for modification/updates to be in compliance with statutes
| 2018-08-15 | 8 | 8 | 8 | Evaluate audit needs with OMIG
SURVEILLANCE
| 2018-09-01 | 8 | 8 | 8 | Incorporate changes into DLTC audit protocols as necessary
11210 |  |  |  |  | Project Name: Oversight and Reporting On MLTC Plan Closures Division Lead: DLTC Team Lead: Donna Lochner Additional Staff: Description: Reporting of plan closures, mergers and acquisitions |  | Canceled July 2018 Effective Date: 4/1/18
COMMUNICATIONS
| 2018-11-01 | 8 | 8 | 8 | Release Informational Notice to plans
POLICY
| 2018-11-01 | 8 | 8 | 8 | Update and release policy reflecting requirements on closing plans
| 2018-11-01 | 8 | 8 | 8 | Create reporting structure for releasing reports
SURVEILLANCE
| 2018-11-01 | 8 | 8 | 8 | Incorporate changes into DLTC audit protocols as necessary
REGULATORY
| 2018-08-01 | 8 | 8 | 8 | Evaluate regulations for modification/updates to be in compliance with statutes
| 2018-08-15 | 8 | 8 | 8 | Evaluate audit needs with OMIG

## Ph. 8 Prog Dev & Mgmt
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2018-2019 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
11301 |  |  |  |  | Project Name: Congestion Surharge for Fee -For-Service Transportation Division Lead: Division of Program Development and Management Integration Team Lead: Mark Bertozzi Additional Staff: Josh Blair; Robert Schmit Description: The Department will pay the Medicaid transportation fee plus the cost of congestion pricing using amounts transferred to the Department for that purpose. The Department will also issue a Medicaid Update to clarify that Medicaid transportation providers (i.e. livery, etc.) will be held harmless from congestion pricing. | 0
| 6/8/18 | P | P | P | Reach agreement with Medicaid Transportation Manangers on two surcharge ($2.75 , $0.75) procedure code modifiers
| 6/22/18 6/28/18 7/31/18 | P | P | P | Implement new surcharge procedure codes and fees in EmedNY
| 6/29/18 7/31/18 8/31/18 | P | P | P | Post Fees on public portion of Emedny
| 7/15/18 9/7/18 9/15/18 | P | P | P | Medicaid Update Article for fee-for-service transportation providers
| 8/1/18 9/15/18 11/15/18 | 8 | 8 | 8 | Transportation Managers send out Alert -and conduct outreach
| 10/1/18 11/1/18 | 8 | 8 | 8 | Transortation Managers complete requested in-service training
| 12/1/18 | 8 | 8 | 8 | MLTC determines how it will report sucharge payments to the Commisioner of Health
| 2019-04-30 | 8 | 8 | 8 | Commissioner of Health collects transportation data to determine the 1st Quarter amount transferred from the MTA Account to the MMIS Escrow Fund
| 2019-04-30 | 8 | 8 | 8 | Fund Transfer from MTA to Medicaid for 1st Quarter 2018 surcharge payments
| 2019-06-10 | 8 | 8 | 8 | Commissioner of Health collects transportation data to determine the 2nd Quarter amount transferred from the MTA Account to the MMIS Escrow Fund with 1st Quarter reconciliation.
11302 |  |  |  |  | Project Name: Update Professional Dispensing Fee Division Lead: DPDM Team Lead: Carol Lindley Additional Staff: Monica Toohey Description: This proposal updates the professional dispensing fee for brand name, generic, and OTC covered outpatient drugs to align with current costs. | 0.4 | Effective Date: 4/1/18
| 2018-04-01 | P | P | P | Enacted Budget For Pharmacy Reimbursement
| 2018-04-17 | P | P | P | Draft and Submit SPA for Internal/Executive Approval
| 2018-06-30 | P | P | P | Submit SPA To CMS |  | Submitted on 6/22/18
| 2018-09-30 | P | P | P | CMS Approval of SPA |  | Approved 9/5/2018
| 2018-11-05 | 8 | 8 | 8 | Provider Communication
| 2019-01-24 | 8 | 8 | 8 | Implement Change in Professional Dispensing Fee
| 2019-03-04 | 8 | 8 | 8 | Issue policy guidance on repricing Pharmacy claims retro to 04/01/2018
| 2019-04-25 | 8 | 8 | 8 | Reprice retro claims
11303 |  |  |  |  | Project Name: Reduce Opioid Use by 20% by 2020 | -1.1 | Effective Date: 7/1/18
Division Lead: Janet Zachary-Elkind- DPDM
Team Lead: Monica Toohey
Additional Staff: Alda Osinaga, Tracy Berger, Melissa Kamal, Barb Rogler, OMIG, OASAS
Description: This proposal will build on the State’s effort to combat the opioid crisis by: implementing patient/prescriber treatment plans/agreements as a requirement for opioid prescribing; modifying formularies and/or claims editing to allow access to non-opioid alternatives without prescriber intervention, when indicated in claims history. Such alternatives include but are not limited to acetaminophen, Nonsteroidal Anti-inflammatory Drugs (NSAIDs), cyclooxygenase 2 (COX-2) inhibitors; and selected anticonvulsants and antidepressants.
| 2018-06-25 | P | P | P | Develop initial components to a treatment plan
| 8/31/2018 | P | P | P | Get comments on treatment plan criteria (OMIG, MCO’s, OASAS & other state agencies)
| 2018-09-15 | 8 | 8 | 8 | Get comments on treatment plan criteria (MSSNY & provider groups)
|  | 8 | 8 | 8 | Implement treatment plan agreements
|  | 8 | 8 | 8 | Instruct practitioners on implementation of treatment plans
|  | 8 | 8 | 8 | Oversite of treatment programs
| 2018-07-11 | P | P | P | Evaluate MCO coverage for non-opioids pain medications
| 2018-07-30 | P | P | P | Make recommendations to MCO's on their adherence program
| 9/15/2018 10/2/18 | 8 | 8 | 8 | Instruct MCO's on access to non-opioid pain medications
|  | 8 | 8 | 8 | Evaluate MCO compliance to non-opioid pain medications
11304 |  |  |  |  | Project Name: Medication Adherence | -5 | Effective Date: 4/1/18
Division Lead: Janet Zachary-Elkind- DPDM
Team Lead: Monica Toohey
Additional Staff: Tracy Berger, Melissa Kamal, Barb Rogler
Description: This proposal will require managed care plans to develop and implement medication adherence programs for people with chronic health conditions such as hypertension, HIV-AIDs, diabetes and mental illness. Low medication adherence may lead to potentially avoidable morbidity, mortality and negative outcomes. The Department of Health will work with the managed care plans to:
- develop and implement best practice medication adherence strategies and plan incentives;
- implement stakeholder engagement approaches; and
- evaluate regulations/possible regulation relief that would encourage stakeholder and patient engagement, in support of improved medication adherence.
| 2018-06-18 | P | P | P | Organize a workgroup to discuss adherence programs & how MCO's can comply
| 8/31/2018 9/15/18 | 8 | 8 | 8 | Establish requirements for adherence programs
| 8/31/2018 9/15/18 10/19/2018 | P | P | P | Survey MCO's about adherence programs |  | Janet Zachary-Elkind/Tracy Berger/Aditi Kallianpur
| 9/30/2018 10/30/18 | 8 | 8 | 8 | Make recommendations to MCO's on their adherence program
| 2019-01-01 | 8 | 8 | 8 | Implement an adherence programs requirement for the MCO's
| 2019-04-01 | 8 | 8 | 8 | Evaluate MCO compliance to adherence programs & outcomes
11305 |  |  |  |  | Project Name: Optimize Outreach Resources for High Risk Members Division Lead: DPDM Team Lead: Peg Elmer Additional Staff: Nancy Pleickhardt Description: Reducing outreach and turn over the balance of outreach resource to managed care plans to administer under state guidelines, i.e. apply Health Home outreach efforts to the highest risk members with the highest utilization – eliminating cold calls from assigned lists
| 2018-10-01 | 8 | 8 | 8 | Outreach Optimization
| 2018-05-23 | P | P | P | FPN
| 6/30/2018 6/26/18 | P | P | P | SPA Submission-to reduce Outreach Rate
| 2018-06-05 | P | P | P | DOH/Plan Q&A
| 2018-06-22 | P | P | P | HH/MCO Quality Summit
| 7/15/2018 7/20/18 | P | P | P | Issue menu of preapproved Outreach Proposals and Template for submission
| 8/31/2018 10/9/18 | 8 | 8 | 8 | Plan deadline for submission of Outreach Proposals
| 9/15/2018 10/23/18 | 8 | 8 | 8 | Issue Outreach Proposal detreminations to Plans
11306 |  |  |  |  | Project Name: Ensure Health Home Connectivity with RHIOs Division Lead: DPDM Team Lead: Sherry Piscitella Additional Staff: Dan Schiller Description: Ensuring Health Homes are complying with requirements pertaining to connectivity with Regional Health Information Organizations (RHIOs) to support case management and service connectivity
| 12/31/18 | 8 | 8 | 8 | Continue follow-up monthly with HHs on RHIO status
| 12/31/18 | 8 | 8 | 8 | Work with NYeC to obtain HH-RHIO connectivity data quarterly
11307 |  |  |  |  | Project Name: Health Home Performance Initiative Division Lead: DPDM Team Lead: Sherry Piscitella Additional Staff: Description: Provide public reports on health home quality data by health homes including standardized scorecards of comparative Health Home performance | (15.00) | Effective: 4/1/18
| 7/11/18 8/15/18 9/26/18 10/26/18 | 8 | 8 | 8 | Complete 2016 Report Card draft and supporting visualizations for approval
| 7/25/18 9/25/18 10/19/18 11/2/18 | 8 | 8 | 8 | Obtain 2017 data and update Report Card and supporting visualizations for approval
| 7/27/18 9/30/18 10/5/18 11/7/18 | 8 | 8 | 8 | Distribute 2016 and 2017 Report Care to HHs via Atrium
| 7/31/18 9/30/18 10/5/18 | P | P | P | Determine if 2016, 2017 or both will be publicly posted on website
11308 |  |  |  |  | Project Name: Criminal Background Checks Division Lead: DPDM Team Lead: Nichole Katz Additional Staff: Description: Requires Health Home care managers serving children and individuals with intellectual and developmental disabilities, and home and community based providers authorized to provide services under the 1115 waiver (upon approval) to children under 21 to get a criminal background check. Subjects such care managers and providers to State Central Registry checks and makes them mandated reporters. | 1.1 | Effective: 4/1/18
| 2018-04-01 | P | P | P | Enacted Budget For Criminal Background Checks
| 5/17/18 | P | P | P | Hold provider webinars explaining requirements and steps to compliance
| 6/1/18 | P | P | P | Provide HCS access to CCO/HHs (CHRC)
| 8/1/2018 10/1/18 | 8 | 8 | 8 | Provide CHRC access to providers with HCS access (HHSC, HHSA, CMA, CCO)
| 8/1/2018 9/15/18 10/15/18 | 8 | 8 | 8 | Provide OCA access for SCR (for HHSA, HHSC, CMA, CCO, MSC)
| 8/1/2018 9/15/18 10/15/18 | 8 | 8 | 8 | Provide SEL system access (HHSC, HHSA, CMA)
| 9/1/2018 10/1/18 | 8 | 8 | 8 | Provide HCS access to MSCs (CHRC)
| 2018-10-01 | 8 | 8 | 8 | Provide CHRC access to MSCs (CHRC)
| 2018-11-01 | 8 | 8 | 8 | Hold onboarding for children's waiver providers
| 2018-12-01 | 8 | 8 | 8 | Begin systems onboarding for children's waiver providers
| 2019-02-01 | 8 | 8 | 8 | Complete systems onboarding for children's waiver providers |  | Effective: 4/1/18
11309 |  |  |  |  | Project Name: Health Home Healthy Rewards Division Lead: DPDM Team Lead: Peggy Elmer Additional Staff: Description: | (15.00) | Effective Date: 4/1/18 Completed August 2018
| 2018-06-07 | P | P | P | DOH/Plan Q&A
| 2018-06-22 | P | P | P | HH/MCO Quality Summit standardize parameters
| 7/30/2018 8/16/18 | P | P | P | Issue guidance document to plans
11310 |  |  |  |  | Project Name: Health Homes - Quality Improvements Division Lead: DPDM Team Lead: Peg Elmer Additional Staff: Description: Health Home Quality Incentive Pool rewards high performing Health Homes that meet performance goals and impose penalties on underperforming Health Homes.
| 2018-10-01 | 8 | 8 | 8 | Health Home Quality Incentive Program
| 2018-06-20 | P | P | P | HH/MCO Work Group Quality Subcommittee draft recommendations | 0.00 | Effective: 4/1/18
| 2018-06-22 | P | P | P | HH/MCO Qualtiy Summit
| 2018-07-31 | P | P | P | HH/MCO Quality Subcommitee revision of recommendations based on summit feedback
| 8/31/2018 10/29/18 | 8 | 8 | 8 | Issue Draft subset of measures for Quality Incentive Payment
| 9/30/2018 11/12/18 | 8 | 8 | 8 | Issue State approved subset of measures for Quality Incentive Payments (QIP) 18-19
11311 |  |  |  |  | Project Name: Increase annual PT visit limit Division Lead: DPDM Team Lead: Melissa Kinnicutt Additional Staff: Allie Naigles-Norwood Description: Annual physical therapy visit limit increasing from 20 to 40
| 3/28/2018 | P | P | P | Publish Federal Public Notice
| 5/25/2018 | P | P | P | Draft SPA
| 7/1/2018 9/1/18 9/27/18 | P | P | P | Submit SPA to CMS
| 6/15/2018 | P | P | P | Draft Change Request Form (CRF) for eMedNY/DVS system support
| 6/25/2018 7/27/18 | P | P | P | Submit Change Request Form for eMedNY/DVS system support
| 8/1/2018 9/1/18 11/15/18 | 8 | 8 | 8 | Obtain CMS approval for SPA
| 9/1/2018 9/27/18 11/30/18 | 8 | 8 | 8 | Publish Medicaid Update announcing benefit limit change after SPA approval
| 9/1/2018 1/1/19 | 8 | 8 | 8 | Publish Updated Rehabilitation Provider Policy Manual after SPA approval
11312 |  |  |  |  | Project Name: Medicaid Max for Article 28 TBI waiver Division Lead: DPDM Team Lead: Melissa Kinnicutt Additional Staff: Allie Naigles-Norwood Description: Pay Article 28 the difference between the Medicaid rate and the Medicare payment or the Medicare Part B coinsurance amount, whichever is higher for TBI waiver members.
| 4/25/2018 | P | P | P | Publish Federal Public Notice
| 7/1/2018 | P | P | P | Draft SPA
| 6/15/2018 | P | P | P | Draft Change Request Form for eMedNY system support of pricing change
| 7/1/2018 | P | P | P | Submit SPA to CMS
| 6/25/2018 7/27/18 | P | P | P | Submit Change Request Form for eMedNY system support of pricing change
| 8/1/2018 9/1/18 | P | P | P | Obtain CMS approval for SPA
| 9/1/2018 2/15/18 | 8 | 8 | 8 | Publish notification to providers via eMedNY listserv after SPA approval
11313 |  |  |  |  | Project Name: Reduce Overutilization of Laboratory Services Division Lead: DPDM Team Lead: Additional Staff: Description: This proposal reduces overutilization of laboratory services through establishment of clinically determined efficiency standards | (7.50) | Effective: 4/1/18 Completed (No Workplan Needed) October 2018

## Compete Plans
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2017-2018 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
[5 empty] | Project Name: Adult Day Health Care (ADHC) Transportation Division Lead: DPDM/DLTC Description: The Department will refrain from taking administrative actions intended to carve out the provision of Medicaid transportation from the ADHC programs reimbursed to manage their own transportation to Fee-For-Service under the administration of the State’s transportation manager during State Fiscal Year 2019. |  | No Workplan - Continuation of Current Policy
[5 empty] | Project Name: Medicaid Transportation Livery Reimbursement Rates in New York City Division Lead: DPDM/DFRS Description: The Department will refrain from taking administrative actions that would reduce the rate of reimbursement to New York City Medicaid livery transportation providers in State Fiscal Year 2019. |  | No Workplan - Continuation of Current Policy
[5 empty] | Project Name: Separate Rate Cells or Risk Adjustment for Specific Population Division Lead: DFRS Team Lead: Reneta Robinson Description: The Department commits to exploring separate rate cells or risk adjustments for the nursing home, high cost / high need home and personal care, and Health and Recovery Plan (HARP) populations. The Department will re-engage the Centers for Medicare and Medicaid Services (CMS) regarding this reimbursement methodology with the assistance of health care industry stakeholders impacted by these changes (e.g. advocates, providers and managed care organizations). |  | No Workplan - Continuation MRT #10202
[5 empty] | Project Name: Global Cap Target Division Lead: DFRS Team Lead: Additional Staff: Description: DOB target to achieve Medicaid savings. | 425 | No Workplan Needed
[5 empty] | Project Name: Outstanding Federal Obligations Division Lead: DFRS Team Lead: Mark Shutts Additional Staff: Description: This proposal provides funding to cover outstanding federal obligations | 132.95 | No Workplan Needed
[5 empty] | Project Name: 2018-19 GC Base Deficit Division Lead: DFRS Description: The GC base is projecting a deficit primarily due to MLTC enrollment growth. | 0 | No Workplan Needed
[5 empty] | Project Name: 1115 Waiver Transition - Childrens Division Lead: DFRS |  | No Workplan - Continuation of Previous MRT
[5 empty] | Project Name: Additional Hospice funding Division Lead: DFRS Team Lead: Russ Smith Description: The proposal is to establish a 10 percent rate increase to the Hospice Residence rates, set a benchmark rate and include specialty rates in the weighted average rate calculation. |  | No Workplan Needed
[5 empty] | Project Name: Reduce AR Balances Division Lead: DFRS Team Lead: Adele Compton Additional Staff: Description: This proposal allows the State to begin an Enhanced Recover Initiative to reduce/eliminate outstanding accounts receivable balances owed to the State by providers. | -12.55 | No Workplan - Continuation of Previous MRT
[5 empty] | Project Name: Ambulance Fee Increase Division Lead: DPDM Team Lead: Additional Staff: Description: This proposal includes funding to support an ambulance rate increase. | 6.28 | Completed
[5 empty] | Project Name: MCO Tax Repeal Division Lead: DFRS Team Lead: Mike Dembrosky Additional Staff: Description: Section 9010 of the ACA imposes a Health Insurance Providers Fee (HIPF) for any covered entity whose business operations provide health insurance for United States health risks. This tax is suspended for Calendar Year 2019. | -3.9 | No Workplan Needed
[5 empty] | Project Name: Proportionally Reduce Managed Care Quality Pools Division Lead: DFRS Team Lead: Mike Dembrosky Additional Staff: Description: This proposal reduces the Managed Care Quality pools proportionately between Mainstream Managed Care and Managed Long Term Care based on program spending. The reductions will be taken from the lower tiers consistent with prior year budget actions. | -12.97 | No Workplan Needed
[5 empty] | Project Name: Reimbursement rates for Crouse Community Center Division Lead: DFRS Team Lead: Rob Yankowsky Additional Staff: Description: This proposal provides a FFS rate increase of 17 percent and a MC rate increase of 4 percent. | 0.35 | No Workplan Needed
[5 empty] | Project Name: Division Lead: DPDM Team Lead: Additional Staff: Description: Allowing managed care plans to contract based on performance and outcomes |  | No Workplan Needed
[5 empty] | Project Name: Division Lead: DPDM Team Lead: Additional Staff: Description: Continuing to work closely with the Office of the Medicaid Inspector General (OMIG) on Health Home related issues and audits |  | No Workplan Needed
[5 empty] | Project Name: First One Thousand Days Division Lead: DPDM Team Lead: Kalin Scott Additional Staff: Description: This proposal implements the first 1,000 Days 10-point plan | 1.45 | Effective: 4/1/18 No Workplan Needed - Reflected in own workgroup
[5 empty] | Project Name: Supportive Housing Division Lead: DPDM Team Lead: Denard Cummings Additional Staff: Description: This proposal provides funding for supportive housing for high cost Medicaid members. Such proposal would work with Plans, VBP contractors, & PPSs to move high utilizers who are homeless into housing. Such proposal would also expand to families in conjunction with the First 1,000 days. | 0.00 | Effective: 4/1/18 No Workplan Needed - Reflected in VBP workgroup
[5 empty] | Project Name: Reducing Unnecessary Utilization - Physical Therapy Cap Division Lead: DPDM Team Lead: Melissa Kinnicutt Additional Staff: Description: This proposal provides funding into preventive services. | 2.29 | Effective: 4/1/18 No workplan needed - Project being completed under different name "Increase annual PT visit limit"
[5 empty] | Project Name: Monthly Meetings on Medicaid Global Cap Division Lead: DFRS Team Lead: Mark Shutts Additional Staff: Description: The Executive commits to monthly meetings with the Legislature during the third Wednesday of every month to provide an update on actual spending to-date and potential changes to projections for the remainder of the State Fiscal Year (May 16, June 20, July 18, August 15, September 19, October 17, November 21, December 19, January 16, February 20 and March 20). The agenda for such meetings shall be agreed upon by the Department and the Legislature. In addition, the Global Cap report will be expanded to include information on all non-Medicaid expenditures made out of Global Cap resources or any material changes on the program in the last month. |  | No workplan needed - Regularly Scheduled Continuous meetings
[5 empty] | Project Name: Correct APG Weights for IV Infusion/Hydration Bags Division Lead: DPDM Team Lead: Mary Jane O'Brien Additional Staff: Description: This proposal reduces the amount paid via the Medicaid ambulatory patient group (APG) methodology to emergency departments and hospital outpatient departments for IV infusion/hydration using saline. The APG payment for each saline bag is approximately $500.00. This proposal would reduce the payment by 50% or to approximately $250.00 per bag. | (5.03) | Effective: 4/1/18 No Workplan Needed - Implemented
[5 empty] | Project Name: Remove Originating Site Requirement from Telehealth Program Division Lead: DPDM Team Lead: Kendra Muckle Additional Staff: Description: This proposal assumes savings associated with removing the originating site requirement in the telehealth program. | (5.00) | Effective: 10/1/18 No workplan needed
[5 empty] | Project Name: Telehealth Expansion Division Lead: DPDM Team Lead: Kendra Muckle Additional Staff: Description: Telehealth is being expanded to include additional originating sites, including the patient’s place of residence or other temporary location, and additional provider-types who may render services via telehealth. | (10.00) | Effective: 4/1/18 No workplan needed
[5 empty] | Project Name: Evaluate Efficacy of Health Home Cost Reporting Division Lead: DPDM Team Lead: Laura Moretti Additional Staff: Description: Working to expand cost reports to include more specific itemization of cost and volume for care management |  | No Workplan Needed - Captured in MRT #11309
[5 empty] | Project Name: Division Lead: DPDM Team Lead: Additional Staff: Description: Ensuring quality by evaluating and collecting information on CMS required quality metrics. These measures will be share with managed care plans and made public as part of the Health Home Performance Management Program. Underperforming Health Homes will be subject to penalties under a State Quality Pool Initiative |  | No Workplan Needed- Captured in MRT #11310
[5 empty] | Project Name: Division Lead: DPDM Team Lead: Additional Staff: Description: Working with managed care plans to evaluate the recent changes allowing plans to contract directly with care management organizations to determine if additional flexibility is needed | 1.10 | No Workplan Needed - Captured in MRT #11305
[5 empty] | Project Name: Penalty for Failure to Enroll High Risk Plan Members in Health Homes Division Lead: DPDM Team Lead: Additional Staff: Description: Plans will be assessed a penalty for failure to enroll HARP and other high risk, high cost members (adults or children) in Health Homes | (15.00) | No Workplan Needed - Captured MRT #11309
[5 empty] | Project Name: Health Home Healthy Rewards Program Division Lead: DPDM Team Lead: Additional Staff: Description: Plan administered rewards program for Health Home members that participate in wellness and preventative care (e.g., annual physicals, smoking cessation, continuous enrollment in Health Homes). | (15.00) | No Workplan Needed - Captured in MRT #11309

## Boo Yah
Boo-Yah!